## Slide 1: 1st World Bank Mission under the National Hydrology Project
WRD,Jharkhand

## Slide 2: Core SPMU Details
Name | Designation | Position in SPMU
Mr. Sukhdeo Singh | Principal Secretary | Project Coordinator
Mr. Ashok Ram | Chief Engineer | Nodal Officer
Mr. Rajesh kumar chaudhary | Executive Engineer | Procurement Expert G & C
Mr. P.B Giri | Deputy Director | Procurement Expert I & I
Mr. Ashok Kumar Tanti | Executive Engineer | Project Monitoring & HIS
Mr. Rajesh Kumar | Deputy Director | Project Monitoring Officer
Mr. Suresh Ram | Assistant Engineer | Asst Director (Project Monitoring)
Ms. Hunny Lakra | Assistant Director | Asst Director (Technical)
Other Staff Details - | NHP Staff details JHARKHAND.xlsx | 

## Slide 3: Funds Received
Fund received in financial year 2016-17 on 10/02/2017 is Rs. 1.00 Crore.
Interest accrued by 06/06/2017 is Rs. 121941.46 .
Fund received in financial year 2017-18 on 01/07/2017 is Rs. 2.66 Crore.
Interest accrued by 08/08/2017 is Rs. 157964.79.
Total fund available with interest as on 08/08/2017 is Rs. 3.6879906 Crore.
Expenditure - NIL

## Slide 4: Major Procurement item in PIP
ItemCode | ItemName | UnitPrice (in Lacs) | Quantity(in No.) | Total(in Lacks)
A1.2.01 | DWLR | 1.5 | 137 | 205.5
A1.2.02 | Construction of piezometers | 2 | 118 | 236
A1.2.03 | TEM Aquifer Mapping for Water stressed Areas | 5 | 11 | 55
A1.6.03 | Atomic absorption Spectrophotometre (AAS) | 25 | 1 | 25
A1.6.08 | UV Spectrophotometer ( double beam with high resolution) | 9.11 | 2 | 18.22
A1.6.16 | Double Distillation Apparatus | 8.35 | 2 | 16.7
A1.6.23 | BOD Incubator | 2 | 2 | 4
A1.6.25 | Gas Liquid Chromatograph (GLC) | 60 | 1 | 60
A1.6.28 | Chemicals for Lab Testing | 25 | 1 | 25
A1.8.01 | River Cross section Surveys | 50 | 1 | 50
A1.1.01 | Automatic Weather Station (AWS) with GSM/VSAT | 10 | 5 | 50
A1.1.02 | Digital Rain Guage (DRG) with GSM/VSAT | 4 | 43 | 172
A1.1.03 | Earth Receiving Station for receiving data at data Center through GSM/VSAT/INSAT | 75 | 1 | 75
A1.3.01 | GD Flow Rate Doppler SL 500 with GSM | 12.5 | 3 | 37.5
A1.3.02 | Civil works for GD Flow Rate Doppler | 1.5 | 3 | 4.5
A1.3.03 | ADCP | 25 | 6 | 150
A1.3.05 | Handheld current meters with accessories | 5 | 10 | 50
A1.8.03 | Purchase of DGPS | 23 | 2 | 46
A1.1.13 | AWLR radar (30M) with GSM | 6.05 | 23 | 139.15
A1.1.14 | AWLR radar (30M) with VSAT | 8.5 | 4 | 34
A3.1.01 | Civil Works for Construction of state data and training centre,WQ LAB,HIS | 1000 | 1 | 1000
A3.3.01 | Furnishing works of state data and training centre, WQ Lab, HIS | 150 | 1 | 150
A3.4.01 | Purchase of Computers with Software with AMC | 0.8 | 40 | 32
A3.4.02 | Purchase of Laptops with Software with AMC | 0.81 | 10 | 8.1
A3.4.07 | Procurement of Video Conference Facility | 18 | 1 | 18
A3.4.14 | Network Design | 10 | 1 | 10
A3.4.15 | Network design | 25 | 1 | 25
A3.5.01 | ERDAS Imagine | 4 | 2 | 8
A3.5.02 | Arc GIS | 25 | 1 | 25
A3.5.03 | Antivirus | 0.05 | 40 | 2
A2.2.01 | Procurement of SCADA System for Chandil reservoir operation and its canal system. | 260 | 1 | 260
B2.1.01 | Development of State WRIS chapter including hiring of consultancy, experts,software, integration of data base and India-WRIS | 185 | 1 | 185
B2.2.01 | Procurement of spatial data base and satellite products | 25 | 1 | 25
D1.5.01 | Software for Training Centers | 50 | 1 | 50

## Slide 5: Major Procurement item in AWP 2016-17
Item Code | Item Name | Item Amount (in Lacs) Rs. | Status
A1.7.01.01 | Ground water monitoring equipments (water level indicator, measuring tape, stop watch) | 5 | PP sent for approval on STEP.
A1.7.02.01 | Resistivitymeter | 16 | PP sent for approval on STEP.
A1.8.03.01 | Purchase of DGPS | 46 | PP sent for approval on STEP.
A1.8.04.01 | GPS Handheld | 6 | PP sent for approval on STEP.
A3.4.01.01,A3.4.09.01,A3.4.10.01,A3.4.12.01 A3.5.03.01,A3.4.02.01 | Purchase of computers with softwares , Printer, Plotter scanner, laptop and accessories etc with AMC | 16.78 | PP sent for approval on STEP.

## Slide 6: Major Procurement item in AWP 2017-18
Item Code | Item Name | Item Amount (in Lacs) Rs. | Status
A1.1.06.01,A1.1.02.01,A1.1.03.01,A1.1.05.01,A1.1.13.01,A1.3.01.01,A1.3.02.01,A1.1.14.01 | "Digital Rain Guage (DRG) , AWLR, Flow Rate etcwith GSM/VSAT" with civil works | 288.95 | Bid document uploaded on MIS for approval.
A1.3.03.01 | ADCP with its accessories | 50 | Bid document uploaded on MIS for approval.
A1.2.02.01 | Construction of piezometers | 80 | Bid document under preparation.
D3.1.01.01 | "Establishment of SPMU IT infrastructure, furniture etc)" | 10 | PP sent for approval on STEP.

## Slide 7: Physical Progress
PP of shopping items - Proposed.
Bid document of RTDAS - Completed (Uploaded for review in MIS).
Land Availability for State Data and training centre - Process underway.
Bid document of Piezometers - Process underway.

## Slide 8: Status of Bid Documents
Bid document of shopping items - Ready to be floated
Bid document of RTDAS - Completed (Uploaded for review in MIS).
Bid document of Piezometers - Under preparation.

## Slide 9: Status of various Studies
Studies/PDS has been proposed in 2nd phase of NHP i.e. Post 2020.

## Slide 10: Status of Data entry in E-SWIS
System for data entry in E-SWIS is not yet installed.

## Slide 11: Status of Hydromet Station
GW status of GW Hydromet Stations.pptx
SW status of SW Hydromet stations.xls
List of hydromet stations has been uploaded on mail as per whats app message of NHP group.
No further correspondence.

## Slide 12: Status of State WRIS
Not established.

## Slide 13: Public Finance Management system
Registerd on 22/12/2016.
Agency Unique code : JHRA00004384

## Slide 14: Any other issues
Lack of experience in procurement through World Bank.
World Bank specific Financial Guidelines.
Bid document preparation.
Specifications of Goods.

## Slide 15: Way Forward
Strong mentor state.
Continuous interaction.
Periodic and Regional Training.

## Slide 16: -----Thank You-----