## Slide 1: National Hydrology Project World Bank Mission at Bengaluru (17th and 18th of August 2017)
Kerala SW

## Slide 2: Details of SPMU
State Level Project Steering Committee(SLPSC) Constituted vide Order No GO (MS) No. 22/2017/WRD Dated 28/04/2017
To provide strategic supervision
To provide policy guidance and steering support
Structure of SLPSC
i | The Secretary, WRD | Chairperson
ii | The Director, IDRB | Convener
iii | The Secretary, Finance Dept. | Member
iv | The Special Secretary, LSGD | Member
v | Representative from Agricultural Dept. | Member
vi | Representative from Forest Dept. | Member
vii | The Chief Engineer, CWC, Coimbatore | Member
viii | The Regional Director, CGWB | Member
ix | The Chief Engineer, IDRB | Co-ordinator (SW)
x | The Director, GWD | Co-ordinator (GW)
Slide 1

## Slide 3: Details of SPMU
Water Resources Department, Govt. of Kerala have constituted the SPMU for National Hydrology Project in respect of Surface Water with 19 Officials vide order GO (MS) No. 44/2016/WRD Dated, Thiruvananthapuram, 15/07/2016
The SPMU is headed by the Chief Engineer (I&D), IDRB as the Co-ordinator and Project Director of NHP.
Director, IDRB is the Nodal Officer of NHP
Slide 1 contd…

## Slide 4: SPMU Members
Sl No | Position in SPMU | Nos
1 | Co-ordinator & Project Director | 1
2 | Nodal Officer | 1
3 | Sr. Water Management Expert | 1
4 | Hydrologist | 1
5 | Modeller | 2
6 | Hydro-Met Instrumentation Expert | 2
7 | Database Management Expert | 1
8 | IT/Web Designing Expert | 1
9 | GIS Expert | 1
10 | Data Entry Operator | 2
11 | Accounts Officer | 1
12 | Assistant Accounts Officer | 1
13 | Procurement Expert (Instrument / IT related) | 1
14 | Procurement Expert (Goods and Consultancy) | 1
15 | MIS Expert | 1
16 | M&E Expert | 1
Slide 1 contd….

## Slide 5: Funds Received & Expenditure
2016-17 |  | 2017-18 | 
Funds Received (Rs. In Lakhs) | Expenditure till date | Funds Received (Rs. In Lakhs) | Expenditure till date
92.83 | 6.76 | 209 | Nil
Slide 2

## Slide 6: Major Procurement Item in PIP
Item Code | Item | Amt (Rs. lcs)
A1.1.01 | RTDAS for Kerala River Basins | 565.60
A1.1(02-06) | Installation of RTDAS (Civil work) | 92.00
A1.3 (01 -06) | Discharge Measurement Equipment | 132.00
A1.4 &A1.6 | Water Quality Equipments | 75.00
A1.7 & A1.8 | Manual Observation and Survey Equipment | 82.50
A2.2.01 | Canal SCADA for System | 175.00
A3.2.01 | Renovation of Data Centre at Thiruvananthapuram | 100.00
A3.4 (01-10) | IT Equipment for Data Centres and WRIS Centre | 157.50
B2.2.01 | Development of State WRIS | 100.00
C1.1.01 | Development of DSS & IWRM | 300.00
C1.2 | Flood forecasting study | 80.00
D1.2 | Rennovation of Knowledge centre | 70.00
Slide 3

## Slide 7: Major Procurement Item in AWP 2016-17 and their status
Item Code | Item | Amt (Rs.Lcs) | Present Status
A1.3.01.01 & A1.3.02.01 | Procurement of Current Meter with accessories - Cup Type-22 Nos and Digital Type-1 No | 8.60 | PP uploaded in STEP. E5 document under finalization. Specification to be finalized by Technical committee.
A1.3.03.01 | Bridge outfit – 2 Nos | 2.00 | “
A1.3.05.01 | Staff Gauge – 124 Nos | 2.48 | “
A1.6.02.01 | Analytical Balance and Water Quality analyser, for Level I Labs | 2.00 | “
A1.8.02.01 | Automatic Level – 2 Nos | 0.5 | “
A1.8.03.01 | GPS Hand held – 18 Nos | 9.00 | “
A3.4.01.01 & A3.4.06.01 | Computers and UPS – 13 Nos Printers – 10 Nos | 9.00 | “
Slide 4

## Slide 8: Major Procurement Item in AWP 2017-18 and their status
Item Code | Item | Amt (Rs.Lcs) | Present Status
A1.1.01.01 | Procurement of RTDAS and it’s installation | 597.00 | Locations identified and submitted to CWC, Coimbatore for approval. Expected to be finalised before 25th August 2017.
A1.1.05.01 | Survey work for establishing Bench Mark in 36 River Gauge stations and Civil works in 6 sites. | 40.73 | Online PP approved. Detailed estimate under preparation.
A1.3 (01-06) &A1.7 | Procurement of Hydro-meteorological Equipment Such as Current meter Cup type – 25 Nos Current meter Digital type – 8 Nos Bridge outfit – 8 Nos Echosounder – 1 and Staff Gauges (LS) | 56.84 | Technical specification to be finalized.
Slide 5

## Slide 9
A1.3.04.01 | Discharge Measurement Equipment - installation of Cableways at 7 River Gauge Stations | 39.00 | Technical specification to be finalized.
A1.6 (01-03) | Water Quality Lab Equipment : Salinity measuring equipment – 12 Nos, Analytical Balance-4 Nos, WQ Analyser-4 Nos, p H Analyser-1 No, EC-TDS Analyser-1 No, Distillation Apparatus- 1No, DO measuring equipment- 1No | 11.20 | “
A1.7 & A1.8 | Manual Observation and Survey Equipment (LS) | 37.93 | “
A1.8 (01-04) | Field Survey equipment Total Station – 2 Nos Automatic Level – 1 GPS Hand held – 1 Differential GPS – 2 Nos | 28.81 | “
Slide 5 contd…

## Slide 10
A3.4 (01-10) | Procurement of Data base server and accessories for WRIS and RTDAS and other IT equipment: Server – 1 Workstations – 2 Nos Computer – 20 Nos Printers – 15 Nos. | 34.21 | “
B2.2.01.01 | Consultancy service for developing State WRIS | 50.00 | “
D1.2.01.01 | Upgradation of Training Centre | 55.00 | “
Slide 5 contd…

## Slide 11: Physical Progress
In house training conducted on Q GIS, Web GIS, HEC-RAS and EPANET.
Identified locations for the installation of RTDAS. Hyro-Met network under finalization.
Procurement Plan uploaded in the STEP and approval awaited.
Terms of Reference for the Consultancy service of State WRIS formulated.
Data collection for developing DSS initiated.
Officers attended national training programme on HEC-RAS and International workshop on Hydro Met Instrumentation.
Gauging is being conducted for 54 GD stations and 140 Met stations.
In House training programme on Basic Hydrology lead by NIH, Belgaum, planned in the second week of October 2017.
Slide 6

## Slide 12: Status of Bid Document
Draft E1 document for the procurement of RTDAS for Rs.597 lakhs uploaded in MIS of NHP: Suggestions/ Approval awaited
Draft E5 Document for procuring of Hand held GPS, Current Meter and Staff Gauge uploaded in MIS : It is suggested by the MoWR that shopping method does not warrant prior review and procurement can be carried out as per World Bank guidelines and complying with the approved PIP, AWP and PP. Hence action is being taken to procure the instruments as per the guidelines.
Slide 7

## Slide 13: Status of various studies/PDS
Sl No | Description of Studies | Present Status
1 | Measurement of Discharge of the Flowing Stream using Image Processing Techniques in Muvattupuzha River Basin | Presented in the First R&D session on PDS at NIH, Roorkee. Awaiting approval.
2 | Sediment Assessment of Reservoirs | “
3 | Water Security and Sustainable Agricultural Productivity through Holistic Management of Ponds in the Command of Neyyar Irrigation Project in Kerala with Stakeholder Participation | “
4 | Evolving an Integrated Water Resources Management Model for the Rejuvenation and Environmental Sustainability of Pulamonthodu Stream in Kerala through Stakeholders’ Participation | “
5 | Assessment of Water Quality status and evolving Mitigation measures to improve the Water Quality of Thrissur Corporation | Revised proposal based the comments of NIH submitted .
6 | Assessment on the extent of Saline Ingress along the Rivers and Coastal stretches of Kerala | Modification of the proposal based on the reviewers comments is underway.
Slide 8

## Slide 14: Status of Data entry in E-SWIS
  Data entry in E-SWIS is not yet started due to lack of trained staff.
  5 officials are nominated for the E-SWIS training to be conducted at NWA, Pune during November 2017.
  At present data entry is being done in SWDES and it is noted that there is an option for importing SWDES data base in E-SWIS.
  We are also planning to conduct in house training programme on E-SWIS as per the convenience of CWC
Slide 9

## Slide 15: Status of Hydro-met stations, Reconciliation with state, CGWB, CWC, IMD etc.
Maintenance and Gauging of 54 GD Stations and 140 Meteorological stations are established/upgraded in Phase I & II of HP is being done using NHP fund.
New proposal
Proposed to upgrade the following stations to RTDAS
Rain Gauge Station (TBRG) : 65 Nos
Automatic Weather Station (AWS): 9
Gauge Discharge stations (RLS) : 28
Water Level stations _Tidal (RLS) : 8
Water Level Reservoirs/Barrage : 11
Additional GSM Telemetry in existing DWLR stations: 2
Reconciliation of Hydrological stations with CWC is under finalization
Reconciliation of Meteorological station with IMD is pending
Slide 10

## Slide 16: Status of State WRIS
Terms of Reference (ToR) as per World Bank guidelines formulated and submitted
Cost estimate for consultancy service framed ( Estimate cost Rs. 43 Lakhs including tax)
Main objective of the State WRIS are
To collect available data from varied sources, generate new database, organize in standardized GIS format and provide scalable web-enabled information system.
To provide easier and faster access for sharing of DATA
To provide tools to create value added maps
To provide foundation/data/reports for modeling, river basin planning and future Spatial Decision Support Systems (SDSS) & automated data collection system.
Institutional strengthening.
Slide 11

## Slide 17: Status of State WRIS
Indian Institute of Information Technology and Management-Kerala (IIITM-K), an autonomous institute functioning under the Dept. of Information Technology, Govt. of Kerala have been identified as the local consultant for developing WRIS.
Procurement method is Single Source Selection (SSS)
Scope of Consultancy Services
Develop a well designed user friendly Water Resources portal displaying all layers related to Water Resources of the state.
Linkage of Real time data.
Integration/linkages with modules e-SWIS, e-GEM, e-WQ and DSS.
Web feature services and Mobile App for citizen for alerts, warnings, information on canal operations and WQ.
Hands on training to departmental officers.
Slide 11 contd..

## Slide 18: Status of State WRIS
Deliverables: 1. Web based WRIS
2. River Basin Atlas of Kerala containing all maps related to WR
3. Webinars
4. Tutorials and Reports
Duration of the Project: 15 months. Then 5 years for maintenance and update of the system.
Client’s Input : Data and Study report
Slide 11 contd..

## Slide 19: Status of Public Finance Management System
Finance Staff needed training . Hence not initiated.
Slide 12

## Slide 20: Any other issues
National/International consultancy required for developing DSS & IWRM and Flood forecasting studies
Required high resolution DEM for modeling purpose
Software for DSS – MIKE BASIN or other Domain Software
Placing RLS in bridges – Need sanction from Public Works Department
Whether river cross sections to be surveyed for DSS or DEM is sufficient
Payment for Gauge readers pending eventhough Financial sanction issued under NHP.
Slide 13

## Slide 21: Way forward
Outcome
Following parameters will have to be identified and is to be monitored for the successful completion of the project
Issues in the water sector in each River Basin. This will be identified with Haritha Kerala Mission and convening workshops
Solutions to the issues on Water availability, Irrigation requirement, WQ etc.
Solutions shall be vetted by conducting workshops by Stake holders
Transferring the solutions to the implementing agencies
Implementation of solutions
Social Auditing of Outcomes and Data collection
This will perfect the outcomes and will help in improving the quality of data collection.
Slide 14

## Slide 22
Thank You