## Slide 1
1st World Bank Mission under the National Hydrology Project
Period - 17th August to 18th August 2017
WEL COME
Maharashtra (SW)

## Slide 2: SPMU (in position) Composition of SPMU-WRD / MAHARASHTRA SW
Name & Designation | Name & Designation | Name & Designation | Name & Designation
1. Shri. I. S. Chahal Principal Secretary & Project Co-ordinator | 7. Ms. P. C. Katkade Modeller | 13. Ms. D. K. Rupanwar, Hydromet Instrumentation Expert | 19. Smt. D. A. Joshi Procurement Expert
2. Shri. D. R. Joshi Nodal Officer | 8. Ms. S. C. Jadhav Modeller | 14. Shri. S. B. Thakur Data Management Expert | 20. Ms. P. M. Shinde Procurement Expert
3. Shri. A. S. More Controlling Officer | 9. Shri. S. K. Kshirsagar Modeller | 15. Ms. R. H. Shinde IT/ Web Design Expert | 21. Shri. S. G. Mohite MIS Expert
4. Shri. R. A. Shimpi Sr. Water Management Expert | 10. Shri. S. B. Chavan Modeller | 16. Shri. M. B. Nakil GIS Expert | 22. Smt. D. S. Khapli MIS Expert
5. Shri. A. A. Pandit Hydrologist | 11. Shri. M. D. Kayarkar Modeller | 17. Smt. V. P. Jadhav Accounts Officer | 23. Shri. D. S. Ket M & E Expert
6. Shri. S. V. Bachhav Hydrologist | 12. Shri. D. K. Madankar Hydromet Instrumentation Expert | 18. Smt. R. L. Barde Asst. Accounts Officer | 24. Smt. R. H. Chavan Data Entry Operator
1

## Slide 3
For the Year | Grant Received from Central Government (In Million INR) | Interest received on Saving Bank Account (In Million INR) | Total Grant (In Million INR) | Expenditure for the Year (In Million INR)
2016-2017 | 36.84 | 0.20 | 37.04 | Nil
2017-2018 | 73.30 | 0.36 | 73.66 | 8.43
Total - | 110.14 | 0.56 | 110.70 | 8.43
2
Funds Received (2016-17), (2017-18) & expenditure till date

## Slide 4: Major Procurement Item in PIP
Item Code | Item Name | Amount (Rs. In Lakhs)
A1.1.01, A1.1.03, A1.1.05, A1.1.07, A1.1.08 | RTDAS with Civil Work for Tapi, Godavari, WFR of Kokan & remaining part of Krishna basin. | 6206.43
A1.1.02, A1.1.04, A1.1.06 | Upgradation & Renovation of Existing RTDAS for all basins in Maharashtra state. | 191.60
A1.10.01, C1.3.01 | SCADA system for Reservoir Operation of Waghur Dam & development of smart irrigation system of Tillari reservoir & canals. | 700.30
A1.3.01, A1.3.02 | Procurement of 4 River Survey Instrument (ADCP) with 5 vans. | 190.54
A1.5.01, A1.5.02, A1.5.04 | Renovation, Furnishing & NABL Accreditation of existing WQ labs in the state & Establishing new WQ lab in Tapi basin. | 119.28
A1.6.01, A1.6.02 | Procurement of WQ lab equipments for existing WQ labs & new WQ lab in Tapi basin. | 170.00
A1.7.01 | Procurement & Fixing of existing Hydromet observation network equipment in the state. | 150.00
A1.8.02 | Providing , Installing & Commissioning of IBS Instrument with Bathymetric Software & Survey Boat. | 161.50
A3.1.01, A3.1.02, A3.4.01, A3.4.02 | Construction of Regional Data Center & procurement of Equipments, Hardware & Software. Integration of Existing RTDAS system in Regional & State Data Centers. Renovation & furnishing of Divisional & Sub-Divisional Data Centers. | 800.30
B2.1.01 | Upgradation of Existing Hydrology Project Web. | 250.00
B2.2.02, C1.2.03 | Procurement of High Resolution maps for Flood Risk Mapping. Flood risk & vulnerability mapping using digital survey data of 4 Major Flood prone cities ( Pune, Pandhpur,Sangli & Chandrapur ) | 250.00
3-A

## Slide 5: Major Procurement Item in PIP
Item Code | Item Name | Amount (Rs. In Lakhs)
B2.6.01, B2.7.01 | Installation of Real Time Display Boards of RTDAS & Development of Mobile App for RTSF & ROS of Krishna Basin. | 170.00
C1.1.01, C1.1.02, C1.1.03, C1.1.04. | River Basin planning for Water Management in Tapi, Godavari & Krishna Basin. | 1065.00
C1.2.02 | Extension of Existing RTSF & ROS system of Krishna & Bhima Basin for Remaining area of South of Panchganga. | 130.00
C1.2.04 | Development of Mathematical model for flood estimation for different basins in Maharashtra. | 100.00
C2.3.01, C2.3.02, C2.3.03, C2.4.01, C2.4.02, | Purpose Driven Studies for 1) Dam Brake Analysis & Modelling for three reservoirs. 2) Enviromental Flow Assessment for Koyna & Panchanganga River, 3) Climate Change Impact Assessment for Godavari Basin 4) Assessment of Regeneration flow in Purna River 5) Study for Conjunctive use of Surface & Ground water for Purna Irrigation Project. | 260.00
D1.2.01, D1.3.01, D3.1.01 | Renovation of Jalvidnyan Bhavan with State Data Center & Training Center. Establishment of SPMU & E-Class Room. | 455.00
D1.4.01, D1.4.02 | Institutional Modernization Support, including IT systems & Softwares. Installation of Internet lease line & its recurrent charges for all data centers. | 250.00
D2.1.01, D2.2.01, D2.3.01, D2.4.01 | Capacity Building by way of training & higher education. | 500.00
D3.1.03, D3.1.05 | Procurement of Inspection Vehicles & Hiring charges for vehicles. | 298.00
D4.1.01, D4.1.02 | Hiring of IT Experts, WQ Experts, Tech. experts & Hydrologist etc. | 400.00
D4.1.03, D4.1.04 | Hiring of office staff & field staff. | 460.00
3-B

## Slide 6: Major Procurement Item in AWP 2016-17
Item Code | Item Name | Amount (Rs. In Lakhs)
A1.5.01 | Renovation & Furnishing of Existing Water Quality Labs in the State. | 44.00
A1.9.02 | A.M.C. of Existing RTDAS for balance 3 years under ongoing contract for Krishna. | 135.00
C1.2.01 | Operation charges for 2 Years of Existing RTSF & ROS (Flood forecasting)system of Krishna & Bhima River Basins in Maharashtra. | 20.00
D1.2.01 D3.1.01 | Renovation of Jalvidnyan Bhavan and establisment of SPMU with furnishing at Jalvidnyan Bhavan. | 24.20
D1.4.01 | Institutional Modernization Support, incl. IT systems & software. | 69.25
D3.1.03 | Procurement of 6 Inspection Vehicles. | 16.00
D3.1.05 | Hiring charges for vehicles during implementation of NHP. | 10.00
4

## Slide 7: Major Procurement Item in AWP 2017-18
Item Code | Item Name | Amount (Rs. In Lakhs)
A1.1.01, A1.1.03, A1.1.05, A1.1.07, A1.1.08 | RTDAS with Civil Work for Tapi, Godavari, WFR of Kokan & remaining part of Krishna basin. | 275.00
A1.1.02, A1.1.04, A1.1.06 | Upgradation & Renovation of Existing RTDAS for all basins in Maharashtra state. | 34.75
A1.10.01, C1.3.01 | SCADA system for Reservoir Operation of Waghur Dam & development of smart irrigation system of Tillari reservoir & canals. | 55.00
A1.3.01, A1.3.02 | Procurement of 4 River Survey Instrument (ADCP) with 5 vans. | 86.50
A1.4.01 | Procurement of Portable water Quality Sondes for Water Quality labs in the state. | 42.00
A1.5.02, A1.5.04 | Establishing new WQ lab in Tapi basin & NABL Accreditation of existing WQ labs in the state. | 37.50
A1.6.01, A1.6.02 | Procurement of WQ lab equipments for existing WQ labs in the state. | 103.39
A1.7.01 | Procurement & Fixing of existing Hydromet observation network equipment in the state. | 98.43
A3.1.01, A3.1.02, A3.4.01, A3.4.02 | Construction of Regional Data Center & procurement of Equipments, Hardware & Software. Integration of Existing RTDAS system in Regional & State Data Centers. Renovation & furnishing of Divisional & Sub-Divisional Data Centers. | 202.50
B2.1.01 | Upgradation of Existing Hydrology Project Web. | 25.00
5-A

## Slide 8: Major Procurement Item in AWP 2017-18
Item Code | Item Name | Amount (Rs. In Lakhs)
B2.7.01 | Development of Mobile App for RTSF & ROS of Krishna Basin. | 20.00
C1.1.01, C1.1.02, C1.1.03, C1.1.04. | River Basin planning for Water Management in Tapi, Godavari & Krishna Basin. | 40.00
C1.2.02 | Extension of Existing RTSF & ROS (Flood forecasting) system of Krishna & Bhima River Basin for remaining area of South of Panchganga in Krishna basin. | 40.00
C2.3.01, C2.3.02, C2.3.03, C2.4.01, C2.4.02, | Purpose Driven Studies for 1) Dam Brake Analysis & Modelling for three reservoirs. 2) Enviromental Flow Assessment for Koyna & Panchanganga River, 3) Climate Change Impact Assessment for Godavari Basin 4) Assessment of Regeneration flow in Purna River 5) Study for Conjunctive use of Surface & Ground water for Purna Irrigation Project. | 110.00
D1.2.01, D1.3.01, D3.1.01 | Renovation of Jalvidnyan Bhavan with State Data Center & Training Center. Establishment of SPMU & E-Class Room. | 177.23
D2.1.01, D2.2.01, D2.3.01, D2.4.01 | Capacity Building by way of training & higher education. | 42.00
D3.1.03, D3.1.05 | Procurement of Inspection Vehicles & Hiring charges for vehicles. | 72.00
D4.1.01, D4.1.02 | Hiring of IT Experts, WQ Experts, Tech. experts & Hydrologist etc. | 35.50
D4.1.03, D4.1.04 | Hiring of office staff & field staff. | 95.00
5-B

## Slide 9
Physical Progress – Completed, Process underway, Proposed
6-A
Item Code | Item Name | Progress Type
C1.2.01 | Operation Charges for 2 Years of Existing RTSF & ROS (Flood forecasting) system of Krishna & Bhima River Basins in Maharashtra. | Completed
A.1.9.02 | A.M.C. of Existing RTDAS for balance 3 years under ongoing contract for Krishna | Process underway
D1.4.01 | Institutional Modernization Support, incl. IT systems & software. | Process underway
D3.1.03 | Procurement of 6 Inspection Vehicles. | Process underway
A1.1.01, A1.1.03, A1.1.05, A1.1.07, A1.1.08 | RTDAS with Civil Work for Tapi, Godavari, WFR of Kokan & remaining part of Krishna basin. | Proposed
A1.1.02, A1.1.04, A1.1.06 | Upgradation & Renovation of Existing RTDAS for all basins in Maharashtra state. | Proposed
A1.10.01, C1.3.01 | SCADA system for Reservoir Operation of Waghur Dam & development of smart irrigation system of Tillari reservoir & canals. | Proposed
A1.3.01, A1.3.02 | Procurement of 4 River Survey Instrument (ADCP) with 5 vans. | Proposed
A1.4.01 | Procurement of Portable water Quality Sondes for Water Quality labs in the state. | Proposed
A1.5.02, A1.5.04 | Establishing new WQ lab in Tapi basin & NABL Accreditation of existing WQ labs in the state. | Proposed
A1.6.01, A1.6.02 | Procurement of WQ lab equipments for WQ labs in the state. | Proposed
A1.7.01 | Procurement & Fixing of existing Hydromet observation network equipment in the state. | Proposed
A3.1.01, A3.1.02, A3.4.01, A3.4.02 | Construction of Regional Data Center & procurement of Equipments, Hardware & Software. Integration of Existing RTDAS system in Regional & State Data Centers. Renovation & furnishing of Divisional & Sub-Divisional Data Centers. | Proposed

## Slide 10
Physical Progress – Completed, Process underway, Proposed
6-B
Item Code | Item Name | Progress Type
B2.1.01 | Upgradation of Existing Hydrology Project Web. | Proposed
B2.7.01 | Development of Mobile App for RTSF & ROS of Krishna Basin. | Proposed
C1.1.01, C1.1.02, C1.1.03, C1.1.04. | River Basin planning for Water Management in Tapi, Godavari & Krishna Basin. | Proposed
C1.2.02 | Extension of Existing RTSF & ROS (Flood forecasting) system of Krishna & Bhima River Basin for remaining area of South of Panchganga in Krishna basin. | Proposed
C2.3.01, C2.3.02, C2.3.03, C2.4.01, C2.4.02, | Purpose Driven Studies for 1) Dam Brake Analysis & Modelling for three reservoirs. 2) Enviromental Flow Assessment for Koyna & Panchanganga River, 3) Climate Change Impact Assessment for Godavari Basin 4) Assessment of Regeneration flow in Purna River 5) Study for Conjunctive use of Surface & Ground water for Purna Irrigation Project. | Proposed
D1.2.01, D1.3.01, D3.1.01 | Renovation of Jalvidnyan Bhavan with State Data Center & Training Center. Establishment of SPMU & E-Class Room. | Proposed
D2.1.01, D2.2.01, D2.3.01, D2.4.01 | Capacity Building by way of training & higher education. | Proposed
D3.1.05 | Hiring charges for vehicles. | Proposed
D4.1.01, D4.1.02 | Hiring of IT Experts, WQ Experts, Tech. experts & Hydrologist etc. | Proposed
D4.1.03, D4.1.04 | Hiring of office staff & field staff. | Proposed

## Slide 11
Status of Bid Document – Floated, Ready to be floated, Under Preparation
7-A
Item Code | Item Name | Status of Bid Document
D3.1.05 | Hiring charges for vehicle during Implementation of NHP for Krishna basin | Floated
B2.3.01 | Digitize paper data, documents, design, drawings & scanned reports for Krishna Basin. | Ready to be floated
A1.1.01, A1.1.03, A1.1.05, A1.1.07, A1.1.08 | RTDAS with Civil Work for Tapi, Godavari, WFR of Kokan & remaining part of Krishna basin. | Under preparation
A1.1.02, A1.1.04, A1.1.06 | Upgradation & Renovation of Existing RTDAS for Tapi, Godavari basin | Under preparation
A1.10.01, C1.3.01 | SCADA system for Reservoir Operation of Waghur Dam & development of smart irrigation system of Tillari reservoir & canals. | Under preparation
A1.3.01, A1.3.02 | Procurement of 4 River Survey Instrument (ADCP) with 5 vans. | Under preparation
A1.4.01 | Procurement of Portable water Quality Sondes for Water Quality labs in the state. | Under preparation
A1.5.02, A1.5.04 | Establishing new WQ lab in Tapi basin & NABL Accreditation of existing WQ labs in the state. | Under preparation
A1.6.01, A1.6.02 | Procurement of WQ lab equipments for WQ labs in the state. | Under preparation
A1.7.01 | Procurement & Fixing of existing Hydromet observation network equipment in the state. | Under preparation
A3.1.01, A3.1.02, A3.4.01, A3.4.02 | Construction of Regional Data Center & procurement of Equipments, Hardware & Software. Integration of Existing RTDAS system in Regional & State Data Centers. Renovation & furnishing of Divisional & Sub-Divisional Data Centers. | Under preparation
B2.1.01 | Upgradation of Existing Hydrology Project Web. | Under preparation
B2.3.01 | Digitize paper data, documents, design, drawings & scanned reports for remaining basins of Maharashtra | Under preparation

## Slide 12
Item Code | Item Name | Status of Bid Document
B2.7.01 | Development of Mobile App for RTSF & ROS of Krishna Basin. | Under preparation
C1.1.01, C1.1.02, C1.1.03, C1.1.04. | River Basin planning for Water Management in Tapi, Godavari & Krishna Basin. | Under preparation
C1.2.02 | Extension of Existing RTSF & ROS (Flood forecasting) system of Krishna & Bhima River Basin for remaining area of South of Panchganga in Krishna basin. | Under preparation
C2.3.01, C2.3.02, C2.3.03, C2.4.01, C2.4.02, | Purpose Driven Studies for 1) Dam Brake Analysis & Modelling for three reservoirs. 2) Enviromental Flow Assessment for Koyna & Panchanganga River, 3) Climate Change Impact Assessment for Godavari Basin 4) Assessment of Regeneration flow in Purna River 5) Study for Conjunctive use of Surface & Ground water for Purna Irrigation Project. | Under preparation
D1.2.01, D1.3.01, D3.1.01 | Renovation of Jalvidnyan Bhavan with State Data Center & Training Center. Establishment of SPMU & E-Class Room. | Under preparation
D2.1.01, D2.2.01, D2.3.01, D2.4.01 | Capacity Building by way of training & higher education. | Under preparation
D3.1.05 | Hiring charges for vehicles for remaining basins of Maharashtra. | Under preparation
D4.1.01, D4.1.02 | Hiring of IT Experts, WQ Experts, Tech. experts & Hydrologist etc. | Under preparation
D4.1.03, D4.1.04 | Hiring of office staff & field staff. | Under preparation
Status of Bid Document – Floated, Ready to be floated, Under Preparation
7-B

## Slide 13
Purpose Driven Studies (PDS)
Sr. No. | Name of Purpose Driven Studies (PDS) | Submission Date | Review
1 | Environmental flow assessment of Krishna basin with special reference to Panchaganga and Koyna rivers. | 18/07/2017 | Under Review
2 | Study for assessment of regeneration flow in Purna irrigation project in Godavari basin in Maharashtra. | 20/07/2017 | Under Review
3 | Study for conjunctive use of surface and ground water for Purna irrigation project. | 20/07/2017 | Under Review
4 | Dam break analysis and modeling with preparation of emergency action plan for upper Wardha project, Dist-Amravati, Ujani project, Dist-Solapur & Gangapur Project, Dist-Nashik in the state of Maharashtra. | 20/07/2017 | Under Review
5 | Climate change impact assessment for Jayakwadi project. | 01/08/2017 | Under Review
8

## Slide 14
9
Status of Data entry in E-SWIS
We have requested NPMU, to arrange training programme of E-SWIS to the field officers of Hydrology Project (Surface Water) Maharashtra state vide letter no. SPMU/Tech/Training/67/2017, dated 13/07/2017.
Now the proposed requested dates are
04/10/2017 to 06/10/2017
01/11/2017 to 03/11/2017
15/11/2017 to 17/11/2017
Data entry in E-SWIS will be initiated after completion of training programme.

## Slide 15
10
Status of Hydromet Station (SW), reconciliation with State, CGWB, CWC, IMD etc.
Sr. No. | Type of Station | No of Stations |  | 
 |  | GSM | VSAT | Total
1 | Automatic Weather Stations (AWS) | 15 | 4 | 19
2 | Automatic Raingauge Stations (ARS) | 235 | 115 | 350
3 | Automated River Water Level & Discharge Station | 57 | 29 | 86
4 | Automated Pan Evaporimeter | 5 | 77 | 82
5 | Automated Reservoir Water Level & Outflow Discharge Station | 0 | 134 | 134
6 | Automated Spillway gate sensor | 0 | 737 | 737
CWC, Nagpur is in contact with SPMU & Executive Engineer, Hydrology Project Division, Nagpur for reconciliation of Hydromet stations in Wainganga Sub basin of Godavari.
We have requested to CWC Hyderabad & Gandhinagar offices for reconciliation of Hydromet Stations in Tapi, Krishna, Godavari & West Flowing Rivers basin coming under their jurisdiction.

## Slide 16
Status of State WRIS
Item Code | Item Name | Status
B2.1.01 | Upgradation of Existing Hydrology Project Web site with State level portal for RTDAS & Development of State Chapter of India-WRIS. | Under preparation
B2.3.01 | Digitisation of paper data, documents, design, drawings & scanned reports. | Under preparation
B2.6.02 | Providing Video conferencing facility at Jalvidnyan Bhavan, Nashik & Field Offices under Hydrology Project, development of E-library. | Under preparation
B2.7.01 | Development of Mobile App for RTSF & ROS of Krishna & Bhima Basin. | Under preparation
B2.2.01 | Procurement of GIS/Satellite Image Database for River Basins in Maharashtra | Will be taken up in future
B2.2.02 | Procurement of High Resolution maps for Flood Risk Mapping of 4 Major Flood prone cities (Pune, Pandharpur, Sangli & Chandrapur) | Is being undertaken in liason with NRSC
B2.2.03 | Procurement of short & medium range weather forecasting products for RTSF-ROS. | Will be taken up in future
B2.4.01 | Up gradation of Existing Web Portal for RTSF & ROS. | Will be taken up in future
B2.6.01 | Installation of Real Time Display Boards of RTDAS for dissemination of Data to public/office. | Will be taken up in future
11

## Slide 17: Status in Public Finance Management System (PFMS)
Registration forms are submitted to PFMS wing.
Registration in PFMS is under progress.
12

## Slide 18: Any other issues
How to quote condition about GST as registration under GST is under process at all levels.
2) Sufficient no. of participants needs to be permitted for various trainings organized by MOWR & World Bank for effective capacity building.
3) Requirement for Standard Bid Documents for following types
a) e-tender document for shopping .
b) e-tender document for ICB Goods.
c) Whether to adopt State Govt. guidelines.
4) Guidance about procurement for hiring the services of experts.
13

## Slide 19: Way forward
SPMU is conducting weekly internal review meeting of SPMU team.
SPMU has started conducting monthly review meeting of field officers to strengthen field staff.
Capacity Building of staff .
Monthly review meetings by field Executive Engineers.
Decentralization of disbursement of funds to field Executive Engineers to expedite the programme and to maintain accounts in required format & Financial Manual /Guidelines.
6) Need of Regional team of NHP, MoWR and World Bank to assist IA’s.
14

## Slide 20
THANK YOU