## Sheet1
Rs in Lacs
|  | Amount | Proposed % | % Suggested
A | Water Resources Data Acquisition System | 4298.3 | 60.63% | 60%
B | Water Resources Information System (WRIS) | 350 | 4.937% | 5%
C | Water Resources Operation and Planning | 1050 | 14.81% | 15%
D | Institutions Capacity Enhancement | 1391 | 19.62% | 20%
| Total | 7089.3
| Celling Limit | 7100

## Cost Summary
COST SUMMARY
Agency:- Gujarat Surface Water
Sum of Total Cost, Lakhs
Component ID | Total |  | Actual % | Required % | Required Amount | Required Amount
A | 4298.3 | 4298.3 | 60.63% | 60% | 4200 | 4260
B | 350 | 350 | 4.937% | 5% | 350 | 355
C | 1050 | 1050 | 14.81% | 15% | 1050 | 1065
D | 1391 | 1391 | 19.62% | 20% | 1400 | 1420
(blank) | 14178.6
Grand Total | 21267.9 | 7089.3 |  |  | 7000 | 7100

## PIP Cost Tab
National Hydrology Project
PROJECT IMPLEMENTATION PLAN (PIP)
Name of Agency: GUJARAT SURFACE WATER
Component ID | Sub Component ID | Activity ID | Activity | Item Code | Items | Type | Quantity | Unit Cost, Lakhs | Total Cost, Lakhs | Comment | Procurement Type (ICB/ NCB/ Shopping/Single Source)
A |  |  | Water Resources Data Acquisition System
A | A1 |  | Water Data Acquisition System
A | A1 | A1.1 | Real Time Data Acquisition System (RTDAS) for Surface Water | A1.1.01 | RTDAS for Gujarat | Goods | 1 | 2853 | 2853 |  | NCB
A | A1 | A1.1 | Real Time Data Acquisition System (RTDAS) for Surface Water | A1.1.02 | Major Civil Works for Hydromet | Works | 1 | 0.5 | 0.5 |  | NCB
A | A1 | A1.1 | [6 empty] | 0
A | A1 | A1.1 | [6 empty] | 0
A | A1
A | A1 | A1.2 | Real TimeGroundwater Measurement | [5 empty] | 0
A | A1 | A1.2 | [6 empty] | 0
A | A1
A | A1
A | A1 | A1.3 | Discharge Measurement Equipment | A1.3.01 | Boats with Outboard engines | Goods | 2 | 50 | 100 |  | NCB
A | A1 | A1.3
A | A1
A | A1
A | A1
A | A1 | A1.4 | Real Time Water Quality Equipment | [5 empty] | 0 |  | NCB
A | A1
A | A1
A | A1
A | A1 | A1.5 | Water Quality Labs | A1.5.01 | Mobile Water Quality Lab | Goods | 5 | 25 | 125 |  | NCS/single source
A | A1 | A1.5 | Water Quality Labs | A1.5.02 | Furnishing Water Qulity labs with equipments & peripherals | Goods | 1 | 26 | 26 |  | Shopping
A | A1 | A1.5 | [6 empty] | 0
A | A1 | A1.5 | [6 empty] | 0
A | A1
A | A1
A | A1
A | A1 | A1.6 | Water Quality Lab Equipment | [5 empty] | 0
A | A1 | A1.6 | [6 empty] | 0
A | A1 | A1.6 | [6 empty] | 0
A | A1 | A1.6 | [6 empty] | 0
A | A1 | [7 empty] | 0
A | A1 | [7 empty] | 0
A | A1 | [7 empty] | 0
A | A1 | A1.7 | Manual Observation Equipment | [5 empty] | 0
A | A1 | [7 empty] | 0
A | A1 | [7 empty] | 0
A | A1 | [7 empty] | 0
A | A1 | [7 empty] | 0
A | A1 | [7 empty] | 0
A | A1 | A1.8 | Field Surveys | A1.8.01 | Bathymetric survey of reservoirs/rivers | NCS | 1 | 100 | 100 | LS Provision | NCB
A | A1 | A1.8 | Field Surveys | A1.8.02 | GPS – Hand held Type2 | Goods | 2 | 0.5 | 1 |  | Shopping
A | A1
A | A1
A | A1
A | A1 | A1.9 | O&M of existing System | A.1.9.01 | AMC for Existing RTDAS Weather Stations for 3 years ongoing contract | O&M | 50 | 0.66 | 33 |  | Ongoing works of HP-II
A | A1 | A1.9 | O&M of existing System | A.1.9.02 | AMC+ Retro fitting for Existing RTDAS Weather Stations for further 5 years ongoing contract. | O&M | 50 | 2 | 100 |  | NCB, in contunition to above
A | A1 | A1.9 | O&M of existing System | A.1.9.03 | AMC for Existing RTDAS Rivergauging Stations for 3 years ongoing contract | O&M | 60 | 1 | 60 |  | Ongoing works of HP-II
A | A1 | A1.9 | O&M of existing System | A.1.9.04 | AMC for Existing RTDAS Rivergauging Stations for further 5 years ongoing contract | O&M | 60 | 3.28 | 196.8 |  | NCB, in contunition to above
A | A1 | A1.9 | O&M of existing System | A.1.9.05 | O&M of Water Quality Monitoring system | O&M | 1 | 100 | 100 | For WQ Lab | NCS
A | A1
A | A1
A | A1
A | A1 | A1.10 | SCADA system for Barrages
A | A1
A | A1
A | A1
A | A1 | A1.11 | Canal SCADA System
A | A1
A | A1
A | A1
A | A1
A | A1 | A1.12 | Automation of Tubewell operation
A | A1
A | A1
A | A2 |  | State and National Water Centres
A | A2 | A2.1 | Construction of Data Centres | A2.1.01 | Civil Works for Rennovation of SWDC/Division office/Sub Division offices | Works | 1 | 135 | 135 | LS Provision | NCB
A | A2
A | A2
A | A2
A | A2
A | A2 | A2.2 | Rennovation of Data Centres
A | A2
A | A2
A | A2
A | A2
A | A2
A | A2 | A2.3 | Furnishing of Data Centres | A2.3.01 | Procurement of Office Furniture & Non ITC equipments for Data Centre | Goods | 1 | 45 | 45 | LS Provision | Shopping
A | A2 | A2.3 | Furnishing of Data Centres | A2.3.02 | Office Maintanance | O&M | 1 | 225 | 225 |  | NCS
A | A2 | A2.3 | Furnishing of Data Centres | A2.3.03 | Procurement of Office Furniture for W.Q. Lab | Goods | 1 | 15 | 15 | LS Provision | Shopping
A | A2
A | A2
A | A2
A | A2
A | A2 | A2.4 | IT Equipment for Data Centres | A2.4.01 | Purchase of ITC Equipments, Cloud Computing & Training equipments | Goods | 1 | 125 | 125 | LS Provision | Shopping
A | A2 | A2.4 | IT Equipment for Data Centres | A2.4.02 | Procurement of Video Conference Facility | Goods | 1 | 15 | 15 | LS Provision | Shopping
A | A2
A | A2
A | A2
A | A2
A | A2
A | A2
A | A2 | A2.5 | Software for Data Centers | A2.5.01 | E library softwares & related Expenses | Goods | 1 | 25 | 25 | LS Provision | Shopping
A | A2
A | A2
A | A2
A | A2
A | A2
A | A2 | A2.6 | HIF and Testing Fascilities
A | A2
A | A2
B |  |  | Water Resources Information System (WRIS)
B | B1 |  | Web Based Water Resources Information System | [5 empty] | 0
B | B1 | B1.1 | Strengthening National / State WRIS | B1.1.01 | System upgrade - Procurement of Hardware and Software | Goods | 1 | 120 | 120 | L S Provision | Shopping
B | B1 | B1.1 | Strengthening National / State WRIS | B1.1.02 | Meetings/ Training Courses for IAs to creat state chapters of India-WRIS. | NCS | 1 | 100 | 100 |  | NCS
B | B1
B | B1
B | B1
B | B1
B | B1 | B1.2 | Development / Procurement of Spatial Databases | B1.2.01 | Consultancy for development of sptial River basin information. | CS | 1 | 60 | 60 | L S Provision | NCB
B | B1 | B1.2 | Development / Procurement of Spatial Databases | B1.2.02 | Procurement of GIS / Satellite Imageries | Goods | 1 | 10 | 10 | L S Provision | Single Source
B | B1
B | B1
B | B1
B | B1
B | B1 | B1.3 | Data Digitization | B1.3.01 | Digitization / Scanning of Reports, Documents | NCS | 1 | 40 | 40 | L S Provision | Shopping
B | B1
B | B1
B | B1
B | B1 | B1.4 | Website Development and Hosting | B1.4.01 | Consultancy Services for Web application / Developing Website | CS | 1 | 20 | 20 | L S Provision | NCS
B | B2 |  | Water Resources Information Products
B | B2
B | B2 | B2.1 | Development of Atlases
B | B2
B | B2
B | B2
B | B2
B | B2 | B2.2 | Development of Information Brochures
B | B2
B | B2
B | B2
B | B2
B | B2
B | B2
B | B2 | B2.3 | Development of Mobile Apps
B | B2
B | B2
B | B2
B | B2 | B2.4 | e-Library
B | B2
B | B2
C |  |  | Water Resources Operation and Planning System
C | C1 |  | River Basin Modelling
C | C1 | C1.1 | Decision Support System for River Basins | C1.1.01 | Software for DSS | Goods | 4 | 15 | 40 |  | Shopping
C | C1 | C1.1 | Decision Support System for River Basins | C1.1.02 | Central licenses through NIH for HP-II softwares | Goods | 4 | 10 | 40 |  | Shopping
C | C1 | C1.1 | Decision Support System for River Basins | C1.1.03 | Hiring of technical Experts for CDO | CS | 1 | 50 | 50 | LS Provision | NCS
C | C1 | C1.1 | Decision Support System for River Basins | C1.1.04 | Hiring experts to customise HEC products for CDO | CS | 1 | 50 | 50 | LS Provision | NCS
C | C1 | C1.1
C | C1 | C1.1
C | C1
C | C1 | C1.2 | Water Balance Modelling for River Basins
C | C1 | C1.2
C | C1 | C1.2
C | C2 |  | Streamflow Forecasting and Reservoir Operations
C | C2 | C2.1 | Flood Forecasting System for River Basins | C2.1.01 | Software for forecasting system | Goods | 4 | 15 | 80 |  | Shopping
C | C2 | C2.1 | Flood Forecasting System for River Basins | C2.1.02 | Integration of old & new stations and development of composite web based MI System, with establishing linking with flood cell | CS | 1 | 75 | 75 | LS Provision | NCS
C | C2
C | C2
C | C3 |  | Irrigation Design and Operation
C | C3
C | C3 | C3.1 | Irrigation Benchmarking Studies
C | C3
C | C3
C | C3
C | C3
C | C3
C | C3
C | C3
C | C3
C | C4 |  | Purpose Driven Studies
C | C4
C | C4 | C4.1 | PDS for Water Quality | C4.1.01 | Monitoring of Surface Water Quality of some Critical river of Gujarat i.e. Tapi, Damanganga & Mahi, Panam etc. | CS | 1 | 500 | 500 | LS Provision (PHE) | NCS
C | C4 | C4.1 | PDS for Water Quality | C4.1.02 | Work on river bank i.e. Tapi, Damanganga & Mahi, Panam etc. | CS | 1 | 90 | 90 | LS Provision (Chemical Engineering) | NCS
C | C4 | C4.1 | PDS for Water Quality | C4.1.03 | Performance of Piono key weir on low head i.e. Tapi, Damanganga & Mahi, Panam etc. | CS | 1 | 25 | 25 | LS Provision | NCS
C | C4
C | C4
C | C4 | C4.2 | PDS for Ground Water
C | C4
C | C4
C | C4 | C4.3 | PDS for Surface Water
C | C4
C | C4
C | C4
C | C4
C | C4 | C4.4 | PDS for SW GW interaction | C4.4.01 | Work in Tapti River basin - interaction between coastal and catchment | CS | 1 | 100 | 100 | LS Provision | NCS
C | C4
C | C4
C | C4
C | C4
C | C4
C | C4
C | C4
D |  |  | Institutions Capacity Enhancement
D | D1 |  | Water Resources Knowledge Centers
D | D1
D | D1 | D1.1 | Construction of Data Centres
D | D1 | D1.2 | Rennovation of Data Centres
D | D1 | D1.3 | Furnishing of Data Centres
D | D1 | D1.4 | IT Equipment for Data Centres
D | D1 | D1.5 | Software for Data Centers | D1.5.01 | Softwares / Models | Goods | 1 | 20 | 20 | LS Provision | Single Source
D | D1 | D1.5
D | D1 | D1.5
D | D1 | D1.5
D | D2 |  | Professional Development
D | D2 | D2.1 | Trainings | D2.1.01 | International Trainings | NCS | 1 | 100 | 100 | LS Provision | NCS
D | D2 | D2.1 | Trainings | D2.1.02 | National Training programmes | Goods | 1 | 35 | 35 | LS Provision | NCS
D | D2 | D2.1 | Trainings | D2.1.03 | Organizing Inhouse Trainings | NCS | 1 | 25 | 25 | LS Provision | NCS
D | D2 | D2.1 | Trainings | D2.1.04 | Trainers cost (Training Experts @SWDC) | NCS | 1 | 20 | 20 | LS Provision | NCS
D | D2 | D2.1 | Trainings | D2.1.05 | Cost of Training material | Goods | 1 | 10 | 10 | LS Provision | Shopping
D | D2 | D2.1 | Trainings | D2.1.06 | Cost of Training material for Annual Water Resources knowledge forum (Operating Cost) | Goods | 1 | 25 | 25 | LS Provision for booklet / brouchers etc. | NCS
D | D2
D | D2
D | D2 | D2.2 | Workshops | D2.2.01 | For Workshops / Awareness Programmes | NCS | 1 | 20 | 20 | LS Provision | NCS
D | D2
D | D2
D | D2 | D2.3 | International Study Tours | D2.3.01 | Study tour to Overseas and Domestic places | Goods | 1 | 120 | 120 | LS Provision | NCS
D | D2
D | D2
D | D2 | D2.4 | Development of Courses
D | D2
D | D3 |  | Project Management
D | D3 | D3.1 | Establishment of PMU | D3.1.01 | Data Quality Management & Enhancing Public domain information | Goods | 1 | 25 | 25 | L S Provision | NCS
D | D3 | D3.1 | Establishment of PMU | D3.1.02 | Trainings / Meetings for Data Quality Management | NCS | 1 | 10 | 10 | L S Provision | NCS
D | D3 | D3.1 | Establishment of PMU | D3.1.03 | Purchase of vehicle for Division & Sub Division | Goods | 5 | 7 | 35 |  | Shopping
D | D3 | D3.1 | Establishment of PMU | D3.1.04 | Technical Assistance and Project Management Consultancy | CS | 1 | 100 | 100 | LS Provision | NCB
D | D3
D | D3 | D3.2 | Operationl cost of PMU | D3.2.01 | Office Expenses for Stationary, Travelling expenses, O&M of IT equipments etc. | Goods | 1 | 185 | 185 | LS Provision | Shopping
D | D3 | D3.2 | Operationl cost of PMU
D | D3
D | D4 |  | Incremental Staff Cost
D | D4 | D4.1 | Incremental Staff Cost | D4.1.01 | Hiring Junior Experts | O&M | 1 | 200 | 200 | LS Provision | NCS
D | D4 | D4.1 | Incremental Staff Cost | D4.1.02 | Hiring IT / GIS experts and Web Administrator | NCS | 1 | 72 | 72 | LS Provision | NCS
D | D4 | D4.1 | Incremental Staff Cost | D4.1.03 | Hiring Water Quality expert (Junior) | NCS | 1 | 36 | 36 | LS Provision | NCS
D | D4 | D4.1 | Incremental Staff Cost | D4.1.04 | Office assistant | O&M | 1 | 36 | 36 | LS Provision | NCS
D | D4 | D4.1 | Incremental Staff Cost | D4.1.05 | Accountant / clerk | NCS | 1 | 180 | 180 | LS Provision | NCS
D | D4 | D4.1 | Incremental Staff Cost | D4.1.06 | Data Entry operator | NCS | 1 | 82 | 82 | LS Provision | NCS
D | D4 | D4.1 | Incremental Staff Cost | D4.1.07 | Hiring of technical Experts for Water quality assessment at GERI | NCS | 1 | 45 | 45 | LS Provision | NCS
D | D4 | D4.1 | Incremental Staff Cost | D4.1.08 | Lab cum Field Staff at GERI | NCS | 1 | 10 | 10 | LS Provision | NCS

## Hydromet Calculator
ID | Item | All Cost in Rs lakh
|  | Quantity | Unit Cost | Amount | Remarks
E1 | Monitoring Stations (All equipment cost and minor civil works included except Telemetry) |  |  | 0
E1.1 | Automatic Weather Station (AWS) | 134 | 10 | 1340 |  | H
E1.2 | Automatic Rain Gauges Station | 50 | 4 | 200 |  | H
E1.3 | Snow Pillows | 0 | 8 | 0 |  | H
E1.4 | Rain and Snow Gauge | 0 | 7 | 0 |  | H
E1.5 | Snow Depth Sensors | 0 | 5 | 0 |  | H
E1.6 | AWLR - Radar type above 30 meter | 17 | 7 | 119 |  | H
E1.7 | AWLR (Shaft/bubbler/Radar upto 30 meter) | 116 | 5 | 580 |  | H
E1.8 | Velocity Radar | 8 | 12 | 96 |  | H
E1.9 | ADCP upto 25 meter | 0 | 15 | 0 |  | H
E1.10 | ADCP above 25 meter | 3 | 25 | 75 |  | H
E1.11 | Soil Moisture Sensors - TDR | 0 | 1.5 | 0 |  | H
|  |  |  | 0 |  | H
E2 | Telemetry Equipment for New Stations |  |  | 0 |  | H
E2.1 | GSM telemetry Equipment | 60 | 0.5 | 30 |  | H
E2.2 | VSAT Telemetry Equipment | 0 | 1.7 | 0 |  | H
E2.3 | INSAT Telemetry Equipment | 0 | 1.7 | 0 |  | H
E3 | Additionl Telemetry Equipment for Existing Stations |  |  | 0 |  | H
E3.1 | GSM telemetry Equipment | 332 | 0.3 | 99.6 |  | H
E3.2 | VSAT Telemetry Equipment | 0 | 1.5 | 0 |  | H
E3.3 | INSAT Telemetry Equipment | 0 | 1.4 | 0 |  | H
E4 | Additional Communication Cost for Telemetry Operation |  |  | 0 |  | H
E4.1 | VSAT Telemetry | 0 | 0.7 | 0 |  | H
E4.2 | GSM Telemetry | 392 | 0.5 | 196 |  | H
E4.3 | INSAT | 0 | 1 | 0 |  | H
E4.4 | Mobile Based Manual Communication | 350 | 0.25 | 87.5 |  | H
H
E5 | Data centres |  |  | 0 |  | H
E5.1 | GSM Based Data Centre | 1 | 30 | 30 |  | H
E5.2 | INSAT Based Data centre | 0 | 95 | 0 |  | H
E5.3 | VSAT Based Data Centre | 0 | 35 | 0 |  | H
|  |  |  | 0 |  | H
| Total |  |  | 2853.1 |  | H
I
I
I
I
I
I
I
I
I
I
I

## Guide to Filling Columns
Componant ID | Sub Comp ID | Activity ID | Componant | Item Code | Items | Type | Quantity | Unit Cost | Total Cost
No Change required in this column | No Change required in this column | Add the ID of Activity, consistant with Componant and Sub-Componant ID | Add the name of Activity here in Blue color | Add the ID of Item, consistant with Componant, Sub-Componant and Activity ID | Add the Name of Item here in Black Color | Works for Civil Works Goods for Goods and Equipment CS for Consultancy Services NCS for Non Consultancy Services | No of Items | Unit cost of each Item | Total Cost (Col H * Col I)

## Component Description
Sub-Component | Activity | Major Activities | Primary IA | Explanatory Notes
A Water Resources Data Acquisition System
A1: Hydromet Observation
| A1.1 | Real Time Data Acquisition System (RTDAS) | States/Central | WRMS system may include: • Weather: automatic weather stations, rainfall and snow gages • Rivers: stage/discharge of rivers, water quality, rating curve updating • Groundwater: levels, water quality • Reservoirs/tanks: water levels, gate positions, outflows and spillways, update rating curves • Sediment: transport and load monitoring • Coastal monitoring • Diversions, water use and irrigation monitoring This will involve procurement of equipment for monitoring and services for commissioning, operation and maintenance. Generally, two years warranty and five years annual maintenance needs to be included in procurement documents (Refer to BBMB and Maharashtra contracts for RTDAS, RTDSS real-time, real-time flood forecasting).
| A1.2 | Civil Works for Hydromet System (RTDAS) |  | Major civil works like Stilling Wells, gauge houses etc Minor civil works like fencing should be part of A1.1
| A1.3 | Discharge Measurement Equipment |  | Procurement of ADCP, current meters, boats, cableways etc
| A1.4 | Groundwater Measurement Equipment |  | Procurement of DWLR, borehole logger, well testing equipment etc
| A1.5 | Civil Works for Groundwater Monitoring |  | Civil works for GW like peizometers, tubewells etc
| A1.6 | Water Quality Labs |  | Construction, rennovation and furnishing of labs
| A1.7 | Water Quality Equipment |  | Procurement of WQS, AWQS, lab (equipment, consumables, staff)
| A1.8 | Manual Observation Equipment |  | Procurement of Portable GPS based water level recorder, flow meters and other devices for measurement of river stream, GW and pipe flows
| A1.9 | Field Surveys |  | River Cross-section survey, Bathymatric survey of reservoirs and any other surveys; procurement of survey equipment like GPS, Total Station etc
| A1.10 | O&M of existing System | States | O&M of system installed in previous phases and HP-2
A2: Automated System Operation and Data Acquisition | A2.1 | SCADA system for Barrages |  | For reservoirs, irrigation systems operations, flood preparedness, spill management, and other water infrastructure
| A2.2 | Canal SCADA System | States/River Basin bodies | Procurement of SCADA system for automated operation
| A2.3 | Automation of Tubewell Operation | States/RBO | Automatic Tubewell operation
A3: Hydro Informatics Centers | A3.1 | Construction of National Data Centres | Central | Construction of data centres, building and consultancy , architecture cost
| A3.2 | Rennovation of National Data Centres | Central | Rennovation and other improvements in building
| A3.3 | Construction of State / River Basin Data Centres | Central/States | Construction of data centres, building and consultancy , architecture cost for state level or river basin level buildings
| A3.4 | Rennovation of State / River Basin Data Centres | Central/States | rennovation and other improvements for state level or river basin level buildings
| A3.5 | Construction of Regional/ Divisional Data Centres | Central/States | Construction of divisional / sub-divisional buildings
| A3.6 | Rennovation of Regional/ Divisional Data Centres | Central/States | rennovation of divisional / sub-divisional buildings
| A3.7 | Furnishing of Data Centres | Central/States | Furnishing of all buildings, office furniture etc
| A3.8 | IT Equipment for Data Centres | Central/States | Information management tools, e.g. ICT incl. cloud-based systems, videoconferencing systems, displays, information systems design
| A3.9 | Software for Data Centers | Central/States | All kind of software for water management, GIS, Windows etc
| A3.10 | Development of Hydrological instrumentation facility | Central | CWPRS and other Institutes wll be equipped to support in the development of Hydromet system.
B: Water Resources Information System (WRIS)
B1: National Water Resources Information System | B1.1 | Strengthening India WRIS |  | • Implementation of central and state wise data storage and data dissemination systems (software; cloud computing and processing, etc.); Integrate WRIS with monitoring data from radars and satellite products; curated spatial information from legacy data and surveys. Requires active exchange platform between states and center • Provide easy access to CMIP5 climate change projections for India for the purpose of Climate Risk Assessments.
| B1.2 | Database management and Repository |  | Consultancy (O&M), Training, Data-entry (including in web-portal, e-SWIS, e-GEMS, e-WQIS and their replica at state data centre) • e-SWIS, e-GEMS and e-WQIS were developed during HP-2. Phase 3 may support AMC, system extension and upgrading. • This sub-component would also aim at (re)establishing and strengthening data sharing and data validation protocols across state and central agencies. Integrate with India WRIS During HP1 and HP2, water quality standards, QA and AQC procedures and monitoring protocols were set by the project. Central agenies to develop standards and state agencies to implement. Application of these procedures will be strengthened and WQ laboratories need to be rationalized.
| B1.3 | National Spatial Information Development |  | Procurement of LiDAR or similar surveys. Development of DEM for the entire country for improved flood hazard mapping and other planning purposes • High resolution surveys such as LIDAR for flood prone areas and for purpose of flood risk mapping (<4000 km2) • High resolution remote sensing imageries and other supplementary information to develop DEM for other areas • Sharing protocol between central agencies and states needs to be streamlined to avoid delays. • Provision of high resolution imageries. Temporal assessments may include but not be limited to: • Estimation of precipitation, snow cover and snow melt, soil moisture, land use and actual evapotranspiration (ET) • Runoff estimates as the basis for flood forecasting and reservoir operations (Hydro-India; see VIC model of NRSC) • Satellite based monitoring of cropping patterns, crop conditions, droughts and water supply conditions in irrigation systems • Satellite based monitoring of water logging, water storage in tanks and other water bodies. Convegence of resources through other projects • Improvement of flow forecasting, reservoir operations, crop planning, drought management, etc. • Collaborate with international agencies as required to process ensemble forecast.
| B1.4 | Data Digitization |  | Digitize spatial river basin information systems including themes provided in India-WRIS Themes may include: Water bodies and their usage, Canal system networks, Groundwater systems, Land use, irrigation systems, Inventories of water pollution. Services to digitize the map. IAs can take help of NRSC/ISRO imageries Procurement of services and toposheets and imageries
| B1.5 | Data Exchange |  | Receiver at master station, service contract (if needed) for data transmission (INSAT/VSAT/GSM) Integrate data with water use agencies including IMD, NRSC, Agriculture, Hydropower, CPCB, Watershed
| B1.6 | Web Hosting |  | Hosting the website, hardware, software, man power required
B2: State Water Resources Information System | B2.1 | Strengthening Regional WRIS |  | State Raplica of National WRIS, see B1.1 above
| B2.2 | Database management and Repository |  | See B1.2 above
| B2.3 | Regional Spatial Information Development |  | See B1.3 Above
| B2.4 | Data Digitization |  | See B1.4 Above
| B2.5 | Data Exchange |  | See B1.5 Above
| B2.6 | Web Hosting | CWC/CGWB/NRSC | See B1.6 Above
C: Water Resources Operation and Planning
C1: Analytical and DSS tools | C1.1 | Decision Support System for River Basins |  | Procure - river cross-section survery for input to the hydraulic model, - consutlancy for downscaling as described above or setup new model for their specialized case. - Also the DSS setup during HP2 will be further strengthened. Systems for river basin planning; water balance assessments;
| C1.2 | Decision Support System for Groundwater Management |  | Prepare conjuntive use plans to increase the gross irrigated area including strategy suggested in PMKSY… States need to match their hotspots with CGWB in order to avoid duplication. Impact on tanks, baseflow in the rivers, aquifer connectivity with stream/canals. CGWB to developed the DSS software and support the states in it application. The modelling centre proposed for GW should focus on developing this software
| C1.3 | Flood Forecasting System for River Basins |  | This would help understand seasonal forecasts for floods, flows, inundation, droughts.
| C1.4 | Studies for Flood Indundated Areas |  | Mapping of flood due to drains, other structures
| C1.5 | Others - TBD
C1.6
C2: Purpose Driven Studies |  | Conjunctive use and GW recharge studies |  | Studies for conjunctive use, Surface GW interaction
|  | Water Quality Studies |  | Design monitoring system to assess loading, fate and transport of constituents within water quality limited hotspots
|  | Studies for Rainwater harvesting and Artificial recharge |  | Studies of artificial recharge structures etc
|  | Reservoir sedimentation assessment |  | Surveys and studies for sediments, coastel ares atc
|  | Studies for Dam Break Analysis |  | Dam safety analysis and dam break studies for specific reservoirs
|  | Irrigation Benchmarking Studies |  | Benchmarking, Irrigation system efficiency, Water use efficiency
|  | Community based monitoring and water management |  | • Pilot a community based, mobile monitoring system for small streams, groundwater, water bodies, flooding, embankment status (crowd sourcing) • Procurement of mobile based services and mobilizing the communities for the monitoring of local water resources. NRSC/ISRO has already piloted this approach.
|  | Others - TBD |  | Such as River Basin Management Plans, Status of India’s Water Resources This would/may include monitoring, information generation and studies of specific issues, as conducted under HP-II, including also Climate Risk Assessments of present and planned WR infrastructure
Others - TBD
C3: Knwoledge Products and Dissemination |  | Information Product |  | India WRIS (DEM, LULC updated, Climate forcast, Hydromet data from state & central agencies, Basin wise water balance assessment & budgeting, Aquifer assessment and budgeting, Advance river flow, Weather model forcast, disaster alert system, Water efficiency*) with State Replica
|  | Information Dissemination |  | Public alert, EAP, Historical map of flood & droughts, block level water availability, use & efficiency assessment, Reservoir water availability advance information. Canal supply information; ambient water quality information; average historical river flow information
WR Institutions Capacity Enhancement
D1: Water Resources Knowledge Centers | D1.1 | National level Centers of Excellence |  | This will include curriculum development, technical courses, refresher courses, Training/Meetings in use of EO products readily available, etc. Multi-media distance learning may include videoconferencing, e-learning (e.g. self-paced courses, webinars, MOOC), vendor fairs, regular video & audio podcasts, documentaries. Strengthening WALMIs to provide technical support to State IAs, including regarding improvement of irrigation system management. Modernization of National Training centers such as NIH, NWA and other regional central Institutes, Centers of excellence Facilities, trained manpower, exchange with international/national agencies; MOU with reputed National and International research Institutes Creation of e-library including subscription to Journals, web-based course introduced eleswhere or any other knowledge source
| D1.2 | State/Regional Centers of Excellence |  | State Raplica of National Center, see D1.1 above
D2. Professional Development |  | Annual Water Resources Knowledge Forum | All IAs
| D2.1 | Trainings
| D2.2 | Technical Assistance for development of training
| D2.3 | Workshops |  | Thematic workshops This would support showcasing the best of what India has to offer and facilitate knowledge exchange; also various competitions may be introduced (e.g. Online Tools, Appathons, Hackathons).
| D2.4 | International Study Tours |  | Strengthened Partnerships with earth observation data and other knowledge providers, open data initiatives, academia, CSOs, internships/visiting experts/development assignments, international exchange program, and overseas and domestic study tours
| D2.5 | Diploma's and Higher Degree Courses |  | Support to universtities for introduction of project related courses
| D2.6 | Website |  | Procurement of consultancy for website development.
| D2.7 | Publications | All IAs | Prininting of reports, publication cost in journals/books
| D2.8 | Others - TBD
D3: Project Management and Technical assistance | D3.1 | Establishment of CPMU |  | Cost of infra-structure, manpower and furnshing and man power requirement TAMC Consultancy for technical assistance and support for procurement, financial management, and MIS and M&E services; general TA support at State level
| D3.2 | Establishment of State PMU |  | Similar to Central agencies, States will have State PMU. see D3.1 above
D4 Operating cost | D4.1 | Incremental staff cost | All IAs | Total cost to be included for each year, even though staff cost are generally reimbursed on a gliding scale.
| D4.2 | Recurrent cost for operation of offices | All IAs | Office vechiles etc will come under this

## Help
Major Changes from Older Version
In line with allocation Pattern from Ministry, the components have been shuffled.
· The major buildings like Data Centers, Office Buildings, Divisional and Sub-Divisional buildings have moved from Component D to Component A. (Although the training centers still stay in component D).
· All the IT related equipment (like Servers, computers, printers) and software have now moved into Component A3 (although there is provision for small amount in component B,C and D too)
· Irrigation Operation systems like SCADA for Barrages and Canals have moved from Component C to Component A, as they have a monitoring component inbuilt into them.
· All the support from Central agencies, spatial database and other information products are now in Component B
· The surveys of any kind are now part of Component A1 instead of Component C
How to use the Excel sheet
The user is expected to fill in the details on unit costs and quantities for each item. Some items have already been listed in the sheet. However, the user is free to insert rows and add his items if they are not available in the sheet. While inserting the rows, few points to be kept in mind are:
· You should not add or edit The Component ID or Name (They are already fixed as A, B, C &D)
· You should not add or edit The Sub-Component ID or Name (They are already fixed as A1,A2,A3; B1,B2; C1,C2,C3;D1,D2,D3,D4)
· There are Activities under Sub-Components. The IDs of Activities are like A1.1; A1.2; A1.3 etc. as an example for activities under Sub-Component A1
· Within Activities, there are Items. The items ID are based on IT of respective ID. For example, if there are 4 items under activity A3.1, the IDs of the items under A3.1 would be A3.1.01; A3.1.02; A3.1.03; A3.1.04 etc.
· Before inserting a row for Activity, please make sure that a particular activity does not already exist in the file. This would be helpful to avoid duplications.
· Make sure to add a new activity only in the end of a particular Sub-Component. This will make sure that you don’t have to edit the IDs of all other activities which would be affected due to insertion of new row. See the picture below for example.
· Make sure to add a new Item only in the end of a particular Activity. This will make sure that you don’t have to edit the IDs of all other items which would be affected due to insertion of new row. See the picture below for example.
· Whenever you add a new row for Activity or item, make sure to fill in the information in columns A, B C and D also. This will make sure that the pivot table works perfectly.
· You can use hydromet Calculator (available as different sheet in the file) to fill the information in Activity A1.1 (Hydromet Observation)
· Minor civil works for Hydromet DAS can be part of DAS bid. However major civil works like construction of stilling well etc can be taken up separately in Activity A1.2.
· The Pivot table summarizes all the cost by components. Just refresh the pivot table after updating the numbers.
Tips to fill the data
· You can estimate the cost of goods considering the operation and Maintenance as part of item or as an additional row. For example, you can estimate the cost of server and cost of O&M in two different rows or as a single item with name as “Server with O&M of 8 years”
· Most of Incremental staff should be included in Activity D4.1. However, some staff for example IT person for operation and maintenance of website can be included in Activity A3.8 or B2.6. |  |  |  | Construction of Data Centres
· If you have unallocated money in component A whereas run short in component B,C,D, you can shift all IT related equipments to component A3. Similarly You can shift the buildings (and furnishing of buildings) to A3. |  |  |  | Rennovation of Data Centres
· On the other hand, if you run out of money in Component A, you can shift some of IT equipment to other components. |  |  |  | Furnishing of Data Centres
IT Equipment for Data Centres
| S No | Indicator | Query | Software for Data Centers
| 1 | New rain Gauges | Select from Hydromet Table, Serial E1.2 , quantity
| 2 | No of Basins with Forecast | Select from Main table, C1.1 Quantity
| 3 | VSAT Equipment installed | Select from Hydromet, sum of E2.2 and E3.2
| 4 | Expenditure on Buildings | Select form main table, A2.1, sum of cost
| 5 | No of operational Flood control rooms | Manual Entry
|  | Total Hydromet Stations installed | Sum of all entities in E1
Best Place to Add Item A3.8.20 would be to insert a row after Row 208. Then you don’t have to edit any ID of existing items.
Figure 1 Cost Tab - Insert Row

## Agency Allocations
State/Agency Wise share of the World Bank, GoI and the State Governments
(Rs in Crore)
Component wise
S.No. | Implementing Agency | Tentative Allocations | A | B | C | D
STATES
1 | Andhra Pradesh (GW) | 80 | 48 | 4 | 12 | 16
2 | Andhra Pradesh (SW) | 80 | 48 | 4 | 12 | 16
3 | Assam | 47 | 28.2 | 2.35 | 7.05 | 9.4
4 | Bihar (GW) | 30 | 18 | 1.5 | 4.5 | 6
5 | Bihar (SW) | 105 | 63 | 5.25 | 15.75 | 21
6 | Chattishgarh SW | 48 | 28.8 | 2.4 | 7.2 | 9.6
7 | Chattishgarh GW | 32 | 19.2 | 1.6 | 4.8 | 6.4
8 | Goa | 68 | 40.8 | 3.4 | 10.2 | 13.6
9 | Gujarat (GW) | 31 | 18.6 | 1.55 | 4.65 | 6.2
10 | Gujarat (SW) | 70 | 42 | 3.5 | 10.5 | 14
11 | Haryana (SW) | 50 | 30 | 2.5 | 7.5 | 10
12 | Himachal Pradesh | 70 | 42 | 3.5 | 10.5 | 14
13 | Jharkhand | 60 | 36 | 3 | 9 | 12
14 | Karnataka (SW) | 110 | 66 | 5.5 | 16.5 | 22
15 | Kerala (GW) | 40 | 24 | 2 | 6 | 8
16 | Kerala (SW) | 42 | 25.2 | 2.1 | 6.3 | 8.4
17 | Madhya Pradesh | 90 | 54 | 4.5 | 13.5 | 18
18 | Maharashtra (GW) | 36 | 21.6 | 1.8 | 5.4 | 7.2
19 | Maharashtra (SW) | 150 | 90 | 7.5 | 22.5 | 30
20 | Manipur | 25 | 15 | 1.25 | 3.75 | 5
21 | Meghalaya | 25 | 15 | 1.25 | 3.75 | 5
22 | Mizoram | 31 | 18.6 | 1.55 | 4.65 | 6.2
23 | Nagaland | 28 | 16.8 | 1.4 | 4.2 | 5.6
24 | Odisha (GW) | 55 | 33 | 2.75 | 8.25 | 11
25 | Odisha (SW) | 60 | 36 | 3 | 9 | 12
26 | Punjab | 74 | 44.4 | 3.7 | 11.1 | 14.8
27 | Rajasthan | 128 | 76.8 | 6.4 | 19.2 | 25.6
28 | Sikkim | 25 | 15 | 1.25 | 3.75 | 5
29 | Tamil Nadu | 100 | 60 | 5 | 15 | 20
30 | Telangana (GW) | 70 | 42 | 3.5 | 10.5 | 14
31 | Telangana (SW) | 97 | 58.2 | 4.85 | 14.55 | 19.4
32 | Tripura | 25 | 15 | 1.25 | 3.75 | 5
33 | Uttar Pradesh(GW) | 50 | 30 | 2.5 | 7.5 | 10
34 | Uttar Pradesh (SW) | 121 | 72.6 | 6.05 | 18.15 | 24.2
35 | Uttarkhand | 75 | 45 | 3.75 | 11.25 | 15
36 | West Bengal (GW) | 50 | 30 | 2.5 | 7.5 | 10
37 | West Bengal (SW) | 100 | 60 | 5 | 15 | 20
UTs
1 | Delhi | 5 | 3 | 0.25 | 0.75 | 1
2 | Puducherry | 20 | 12 | 1 | 3 | 4
CENTRAL AGENCIES
1 | Ministry of Water Resources, River Development & Ganga Rejuvenation (MoWR,RD & GR) | 210 | 10 | 30 | 0 | 170
2 | Central Water Commission(CWC) | 275 | 35 | 35 | 155 | 50
3 | Central Ground Water Board (CGWB) | 85 | 17 | 23 | 35 | 10
4 | National Institute of Hydrology (NIH) | 85 | 10.75 | 0 | 25.5 | 48.25
5 | Central Water & Power Research Station (CWPRS) | 60 | 10 | 0 | 2 | 48
6 | Central Pollution Control Board (CPCB) | 26 | 22 | 1 | 0 | 3
7 | India Meteorological Department (IMD) | 0 | 0 | 0 | 0 | 0
8 | Survey of India (SOI) | 300 | 0 | 250 | 0 | 50
9 | National Remote Sensing Agency(NRSA) | 80 | 0 | 55 | 10 | 15
10 | Bhakra Beas Management Board (BBMB) | 30 | 10 | 2 | 12 | 6
11 | Damodar Valley Corporation (DVC) | 50 | 30 | 2.5 | 7.5 | 10
| Contingency | 36
| TOTAL | 3640 | 1586.55 | 518.65 | 607.45 | 890.85