## Slide 1: National Hydrology Project
23.05.2017, New Delhi
Ministry of Water Resources, River Development and Ganga Rejuvenation
Project Management & Fund Flow

## Slide 2
Annual Work Plan (AWP) and Fund Release Mechanism
Preparation
Consolidation
No Objection
Budget Allocation & Release of Grant
ALL IAs
By Aug 15: Submission of AWP package to NPMU with following
Physical and Financial Progress
Projections for remaining seven months and request for 2nd tranche.
AWP and PP for next year with request for budget allocation.
Utilization certificate for expenditures incurred during past 5 months
Audit report for previous years
NPMU
Aug, 31- Request for Budget allocation for next FY Year to finance.
Sep 30: Review, consult with IA and consolidate AWP & PP for next year.
Oct 15: Separately review request for 2nd tranche and submit for release of funds to IFD.
World Bank
Oct 31: Review and issue NOL
NPMU-Nov, 15: AWP with Budget Outlay submitted to Finance department.
Finance Department, MoWR, RD & GR- Dec, 15: Review and make appropriate financial allocation under the project Budget Head
Secretary, MoWR, RD & GR-Jan 15: Final Approval –March, 15: Budget released to Implementing agencies
Nov 15: Final Approval by finance and Secretary for release of funds

## Slide 3
Secretary, MoWR, RD & GR
Jt . Secretary & Financial Advisor
Management Consultant Financial Team
Implementing Agencies Financial Report
Audit
Jt . Secretary (Admin) & Project Coordinator
Sr. Jt. Comm.
Section Officer
Under Secretary
NPMU
Financial Arrangement in MoWR, RD & GR

## Slide 4
World
Bank
Quarterly
Phy + Fin
Quarterly
Quarterly
Progress Reporting Strategy
Compilation
Consolidation & QA/QC
Review & Advisory
Physical Progress
Safeguard Compliance
Financial Progress Reporting
All implementing agencies
M&E/ MIS Expert compile progress report
Nodal Officer Sign-off the report for submission to NPMU
All implementing agencies
M&E/ MIS Expert compile report along with trained Field Level officials
Nodal Officer overall responsible for Safeguard Compliances and Sign-off the report for submission to NPMU
All implementing agencies
Accounts/ Finance Officer compile report
Nodal Officer Sign-off the report for submission to NPMU
National
Project
Management
Unit
M&E Cell will consolidate the (1) Physical and Safeguard Compliance reports s& (2) Financial Report
Safeguard Specialist will carry out QA/QC through random sampling and site visits.
Project Coordinator Sign-off the report for submission to World Bank

## Slide 5
Tranche | Conditions of release
First (upto 60% of the AWP) | IUFR for the previous half year and UC for the previous period Audit report for the previous financial years which are due before the tranche is requested
Second (Balance of AWP) | Utilization of at least 60% of the total available funds (including opening balance) and submission of Utilization Certificates. The opening balance of the PMUs should not exceed 10% of the allocation of the previous year. Central funds would proportionally reduced for unutilized amount. Audit Reports for the last FY (with auditor’s remarks), Utilization Certificates and Bank Reconciliation Statement for the previous year furnished along with Non-diversion of fund certificate. IUFR for the previous half year Achievement with reference to Annual Action Plan.
Release of funds would also be subject to physical and financial process reporting on MIS on monthly basis.
Release of Tranche

## Slide 6
Opening of Bank A/c and operation
Where to open bank a/c? In any scheduled bank.
Whether sub-account permitted? No
What will be type of A/c? Saving.
Whether a/c will be operated by single or jointly? Jointly, Preferably one technical person and one financial person.
How interest in a/c will be dealt? Used for project purpose.
Who will make payment? All payment will be made centralized through PMU.

## Slide 7: SOP
Which bid document need to be sent to NPMU?
  All hydro-met for checking of Hydro-met network, locations, communication system and payment clauses.
  All prior review bids as per threshold.
  First bids of all types of procurement for NHP (1 – NCB, 1-NCS, 1-ICB etc.)
  NO shopping bids
Single Source Procurement- All single source procurement should be reflected in PP with justification and got approved by WB.
Studies proposed in Component-C- ToR for all studies need to be submitted to NPMU.
Foreign training/foreign study tours- All Proposal need to be submitted to NPMU.
Purpose Driven Study- Need to be submitted to NIH.

## Slide 8: SOP
Post Review Bids- Need to submit to NPMU after award.
Assistance to IAs
Besides the bids/procurement listed above, if IAs want the assistance in preparation of their bids, any clarifications etc., the NPMU shall provide the same in consultation with WB till placement of TAMC. After, TAMC is in place, the assistance shall be provided by TAMC in consultation with NPMU/WB.

## Slide 9: Thank You
Notes: 9