## Slide 1: Status of Odisha Surface Water under NATIONAL HYDROLOGY PROJECT
Director, Hydrometry, Bhubaneswar

## Slide 2: State Project Monitoring Unit (SPMU)
SPMU : A State Project Monitoring Unit (SPMU) is constituted for smooth implementation of National Hydrology Project (NHP) in Odisha by Department of Water Resources, Govt. of Odisha vide Notification No. 13675 dated 10.06.2017 with the following members.
1 | State Project Co-ordinator | EIC (P&D), WR, Bhubaneswar
2 | Project Director (NHP) | Director, Coastal Protection & River Training, Bhubaneswar
3 | Nodal Officer (SW) | Director, Hydrometry, Bhubaneswar
4 | Nodal Officer (GW) | Superintending Engineer, GWS&I, Bhubaneswar
SPMU (Odisha )

## Slide 3: Project Monitoring Unit (PMU) [Odisha SW]:
Sl.No. | Name | Designation | Function
1 | Er. S.K. Balabantaray | Director, Hydrometry | Nodal Officer, NHP ( Odisha –SW)
2 | Er. Judhisthir Naik | Dy. Director | Sr. Water Management Expert
3 | Er. N.K. Sahoo | Dy. Director | Procurement Expert
4 | Er. S.N.Behera | A.E.E. | Hydrologist
5 | Er. Rasmita Kumari Sahu | A.E.E. | Modeller
6 | Er. Binit Charan Behera | A.E. | Hydromet Instrumentation Expert
7 | Er. S.S.Das | J.E. | Hydromet Instrumentation Expert
8 | Er. Abhimanyu Behera | A.E. | Data Entry Operator
9 | Er. Jitendra Dash | A.E. | Data Entry Operator

## Slide 4
Project Co-ordinator
STATE PROJECT MONITORING UNIT (SPMU)
Engineer-In-Chief, P&D
Director, Hydrometry
PMU
SPMU
DD, SDP
BBSR
DD, DA & P
BBSR
(3 Sub-Div.)
DD, Hyd. North
Zone, Bolangir
( 2 Sub-Div.)
DD, Hyd. South
Zone, Jeypore
(4 Sub-Div.)
Nodal Officer (Odisha Surface Water)
Sr. Water Management Expert (1 No.)
Procurement Expert (1 No.)
Hydrologist (1 No.)
Modeller (1 No.)
Hydromet Instrumentation Expert (2 Nos.)
Data Entry Operator (2 Nos.)
Implementing Divisions
Nodal Officer (Odisha Ground Water)

## Slide 5: Funds Received under NHP
For the year 2016-17 :
For the year 2017-18 :
Funds received by Odisha Surface Water for the year 2016-17 is Rs. 0.67 Crore from MoWR, RD & GR, GoI, as per the approved Annual Work Plan (2016-17) vide letter no. 96035/1/2016-NHP/993-994 dtd. 31.01.2017.
Funds received for the year 2017-18 - 3.24 Crore.
Year wise Expenditure :
For 2016-17 : NIL
For 2017-18 (Till date) : NIL

## Slide 6: Major Procurement Items in PIP :
Sl.No. | Item Code | Item | Quantity (in Nos.) | Amount (in Lakhs)
1 | A1.1.01 | Installation of Real Time Data Acquisition System (RTDAS) for all the River Basins of Odisha. RTDAS stations Procurement of ADCP | 275 3 | 1420.00
2 | A1.3.01 | Boat with Outboard Engines | 3 | 150.00
3 | A1.8.01 | Bathymetric survey of selected rivers | 1 | 500.00
4 | A2.4.02 | Purchase of Server with software | 1 | 160.00
5 | A2.4.04 | Purchase of Video Conference facility | 2 | 50.00
6 | A2.4.06 | Digital Display System | 5 | 60.00
7 | A2.5.02 | GIS & RS software | 1 | 25.00
8 | C1.1.01 | Consultancy Services for Setup and Operation of DSS (for River Burhabalanga and Tel) | 1 | 400.00
9 | C4.3.01 | Modeling of Sediment Yield and distribution in Rengali Reservoir | 1 | 150.00

## Slide 7: Major Procurement Items in AWP 2016-17 :
Sl.No. | Item Code | Item | Quantity (in Nos.) | Amount (in Lakhs)
1 | A1.1.01 | Procurement of ADCP | 1 | 30.00
2 | A1.8.01 | Bathymetric survey of selected rivers | 1 | 5.70

## Slide 8: Major Procurement Items in AWP 2017-18 :
Sl.No. | Item Code | Item | Quantity (in Nos.) | Amount (in Lakhs)
1 | A1.1.01 | Installation of Real Time Data Acquisition System (RTDAS) for all the River Basins of Odisha. RTDAS stations Procurement of ADCP | 275 2 | 544.00
2 | A1.3.01 | Boat with Outboard Engines | 1 | 50.00
3 | A1.8.01 | Bathymetric survey of selected rivers | 1 | 30.00
4 | A2.4.02 | Purchase of Server with software | 1 | 31.00
5 | A2.4.06 | Digital Display System | 1 | 10.00
6 | A2.5.02 | GIS & RS software | 1 | 25.00
7 | C1.1.01 | DSS | 1 | 25.00

## Slide 9: Physical Progress
The estimate of ADCP submitted to Govt. in DoWR for approval.
The estimate of 275 RTDAS stations is in progress.
The estimate of Digital Display Board is prepared and under sanction.
The estimate for scanner prepared and under sanction.
Estimate for Boat with outboard engine is under preparation.

## Slide 10: Status of BID Document
Draft copy of BID Document for the Work “ Supply, Installation, Testing, Commissioning, Training & Maintenance of Hydrological Information System for Odisha State “ under NHP amounting to Rs. 15.20 Crores submitted to MoWR, RD & GR, GoI, New Delhi on dt. 21.11.2016 for necessary approval.
BID Document for ADCP is under preparation.

## Slide 11: Status of Data entry in E-SWIS:
Data entry in E-SWIS to be started.
Status of Hydromet Station:
Number & location of Hydro-met stations is in the process of finalization in consultation with Chief Engineer, Mahanadi & Eastern Rivers, CWC, Bhubaneswar.

## Slide 12
'If We Can't Measure It, We Can't Manage It‘

## Slide 13: THANK YOU