## Slide 1
National Hydrology Project
Govt. of West Bengal
IRRIGATION AND WATERWAYS DEPARTMENT
(WEST BENGAL SURFACE WATER)
1st World Bank Mission
Bhubaneswar, Odisha
22nd & 23rd august, 2017

## Slide 2: Details of SPMU
Director, APPEMC
SE, IPC-II
Water Resource Management Unit
Hydrology and Modeling Unit
Tendering Unit
Implementing Unit
Sri R.K. Sharma EE, DVC Study Cell
Sri D. Maity Dy. Director, APPEMC
Sri P. Paul, Dy. Director, CDO
Sri Bomkesh Ojha, Asstt. Director, DSO
Sri Debasish Roy, Asstt. Director, CDO
Sri D. Roy Chowdhury, Dy. Director, CDO
Dr. B.C. Barman, Dy. Director, RRI
Dr. S.S. Dey Dalal, Dy. Director, RRI
Sri Pinaki Chatterjee, Asstt. Director, CDO
Shri Abhijit Roy, RO, RRI
Sri Sunil Kumar, Dy. Director, APPEMC
Sri S. Bhattacharya, EE, Burdwan I&P Division
Sri S. Sarkar, EE-I, IP Division (South)
2 Nos. A.E of EE-I, I&P Division (South)
EE, Burdwan I&P Division, Burdwan
EE, Damodar HQ Division, Durgapur
EE, Durgapur M&E Division, Durgapur
EE, Sundarban Delta Project, RRI
EE, I&P Division (Central)
EE, NB Planning Division, Malda
EE, Jalpaiguri (I) Division, Jalpaiguri
EE, Purulia Investigation Division, Purulia
EE, KKB Division, Sabang
EE, Mayurakshi HQ Divison, Suri
Sri Subhodip Sarkar, RO, RRI
Sri S. Sarkar, EE-I, IP Division (South)
Principal Secretary
DSW-I
CE, D&R

## Slide 3: Fund Received
For 2016-17: rs.73.25 lacs
For 2017-18: rs.300.00 lacs
expenditure: NIL

## Slide 7: Status of Physical progress
1. Bid documents of various activities as per pp 2017-18 are under process.
2. No physical progress achieved so far.

## Slide 8: Status of Bid Document
PROCUREMENT PLAN OF BENGAL (SW) DURING 2017-18 |  |  |  |  |  |  | 
Sl. No. | Package Name | Procurement Type | Procurement Method | Bank Review | Date of Initiating the Process | Expected Award Date | Present Status
1 | Development of RTDAS for River Sub-Basins and Major Dams in West Bengal | Goods | NCB | Prior | 10-Jul-17 | 11-Oct-17 | Bid Document uploaded in MIS
2 | Procurement of Discharge measuring Equipment including Development of Rating Curves for and Assessment of Siltation | Goods | NCB | Prior | 24-Jul-17 | 11-Oct-17 | 
3 | Survey Works in connection with Establishment of Benchmarks | Goods | NCB | Prior | 24-Jul-17 | 11-Oct-17 | 
4 | Procurement of Survey Instruments | Goods | NCB | Prior | 12-Jul-17 | 11-Sep-17 | Bid Document under preparation
5 | Procurement of SCADA System for Durgapur Barrage | Goods | NCB | Prior | 27-Jun-17 | 13-Oct-17 | Bid Document uploaded in MIS
6 | Construction of State Data Center at Kolkata | Civil Works | NCB | Prior | 2-Aug-17 | 16-Oct-17 | Bid Document under preparation
7 | Construction of Regional Data Center at Durgapur | Civil Works | NCB | Prior | 21-Jul-17 | 18-Sep-17 | do
8 | Procurement of GIS Software for River Research Institute | Goods | Shopping | Prior | 11-Aug-17 | 11-Oct-17 | do
9 | Procurement of Geotechnical Software for River Research Institute | Goods | Shopping | Prior | 14-Aug-17 | 11-Oct-17 | do
10 | Digitization of Data | NCS | Shopping | Prior | 17-Aug-17 | 25-Oct-17 | do
11 | Development of Mobile Apps for Surface Water Resources Information System | Goods | Shopping | Prior | 17-Jul-17 | 11-Oct-17 | do
12 | Procurement of Consultant in connection with PDS for Environmental Flow in Sundarban | CS | Direct Contracting | Prior | 21-Jul-17 | 15-Sep-17 | Decision of NIH Pending
13 | Procurement of Consultant in connection with PDS for Kangsabati Reservoir Sedimentation Assessment | CS | Direct Contracting | Prior | 19-Jul-17 | 23-Aug-17 | Not recommended
14 | Civil works related to Infrastructural Development of River Research Institute | Civil Works | NCB | Prior | 17-Jul-17 | 18-Sep-17 | Bid Document under preparation
15 | Furnishing works for State Data Center at Kolkata | Goods | Shopping | Prior | 21-Aug-17 | 6-Nov-17 | do
16 | Procurement of ITC equipment for State Data Center at Kolkata | Goods | Shopping | Prior | 27-Jul-17 | 18-Sep-17 | do
17 | Procurement of Consultant for Technical and Financial Management Support to SPMU | CS | Shopping | Prior | 21-Jul-17 | 15-Sep-17 | Not required
18 | Procurement of Tidal Gauge Sensors and Salinity Sensors Equipment in connection with PDS for Environmental Flow in Sundarban | Goods | NCB | Prior | 3-Aug-17 | 23-Oct-17 | Related with PDS

## Slide 9: Status of Various Studies / PDS
Pds for environmental flow in sundarban: approval pending from nih.
PDS for kangsabati Reservoir: presented during first r&D sessions on 13-14 th july 2017 at nih, roorkee. The proposal has not been recommended by the Expert committee.

## Slide 10: Status of Data entry in E-SWIS
Registration in e-swis is under process. Request for log in id and password sent to npmu on 10/08/2017.

## Slide 11: Status of Hydro-met Stations
1. Ordinary rain gauge sites under I&Wd
proposed to be upgraded in nhp : 39 nos.
2. Newly Proposed rain gauge sites in nhp : 15 nos.
3. Ordinary river gauge sites under i&wd
Proposed to be upgraded in nhp : 44 nos.
4. Newly Proposed river gauge sites to be
upgraded in nhp : 27 nos.
(list of 54 nos. meteorological monitoring stations and 71 nos. hydrological monitoring stations was sent to ce, tbo, cwc, siliguri, Darjeeling for vetting on 30th may, 2017 for reconciliation)

## Slide 12: Status of State WRIS
Bid documents related to ‘Supply, Installation and Commissioning of Integrated GIS and Mobile Based Surface Water Resource Information System for West Bengal’ is under preparation.
Bid document of ‘Digitization of data’ is under preparation
Bid document for ‘procurement of 150 nos. mobile phones’ is under preparation.

## Slide 13: Status of PFMS
Jalasampad Bhawan
24 Parganas (North)
Executive Engineer, Burdwan Investigation & Planning Division, I&WD
DDO
0342 2646799
23370281
8900890704

## Slide 14
THANKS