## Slide 1: Central Ground Water Board
First World Bank Mission
24.08.2017

## Slide 2: Details of SPMU (in position), Staff Strength etc
Chairman, CGWB: Coordinator
Member (RGI): Project Director, CGWB
Regional Director (HP) – CHQ-Nodal Officer
Regional Director of 18 Regions
Senior Hydrogeologist (Scientist D/ Scientist C)-1
Procurement cell of CGWB - 3
System Analyst - 1
Computer Programmer - 1
Junior Hydrogeologist / Assistant Hydrogeologist-1
Ministerial Staff for keeping accounts -1
HP cell at each of 18 Regions to carry out HP activities
Senior Hydrogeologist (Scientist D/ Scientist C) - 1
Junior Hydrogeologist / Assistant Hydrogeologist - 1
Ministerial Staff for keeping accounts - 1

## Slide 3: Funds Received & Expenditure Incurred
Year | Fund Received (Rs in Lakh) | Expenditure Incurred (Rs in Lakh)
2016-17 | 65.00 | 16.62
2017-18 (as on July 2017) | 768.20 | 0.57

## Slide 4: Major Procurement item in PIP (Item Code, Item and amount)
Item Code | Item Name | Total (Rs in lakh) | Remarks
C1.1.01 | Hiring of Consultancy Services | 2875 | LS Provisions TBS Consultancy for Center of Excellence, PDS study, River Basin Management Study Liaison with State Implementing agencies
B1.1.01 | e GEMS Consultancy | 2250 | LS Provisions Single Source/QCBS Design, Development of Additional Module Procurement of Additional Licenses & training for Pan India Expansion Linking/integration of CGWB database with India-WRIS
A1.2.03 | Construction of wells (PDS in parts of Ganga Basin) | 960 | Part of PDS Study in parts of Ganga Basin Construction of wells through outsourcing down to a maximum of 300m
C2.2.02 | Pilot study at selected location for Aquifer remediation (PDS) | 440 | LS provisions Part of PDS & to be taken up as a later part of the study

## Slide 5: Major Procurement item in PIP (Item Code, Item and amount)
Item Code | Item Name | Total (Rs in lakh) | Remarks
A1.2.02 | Construction of 60 Piezometers through outsourcing | 435 | Real time monitoring of water quality in coastal aquifers in Tamil Nadu & UT of Puducherry
D2.1.01 | National / International Trainings | 400 | L S Provision
D2.3.01 | Training in colloboration with USGS | 295 | LS Provision
C2.2.01 | Water quality sample analysis & isotope dating | 185 | LS Provisions Shopping or Direct Contracting
A3.5.01 | Centre of Excellence: Procurement of Software and AMC | 148 | LS provision Procurement of software, AMC
A1.2.01 | Real time monitoring of water quality in coastal aquifers in Tamil Nadu & UT of Puducherry (DWLR with water quality probes-Supply, installation, realtime data acquisition & maintenance) | 108 | Real time monitoring of water quality in coastal aquifers in Tamil Nadu & UT of Puducherry

## Slide 6: Major procurement item in AWP 2016-17 & their Status (Item Code, Item and amount)
Item Code | Item Name | Total (Rs in lakh) | Remarks
D2.1.01 | National / International Trainings | 35.0 | Three Officers were trained at IHE-Delft, The Netherlands The amount was withdrawn from CGWB & paid by NHP wing directly

## Slide 7: Major procurement item in AWP 2017-18 & other state (Item Code, Item and amount)
Item Code | Item Name | Total (Rs in lakh) | Remarks
A1.2.01.04 | Procurement of DWLR with Water quality probes and with Telemetry (Supply, installation, real-time data acquisition & maintenance) | 43.20 | Real-time Monitoring of WQ in coastal Aquifers
A1.2.02.03 | Construction of 60 Piezometers through outsourcing | 435.00 | Real-time Monitoring of WQ in coastal Aquifers
A1.2.03.04 | Drilling through Outsourcing-Shallow (down to a maximum depth of 300m) -160 nos. | 96.00 | Part of PDS
C1.1.01.01 | Hiring of Consultancy Services (Center of Excellence, PDS study, River Basin Management Study, procurement of Goods/services/works and liaison with State Implementing agencies) | 71.75 | Agency or consortium to provide Time Based Consultancy for various activities

## Slide 8: Physical Progress
Item Code | Item Name | Status
D2.1.02 | Domain specific training (In-house) | 2016-17 – 3 Nos Completed
D2.2.01 | Workshops / Awareness Programmes | 2016-17 – 6 Nos Completed 2017-18 – 2 Nos Completed
D2.1.01 | International Training | 2016-17 – 3 officers trained at IHE-Delft, The Netherlands
Completed

## Slide 9: Physical Progress
Item Code | Item Name | Status
A1.2.02.03 | Construction of 60 Piezometers through outsourcing | Bid Documents under submission to NHP Wing for NOL & Approval
D2.1.02 | Domain specific training (In-house) | 2017-18 – 3 Nos Proposal submitted to NHP Wing & Approval Awaited
D2.2.01 | Workshops / Awareness Programmes | 2017-18 – 4 Nos 2 each to be completed in Quarter 3 & 4
D2.1.01 | International Training | Awaiting Approval A team of 20 GW modelers to be created in CGWB through customized training at IHE-Delft, The Netherlands
D3.2.02.02 | Hiring of Vehicle | In the process of procurement (GeM portal)
D4.1.01.02 | Hiring of Data Entry operator, Account Assistant, other experts (Junior) etc. | Awaiting Approval
A3.4.01.03 | Purchase of Colour Photocopier | In the process of procurement (GeM portal)
A3.4.01.04 | Purchase of Printer (Colour/B&W) | In the process of procurement (GeM portal)
Process Underway

## Slide 10: Physical Progress –Proposed
Item Code | Item Name | Physical Progress
A1.2.01.04 | Procurement of DWLR with Water quality probes and with Telemetry (Supply, installation, real-time data acquisition & maintenance) | Specification for DWLR with WQ probe and Telemetry is to be finalized in Interdepartmental Committee for Framework Agreement
A1.2.03.04 | Drilling through Outsourcing-Shallow (down to a maximum depth of 300m) -160 nos. | Part of PDS Finalization of modalities with NIH as a partner organization
C1.1.01.01 | Hiring of Consultancy Services (Centre of Excellence, PDS study, River Basin Management Study, procurement of Goods/services/works and liaison with State Implementing agencies) | To finalize different components, after finalization of TAMC contract, as the consultancy is interlinked

## Slide 11: Status of Bid Document
Item Code | Item Name | Status
A1.2.02.03 | Construction of 60 Piezometers through outsourcing | Bid Documents under submission to NHP Wing for NOL & Approval

## Slide 12: Status of various Studies / PDS etc
Real-Time Monitoring of WQ in Coastal Aquifers of TN & UT of Puducherry
  Bid Document under submission to NHP wing for NOL of WB & Approval
  Specification for Framework Agreement to be finalized by interdepartmental committee and will be floated after the award of construction of piezometers
  PDS in the sub basin above the confluence of Ram Ganga with Ganga
    Clarifications received from NHP wing about using NIH as partner Organization
    To finalize the modalities with NIH as a partner organization

## Slide 13
General comments
Total / optimal number of monitoring wells required for the State based on Current / specific objectives of monitoring Prevailing hydrogeological conditions Broad objectives of national level monitoring. Every assessment unit in the country: One Piezometer fitted with DWLR and telemetry and the data shall be converged on a single platform for common access. Strengthening and optimization of monitoring wells based on number of existing Piezometers of CGWB and States. Piezometers should be a dedicated one for water level and quality monitoring & should not be used for withdrawal of ground water Dug wells will continue to be monitored and shall be replaced with Piezometers in phases. The water level data collected from dug wells shall be used with caution and after suitable validation for all planning purpose. Strong GW Directorate of State Government manned by domain expert required Critical ground water situation Complex aquifer situation Continuing heavy dependence on ground water
Status of Hydromet Station (Summary of Committee Zonal meetings)

## Slide 14
Zone | States | Meeting Held on | Venue | Remarks
South | Kerala, Tamil Nadu, Puducherry, Telangana, Andhra Pradesh, Karnataka, Goa | 20-21 July 17 | Chennai | Karnataka did not provide data Goa could not participate as no Hydrogeologist is available to process Karnataka & Goa to be taken up separately.
North | Punjab, Haryana, HP, UP | 24 July17 | New Delhi | Haryana has not provided data & RD, CGWB to take up joint exercise with State IA UP had sought different dates due to Assembly Session
East | NE States, WB, Bihar, Jharkhand, Odisha | 3-4 Aug 17 | Kolkata | Manipur and Mizoram were not represented . No proposal from Assam & Sikkim.
West | Rajasthan, Gujarat, Maharashtra, MP, Chattisgarh | - | Ahmedabad | On request of State, meeting postponed due to flood in Ahmedabad. New Date to be decided
Status of Hydromet Station (Summary of Committee Zonal meetings)
Total IAs 26 | Reviewed 20 | Completed 16 | Yet to be Finalized 4 – 3 IAs not ready for review (Karnataka, Goa, Haryana) 1 – To be finalized (Punjab) | To review 6 (Raj, Guj, Chat, MP, UP, Mah)

## Slide 15
Zone | Remarks
South | AP& Telangana: 3 piezometers in each water shed at Recharge, Intermediate and Discharge areas. Piezometers of CGWB will also be utilized by state Government to install DWLR with telemetry. Kerala: The proposed 150 Nos DWLR with Telemetry may be taken up at the earliest in the existing Piezometers. Additional Piezometers with Telemetry will be considered during the Mid-Term review based on the performance of the State (152 Blocks). Tamil Nadu: Install DWLR with telemetry in all these blocks in the existing piezometers of State Govt. or CGWB (already approved in the PIP). Further requirement of piezometers (phirka wise, as proposed the State representative) to be considered on data analysis. Karnataka & Goa: CGWB to hold discussions with State IAs to firm up the network requirement
Status of Hydromet Station (Summary of Committee Zonal meetings)

## Slide 16
Zone | Remarks
North | HP: Proposal of State IA recommended. Pin pointing of the final locations for piezometers shall be a joint exercise of State Agency and CGWB Punjab: To establish a mechanism for regular interaction and coordination between the Water Resources Department and the D/o Drinking Water & Sanitation. CGWB to discuss with State Agency and finalize the proposal of the state for constructing shallow piezometers in South Western Punjab (960 Nos), keeping in view its objectives Haryana: Haryana has not provided data & RD, CGWB to take up joint exercise with State IA. Another meeting proposed at Chandigarh to visit field area & consider Punjab & Haryana Proposals, after discussing with RD, CGWB
Status of Hydromet Station (Summary of Committee Zonal meetings)

## Slide 17
Zone | Remarks
East | NE States RD, NER, CGWB, Guwahati will coordinate with National Ground Water Institute, Raipur to conduct at least 2-3 trainings per year at suitable locations in the North Eastern Region Odisha Odisha GW, in consultation with CGWB will first identify potential sites and initiate installation of DWLR with telemetry (as per PIP, 600 DWLR with telemetry are proposed) After analyzing the data received from these, the new piezometers will be constructed based on the gaps identified. Existing piezometers are enough to have a density of 3 wells per assessment unit on an average for the entire State (314 Assessment Units) Bihar Recommended construction of 40 Piezometers with DWLR with telemetry proposed under NHP are for deeper aquifers in all districts West Bengal Implementing Agency (West Bengal GW), is already monitoring 301 Piezometers through DWLR with telemetry All the proposed 700 DWLR & 236 Piezometers were approved, to be installed in consultation with CGWB, ER.
Status of Hydromet Station (Summary of Committee Zonal meetings)

## Slide 18: Status Public Finance Management System (PFMS)
PFMS is already established in CGWB
Payments are being made through PFMS

## Slide 19: Way forward
Establishment of Real-time Monitoring in coastal Aquifers of TN & UT of Puducherry
PDS to be taken up in partnership with NIH
Hiring of consultants for establishment of Centre of excellence in CGWB
Training of a team of officers in GW modelling at IHE-Delft, The Netherlands
Complete Domain Specific Training at NGI, Raipur
Complete 4 more Awareness Raising Programme

## Slide 20
Thanks