## Slide 1: SPMU Details
Sl. No. | Post under NHP | Name | Designation
1. | Project Co-ordinator | Shri S. K. Sinha | Executive Director (Civil)
2. | Nodal Officer | Shri S. B. Pandey | Dy. Chief Engineer (Civil), Water Resources
3. | Sr. Water Management Expert | Shri Bijay Sarkar | Dy. Chief Engineer (Civil), Engineering & Planning
4. | Superintending Officer | Shri S. K. Maji | Superintending Engineer (Civil) & Manager, Reservoir Operations
5. | Hydrologist | Md. Nasim Ansari | Executive Engineer (Civil)
6. | Hydro-Met Instrumentation Expert | Shri Dipankar Ghosh | Executive Engineer (Civil)
7. | Accounts Officer | Shri Ramjee Pandey | Dy. Manager (Finance)
8. | Data-based Management Expert | Shri Atul Kumar Singh | Assistant Engineer (Civil)
9. | Data Entry Operator | Md. Abdul Rahman | Jr. Clerk cum Typist
Note: In addition to members of the SPMU (in position), there are 10 nos. of Officers / Staffs associated with NHP. |  |  | 

## Slide 2: Status of Fund (Qtr. Ending 30th June, 2017)
Chart: 
| Expenditure made | Fund Received
 | 14.85 | 234
Financial Year | Funds Received | Expenditure made | Financial Progress | 
2016-17 | 30.87 | 6.08 | 20 % | 
2017-18 | 209.00 + 24.79* 233.79 | 14.85 Target Q1-58.45 | 15% in Q1 | 
Rs. in Lakh
*Balance of FY: 2016-17 which was revaluated for FY: 2017-18
Up-to-date Committed expenditure : Rs. 5 Lakh
Bid document for Hydrology Control Room was sent to NPMU on 27.01.17. NOL was received on 22.03.17. NIT was floated on 14.06.17 and opened on 17.07.17. There was no response & it was re-tendered on 19.08.2017.
Chart: 
| Fund Received | Expenditure made
Sales | 30.87 | 6.08
Expenditure made 6.08
Expenditure made in Q1
Fund Received

## Slide 3
Sl. No. | Item Code | Item | Amount
1. | A1.1.01 | RTDAS for DVC | 726.80
2. | A1.1.02 | Real Time Monitoring System for M & I Water Supply | 250.00
3. | A1.5.01 | Construction of Water Quality Lab and its furnishing | 300.00
4. | A1.6.01 | Water Quality Lab Equipments | 300.00
5. | A3.1.01 | Construction of Hydrological Data Centre of DVC | 250.00
6. | A1.10.01 | Integrated Reservoir Monitoring of 04 nos. of DVC’s Dams which are at Maithon, Panchet, Konar and Tilaiya in the state of Jharkhand | 347.64
7. | C1.2.01 | Inflow Forecasting system and Stream Flow measurement for Damodar Basin upto outfall of Damodar River | 250.00
8. | C2.3.01 | Sedimentation Survey of 04 nos. Reservoirs of DVC | 80.00
in Rs. lakh
Major Procurement Items in PIP

## Slide 4
Sl. No. | Item Code | Item | Total Allocated Fund (INR lakhs) | Amount kept in FY: 2016-17 (INR lakhs) | Status
1. | A1.5.01 | Construction of Water Quality Lab and its furnishing | 300.00 | 3.00 | The fund was received in Feb., 2017. As such, administrative and technical sanction could not be arranged and NIT could not be floated.
2. | A3.1.01 | Construction of Hydrological Data Centre of DVC | 250.00 | 3.00 | “do”
Major Procurement Items in AWP 2016-17

## Slide 5
Sl. No. | Item Code | Item | Total Allocated Fund (INR lakhs) | Amount kept in FY: 2017-18 (INR lakhs) | Status
1. | A1.1.01.01 | RTDAS for DVC | 726.80 | 200.00 | Hydromet sites have been finalized in consultation with CWC on 21.07.2017 and the final bid document will be submitted by 31.08.2017 for prior review
2. | A1.1.01.02 | Procurement of server of RTDAS | 10.00 | 10.00 | Procured and installed successfully. In operation w.e.f. 20.07.2017.
3. | A1.1.02.01 | Procurement of Automated Pipe Flow Measurement sensors for Drinking /Industrial water supply for 40 nos. of consumers with GSM telemetry | 250.00 | 75.00 | Bid Document is under preparation and will be submitted to NPMU for prior review by 30.10.2017
4. | A1.5.01.02 | Construction of Water Quality Lab and its furnishing | 300.00 | 50.00 | Drawing & Estimation is under process.
5. | A1.9.02.01 | Operation & Maintenance of 09 nos. of existing hydrological sites of DVC | 300 | 30.00 | The said work has been finalized & awarded on 04.08.2017
Major Procurement Items in AWP 2017-18

## Slide 6
Sl. No. | Item Code | Item | Total Allocated Fund (INR lakhs) | Amount kept in FY: 2017-18 (INR lakhs) | Status
6. | A3.1.01.02 | Construction of Hydrological Data Centre of DVC | 250.00 | 75.00 | Date of NIT: 14.06.2017 Date of opening of technical bid : 17.07.2017 No Response NOL for retendering received : 09.08.2017 Date of opening : 16.10.2017
7. | C1.2.01.01 | Inflow forecasting system and stream flow measurement for Damodar Basin upto outfall of Damodar River | 250.00 | 20.00 | ToR is under preparation and will be submitted to NPMU for prior review by 31.08.2017.
8. | C2.3.01.01 | Sedimentation survey of 4 nos. Reservoirs of DVC which are Maithon, Panchet, Tilaiya and Konar | 80.00 | 5.00 | ToR is under preparation in consultation with CWC and work will be awarded by 31.12.2017.
Major Procurement Items in AWP 2017-18

## Slide 7
Status of Bid Document for the major works approved in
FY: 2016-17 and 2017-18
Sl. No. | Item | Expected Proposal Submission date (as per AWP) | Expected Contract Award date (as per AWP) | Status
1. | RTDAS for DVC | 16.05.2017 | 25.08.2017 | Optimization of Hydromet sites finalised on : 21.07.2017. Submitted to Director River Data Compilation Directorate, CWC with copy to NPMU on 27.07.2017. Proposed Bid document submission date : 31.08.2017. Proposed Expected contract award date : 30.01.2018
2. | Procurement of Automated Pipe Flow Measurement sensors for Drinking / Industrial water supply for 40 nos. of consumers with GSM telemetry | 12.06.2017 | 15.09.2017 | Finalization of tech-specs in consultation with FloodKon. Proposed Bid Document submission date for prior review : 30.10.2017. Proposed Expected contract award date :28.02.2017.

## Slide 8
Sl. No. | Item | Expected Proposal Submission date (as per NPMU) | Expected Contract Award date (as per NPMU) | Status
3. | Construction of Hydrological Data Centre of DVC | 27.01.2017 | 28.04.2017 | NIT floated on :14.06.2017. Technical bid opened on: 17.07.2017. No response NOL received on : 09.08.2017. Revised NIT date : 16.08.2017. Date of opening of technical bid : 16.10.2017. Proposed Expected contract award date : 30.12.2017.
4. | Inflow forecasting system and stream flow measurement for Damodar Basin upto outfall of Damodar River | 22.09.2017 | 18.12.2017 | ToR is under preparation. To be submitted to NPMU on 31.08.2017. Proposed Expected contract award date : 30.04.2018.
5. | Sedimentation survey of 4 nos. Reservoirs of DVC which are Maithon, Panchet, Tilaiya and Konar | 12.09.2017 | 18.11.2017 | ToR is under preparation in consultation with Watershed & Reservoir Sedimentation Directorate, CWC. Proposed Expected Contract Award date : 31.12.2017.
Status of Bid Document for the major works approved in
FY: 2016-17 and 2017-18

## Slide 9
DVC has not proposed any PDS in FY: 2016-17 & FY: 2017-18. However details of PDS proposed in PIP are listed below:
Status of various Studies/PDS
Sl. No. | Item Code | Item | Total Allocated Fund (INR lakhs)
1. | C1.1.01 | River Basin Assessment of Damodar Basin (include water availability study & Future water utilization) | 220.00
2. | C2.1.01 | Water Quality Studies of Surface and Ground Water of Damodar Valley Catchment | 75.00
3. | C2.3.02 | Studies of Flood Inundated Areas of Damodar Valley Basin | 60.00
4. | C2.4.01 | Study for exploration of Conjunctive use of Surface water with Ground Water | 65.00

## Slide 10
Presently DVC is not entering data in E-SWIS. Proposal for getting the user ID and Password was sent to NPMU on 17.08.2017. Once we get the User ID and Password DVC will be a part of E-SWIS.
Status of Data Entry in E-SWIS

## Slide 11
The Hydromet Stations in respect of DVC has been finalized in consultation with Chief Engineer (CWC), LGBO, Patna on 21.07.2017 which was intimated to Director River Data Compilation Directorate, CWC and NPMU on 27.07.2017.
Status of Hydromet stations

## Slide 12
In PIP approved for DVC, none of the items of WRIS has been kept. Hence, it is not applicable to us.
Status of State WRIS

## Slide 13
Presently DVC is not using Public Finance Management System (PFMS) for efficient & effective tracking of Grant-in-aid (fund) received from the MoWR, GoI for implementation of National Hydrology Project.
Status of PFMS

## Slide 14: Issues
To achieve the time-line for RTDAS, frame work agreement by NPMU needs to be finalized at the earliest.
On advice of the MoP, GoI DVC has signed Memorandum of Understanding (MoU) for 2017-18 with the ministry for management and control of Reservoir Operation & irrigation with application of GIS technology.
As per the time-line fixed in the MoU, tender for procurement of GIS software is to be finalized by the end of Mar’18.
A provision of Rs 90 lakh has been made in the approved PIP for DVC which has not been proposed in the approved AWP of 2017-18.
As such procurement of GIS softwares needs to be included in the AWP of 2017-18 to ensure finalization of Tender by Mar’18 as committed by DVC to MoP.
Proposal to this effect has already been sent to NPMU on 20.08.17 for consideration. NPMU has been requested to include this item of works in AWP of FY 2017-18.

## Slide 15
DVC is preparing to achieve revised targets for works under NHP.
We will complete all the works within the stipulated time frame.
As per the approved annual plan 2017-18, total fund allocated is Rs. 537 lakh. First instalment of Rs. 209 lakh for FY 2017-18 was received in July’17. Fund available in FY 17-18 is Rs.234 lakh.
Quarter wise expenditure plan for FY: 2017-18.
Additional fund requirement in FY: 2017-18 over & above Rs. 184 lakh is Nil.
Fund requirement in FY: 2018-19 is Rs. 303 lakh.
Way Forward
Quarter | Proposed Expenditure (Rs. in Lakh)
Q1 | 14.85
Q2 | 10
Q3 | 50
Q4 | 109.4
Total | 184.25