## Help (hidden)
S. No | Old Code | Sub-Component | Major Activities | Primary IA | Explanatory Notes
A |  | Hydromet Data Acquisition System
A1 |  | A1: Hydromet Observation Network
A1.1 | A1.1 |  | Expand and upgrade Hydromet Observation network. | States/Central | WRMS system may include: • Weather: automatic weather stations, rainfall and snow gages • Rivers: stage/discharge of rivers, water quality, rating curve updating • Groundwater: levels, water quality • Reservoirs/tanks: water levels, gate positions, outflows and spillways, update rating curves • Sediment: transport and load monitoring • Coastal monitoring • Diversions, water use and irrigation monitoring This will involve procurement of equipment for monitoring and services for commissioning, operation and maintenance. Generally, two years warranty and five years annual maintenance needs to be included in procurement documents (Refer to BBMB and Maharashtra contracts for RTDAS, RTDSS real-time, real-time flood forecasting).
A1.2 |  |  | Water use monitoring system in Reservoirs and Barrages | States | Some organizations may bid a separate HON for Reservoir monitoring including storage (water level) gate opening sensors, Water level for outflows and spillways, update rating curve using ADCPs or equivalent.
A1.3 |  |  | Strengthen Manual Observations |  | Procurement of Portable GPS based water level recorder, flow meters and other devices for measurement of river stream, GW and pipe flows. Software for acquisition
A1.4 |  |  | Water quality monitoring insitu and lab | States/Central | Procurement of WQS, AWQS, lab (equipment, consumables, staff)
A2 |  | A2: Field Surveys |  |  | River Cross-section survey, Bathymatric survey of reservoirs and any other surveys
A3 |  | A3: Hydro Informatics Centers
A3.1 | D1.1 |  | Establishment of River Basin/ State Water Informatics Center | MoWR | • Centers will be strengthened with Deputed Experts from various Departments. This would lead to an integrated Center of Excellence for water resources knowledge and analysis, including use of modern modeling tools; provision of national helpdesk services. • Project will support building and equipment, trained manpower, exchange with international/national agencies
A3.2 | D1.3 |  | Upgrading regional and (sub-) divisional offices | Central/States | Divisional data centers, office and laboratory infrastructure
A3.3 | D1.4 |  | Institutional Modernization Support, incl. ITC systems for offices and Data Centers | Central/States | Information management tools, e.g. ICT incl. cloud-based systems, videoconferencing systems, displays, softwares, manuals, information systems design
A3.4 |  |  | Development of Hydrological instrumentation facility | Central | CWPRS and other Institutes wll be equipped to support in the development of Hydromet system.
B |  | National Water Information Services
B2 |  | B2: National Water Resources Information System
B2.1 | B2.1 | Strengthening India WRIS | Web Enabled National Water Resources Information center | MoWR/CWC | • Implementation of central and state wise data storage and data dissemination systems (software; cloud computing and processing, etc.); Integrate WRIS with monitoring data from radars and satellite products; curated spatial information from legacy data and surveys. Requires active exchange platform between states and center • Provide easy access to CMIP5 climate change projections for India for the purpose of Climate Risk Assessments.
|  |  | Intrgration with extenrnal partner agencies |  | Integrate data with water use agencies including IMD, NRSC, Agriculture, Hydropower, CPCB, Watershed
A2 |  | Real time Data acquisition and repository
A2.1 |  |  | Digitization and data entry of histroical database in E-SWIS, E-GEMS- E-WQIS | Central/State | Consultancy (O&M), Training, Data-entry (including in web-portal, e-SWIS, e-GEMS, e-WQIS and their replica at state data centre)
A2.2 |  |  | Real time Transmission systems |  | Receiver at master station, service contract (if needed) for data transmission (INSAT/VSAT/GSM)
A2.3 | A2.3 |  | Upgrade centralized and web-based data entry, data storage, data management and data dissemination systems, including: e-SWIS, e-GEMS, e-WQIS and India-WRIS | Central | • e-SWIS, e-GEMS and e-WQIS were developed during HP-2. Phase 3 may support AMC, system extension and upgrading. • This sub-component would also aim at (re)establishing and strengthening data sharing and data validation protocols across state and central agencies. Integrate with India WRIS
A2.4 | A1.2 |  | Set monitoring standards: water quantity/quality, QAQC methods | Central/States | During HP1 and HP2, water quality standards, QA and AQC procedures and monitoring protocols were set by the project. Central agenies to develop standards and state agencies to implement. Application of these procedures will be strengthened and WQ laboratories need to be rationalized.
B1 |  | National Spatial Information Development
B1.1 | B1.1 |  | High resolution Topo Survey | Survey of India/NRSC | • Procurement of LiDAR or similar surveys. Development of DEM for the entire country for improved flood hazard mapping and other planning purposes • High resolution surveys such as LIDAR for flood prone areas and for purpose of flood risk mapping (<4000 km2) • High resolution remote sensing imageries and other supplementary information to develop DEM for other areas • Sharing protocol between central agencies and states needs to be streamlined to avoid delays. • Provision of high resolution imageries. Convegence of resources through other projects
B1.2 | B1.2 |  | Earth Observation (EO) products | IMD/NRSC/States | Temporal assessments may include but not be limited to: • Estimation of precipitation, snow cover and snow melt, soil moisture, land use and actual evapotranspiration (ET) • Runoff estimates as the basis for flood forecasting and reservoir operations (Hydro-India; see VIC model of NRSC); see also B2.3 • Satellite based monitoring of cropping patterns, crop conditions, droughts and water supply conditions in irrigation systems • Satellite based monitoring of water logging, water storage in tanks and other water bodies.
B1.3 | B1.3 |  | Ensemble Weather forecast products (short- and medium range) | IMD/NRSC/ISRO | • Improvement of flow forecasting, reservoir operations, crop planning, drought management, etc. • Collaborate with international agencies as required to process ensemble forecast.
B1.4 | B2.2
B2.2 | B2.1 | B2: State Water Resources Information System | Web enabled State water information center |  | Replica of NWRIS and Develop and customize State chapter out of NWRIC inclduing spatial river basin information systems provided in India-WRIS and populate with additional information from state
B2.3 | A2.1 |  | Digitize and integrate maps and doc | State agencies | Services/manpower to digitize.
B2.4 | A2.2 |  | Develop spatial river basin information systems including themes provided in India-WRIS | States, CWC and CGWB | • Themes may include: Water bodies and their usage, Canal system networks, Groundwater systems, Land use, irrigation systems, Inventories of water pollution. • Services to digitize the map. IAs can take help of NRSC/ISRO imageries Procurement of services and toposheets and imageries
B2.5 |  |  | Integrate data with water use stakeholders including PHED, Agriculture etc |  | Procurement of serviced to develop data conversion software or digitization of data for Water quality data from PHED, land use and land cover from agriculture, watershed structures
B3 |  | B3:Information Sharing and Dissemination
B3.1 |  |  | Data sharing and exchange | CWC/CGWB/NRSC | • This would allow integrating online data available in other sources/departments/international sources. Also link digital-online libraries. • The same system will be updated with information products such as online yearbooks, online interactive atlases, customizable interactive visualization dashboards, benchmarking products. • Customizable knowledge portals and mobile Apps; Bulletins (e.g. flood forecasting)
B3.3 |  |  | Information Product |  | India WRIS (DEM, LULC updated, Climate forcast, Hydromet data from state & central agencies, Basin wise water balance assessment & budgeting, Aquifer assessment and budgeting, Advance river flow, Weather model forcast, disaster alert system, Water efficiency*) with State Replica
B3.2 |  |  | Information Dissemination |  | Public alert, EAP, Historical map of flood & droughts, block level water availability, use & efficiency assessment, Reservoir water availability advance information. Canal supply information; ambient water quality information; average historical river flow information
C |  | Water Resources Operation and Planning System
C1 |  | C1: Analytical and DSS tools
C1.1 |  |  | Water Resources Assessment Tools | CWC/River Basin organizations | Systems for river basin planning; water balance assessments; flood forecasting, at Macro Scale by CWC. The consutlancy for setting up river basin modellling frameowork will be procured by CWC or concerned RBOs and will be provided to states for downscaling.
C1.2 | C1.2 |  | Flood forecasting system for interstate basins | CWC/River Basin organizations | This would help understand seasonal forecasts for floods, flows, inundation, droughts.
C1.3 |  |  | Flood forecasting at State level/Sub-basins level | State/RBO | Procure - river cross-section survery for input to the hydraulic model, - consutlancy for downscaling as described above or setup new model for their specialized case. - Also the DSS setup during HP2 will be further strengthened.
C1.4 | C1.1 |  | Hydrologic Design Aids | CWC | Consultancy (for upgrade and training) deveoped during HP2 for flood,sedimentation and water availablity
C2 |  | C2: Irrigation operation and management systems
C2.1 |  |  | Integrated Reservoir Operation Systems | States/River Basin bodies | For reservoirs, irrigation systems operations, flood preparedness, spill management, and other water infrastructure
C2.2 |  |  | Automtated reservoir and canal operation systems | States/RBO | Procurement of SCADA system for automated operation
C2.3 |  |  | Irrigation system assesment | States | Benchmarking, Irrigation system efficiency, Water use efficiency
C3: Groundwater Management
C3 |  |  | Surface-Groundwater interaction | CGWB/States | Impact on tanks, baseflow in the rivers, aquifer connectivity with stream/canals.
C3.1 |  |  | Conjuctive use | CGWB/States | Prepare conjuntive use plans to increase the gross irrigated area including strategy suggested in PMKSY...
C3.2 | A3.4 |  | Groundwater exploration and aquifer mapping | States/CGWB | States need to match their hotspots with CGWB in order to avoid duplication.
C3.3 |  |  | Decision Support System (DSS) for ground water development, management and artificial recharge | CGWB | CGWB to developed the DSS software and support the states in it application. The modelling centre proposed for GW should focus on developing this software
C4 |  | C2: Purpose Driven Studies
C4.1 | C2.2 |  | Reservoir sedimentation assessment | States | Procurement of services/equipments
C4.2 | C2.2 |  | Bathymetric river surveys in critical areas | States | Procurement of services.
C4.3 | C2.2 |  | Assess water quality/waste loads | States | Design monitoring system to assess loading, fate and transport of constituents within water quality limited hotspots
C4.4 | C2.2 |  | Others - TBD | All IAs | This would/may include monitoring, information generation and studies of specific issues, as conducted under HP-II, including also Climate Risk Assessments of present and planned WR infrastructure
C4.5 | C2.1 |  | Others - TBD | States/River Basin bodies | Such as River Basin Management Plans, Status of India’s Water Resources
C4.6 | A1.3 |  | Community based monitoring and water management | States/Central | • Pilot a community based, mobile monitoring system for small streams, groundwater, water bodies, flooding, embankment status (crowd sourcing) • Procurement of mobile based services and mobilizing the communities for the monitoring of local water resources. NRSC/ISRO has already piloted this approach.
|  | C3:Knwoledge Products and Dissemination |  |  | • This would allow integrating products developed in various applications and publish final prodcuts on web, atlas or contribute to various reports
D |  | WR Institutions Capacity Enhancement
D1 |  | D1: Water Resources Knowledge Centers
D1.1 |  |  | Modernization of National Training centers such as NIH, NWA and other regional central Institutes, Centers of excellence | Central | Facilities, trained manpower, exchange with international/national agencies; MOU with reputed National and International research Institutes
D1.22 |  |  | Modernize State level Training Institutes such as WALMI for Modern irrigation and water management practices | All IAs | Strengthening WALMIs to provide technical support to State IAs, including regarding improvement of irrigation system management.
D1.3 |  |  | Collboarate with academia for modelling centers and introduction of courses |  | Support to universtities for introduction of project related courses
D1.4 | D2.1 |  | Policy Support |  | Policy on data pooling, data quality management, enhancing public-domain information.
D1.5 | D3.2 |  | Class room Training/Meetings and multi-media distance learning |  | This will include curriculum development, technical courses, refresher courses, Training/Meetings in use of EO products readily available, etc. Multi-media distance learning may include videoconferencing, e-learning (e.g. self-paced courses, webinars, MOOC), vendor fairs, regular video & audio podcasts, documentaries.
D1.6 |  |  | Access to knowledgebank |  | Creation of e-library including subscription to Journals, web-based course introduced eleswhere or any other knowledge source
D1.7 | D2.2 |  | Strengthened Partnerships and study tours |  | Strengthened Partnerships with earth observation data and other knowledge providers, open data initiatives, academia, CSOs, internships/visiting experts/development assignments, international exchange program, and overseas and domestic study tours
D2 |  | D2. Professional Development
D2.1 | D3.1 |  | Annual Water Resources Knowledge Forum | All IAs | This would support showcasing the best of what India has to offer and facilitate knowledge exchange; also various competitions may be introduced (e.g. Online Tools, Appathons, Hackathons).
D2.2 |  |  | Workshops | All IAs | Thematic workshops
D2.3 |  |  | Publications | All IAs | Prininting of reports, publication cost in journals/books
D2.4 |  |  | Website | States | Procurement of consultancy for website development.
D3 |  | D3: Project Management and Technical assistance
D3.1 | D4.1 |  | Establishing CPMU at MoWR and PMUs at Implementing Agency level | MoWR | Cost of infra-structure, manpower and furnshing and man power requirement
D3.2 | D4.2 |  | Technical Assistance and Management Consultancy at Center and State level | States/ Central Agencies | TAMC Consultancy for technical assistance and support for procurement, financial management, and MIS and M&E services; general TA support at State level
D3.3 |  |  | Internatioal Advisory experts/ Think Tank | MoWR/IAs
D4 |  | Operating cost
D4.1 | D5.1 |  | Incremental staff cost for O&M of HIS/WRIS | All IAs | Total cost to be included for each year, even though staff cost are generally reimbursed on a gliding scale.
D4.2 |  |  | Recurrent cost for operation of offices | All IAs | Office vechiles etc will come under this

## PIP Cost Tab (hidden)
Componant ID | Sub Comp ID | Activity ID | Componant | Item Code | Items | Type | Unit Cost | Quantity | Total Cost in Lakhs | Plan 1 | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[11 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Cost of Procurements in lakhs | Remarks For year 2016
A | Hydromet Data Acquisition System |  | Hydromet Data Acquisition System
| A1 | Hydromet Observation Network | Hydromet Observation Network
|  | A1.1 | Real Time Data Acquisition System (RTDAS) | A1.1.01 |  |  | 0 | 0 | 0
|  |  |  | A1.1.02 |  |  | 0 | 0 | 0
0
0
0
|  | A1.2 | Civil Works for Hydromet System (RTDAS) | A1.2.01 |  |  | 0 | 0 | 0
|  |  |  | A1.2.02 |  |  | 0 | 0 | 0
0
0
0
|  | A1.3 | Geo-referencing of the monitoring and extraction units in the State through DGPS | A1.3.01 | All monitoring wells to be geo referenced using DGPS | CS | 750 | 3500 | 26.25 | 3500 | 2016 Q3: 1750; 2016 Q4: 1750 | 26 | 26
0
|  | A1.4 | Groundwater Measurement Equipment | A1.4.01 | DWLR with Telemetry | Goods | 125000 | 175 | 218.75 | 175 | 2017 Q2: 50; 2017 Q3: 75; 2017 Q4: 50 | 219
|  |  |  | A1.4.02 | DWLR without Telemetry | Goods | 100000 | 500 | 500 | 500 | 2017 Q2: 125; 2017 Q3: 175; 2017 Q4: 200 | 500
|  |  |  | A1.4.03 | Sampling pump | Goods | 100000 | 13 | 13
|  |  |  | A1.4.04 | GW Monitoring Equipment (WL Indicator, measuring tape, stop watch) | Goods | 25000 | 40 | 10 |  | 2016 Q2: 40 | 10 | 10
|  |  |  | A1.4.05 | Resistivity meter | Goods | 250000 | 13 | 32.5 | 13
|  |  |  | A1.4.06 | Borehole logging equipment | Goods | 15000000 | 1 | 150
|  |  |  | A1.4.07 | DWLR with quality probes | Goods | 450000 | 75 | 337.5 | 75 | 2017 Q3: 75 | 338
|  |  |  | A1.4.08 | DWLRs with telemetry for DSS for urban Hydrology | Goods | 125000 | 6 | 7.5
|  |  |  | A1.4.09 | Geological Survey Kits | Goods | 5000 | 20 | 1 |  | 2016 Q2: 20 | 1
|  |  |  | A1.4.10 | AWS for DSS on Urban Hydrology | Goods | 300000 | 3 | 9
|  |  |  | A1.4.11 | WQ kits for DSS on Urban Hydrology | Goods | 500000 | 1 | 5
|  |  |  | A1.4.12 | Raingauges for DSS on Urban Hydrology | Goods | 10000 | 20 | 2
0
|  | A1.5 | Civil Works for Groundwater Monitoring | A1.5.01 | Shallow/open wells | Works |  | 0 | 0
|  |  |  | A1.5.02 | Medium/Deep piezometers (Bore well+protection works) | Works | 75000 | 600 | 450 | 600 | 2016 Q2: 200; 2016 Q3: 200; 2016 Q4: 200 | 450 | 450
|  |  |  | A1.5.03 | Deep piezometers (Tube well+protection works) | Works | 300000 | 150 | 450 | 150 | 2016 Q2: 50; 2016 Q3: 50; 2016 Q4: 50 | 450 | 450
|  |  |  | A1.5.04 | Construction of Borewells for PHM Monitoring | Works | 50000 | 10 | 5
|  |  |  | A1.5.05 | Construction of tubewells in PDS-I studies | Works | 100000 | 10 | 10
|  |  |  | A1.5.06 | Drilling of Observation Wells in PDS-II Sudies | Works | 50000 | 15 | 7.5
|  |  |  | A1.5.07 | Drilling of bore holes for studies in aquifer mapping in OE basins of Prakasam and Chittoor districts | Works | 75000 | 50 | 37.5
|  |  |  | A1.5.08 | Procurement of PHM equipment for conducting well performance test | Goods | 5000 | 736 | 36.8
0
|  | A1.6 | Water Quality Labs | A1.6.01 | Civil Works for Water Quality Lab Buliding | Works | 0 | 0 | 0
|  |  |  | A1.6.02 | Furnishing of Water Quality Lab | Goods | 0 | 0 | 0
|  | A1.7 | Water Quality Equipment | A1.7.01 | Automatic Water Quality Sensors- 11 Parameters (online) | Goods | 0 | 0 | 0
|  |  |  | A1.7.02 | WQ Field Kit 1 | Goods | 750000 | 5 | 37.5
|  |  |  | A1.7.03 | WQ Field Kit 2 | Goods | 40000 | 5 | 2 |  | 2016 Q2: 4 | 1.6 | 1.6
|  |  |  | A1.7.04 | WQ Field Kit 3 | Goods | 0 | 0 | 0 | [33 empty] | 0 | 0
|  |  |  | A1.7.05 | WQ Field Kit 4 | Goods | 0 | 0 | 0 | [33 empty] | 0 | 0
|  |  |  | A1.7.06 | Analytical Balance Digital | Goods | 125000 | 5 | 6.25 |  | 2016 Q2: 4 | 5 | 5
|  |  |  | A1.7.07 | Autoclave | Goods | 150000 | 5 | 7.5 |  | 2016 Q2: 4 | 6 | 6
|  |  |  | A1.7.08 | Automatic Loop Stabilizer | Goods | 150000 | 5 | 7.5 |  | 2016 Q2: 4 | 6 | 6
|  |  |  | A1.7.09 | Bacteriological Incubator | Goods | 150000 | 5 | 7.5 |  | 2016 Q2: 4 | 6 | 6
|  |  |  | A1.7.10 | Common Balance | Goods | 40000 | 5 | 2 |  | 2016 Q2: 4 | 1.6 | 1.6
|  |  |  | A1.7.11 | DO Sampler | Goods | 40000 | 5 | 2 |  | 2016 Q2: 4 | 1.6 | 1.6
|  |  |  | A1.7.12 | Double Distillation Apparatus | Goods | 835000 | 5 | 41.75 |  | 2016 Q2: 4 | 33.4 | 33.4
|  |  |  | A1.7.13 | EC-TDS Analyzer | Goods | 122000 | 5 | 6.1 |  | 2016 Q2: 4 | 4.88 | 4.88
|  |  |  | A1.7.14 | Electronic Balance | Goods | 122000 | 5 | 6.1 |  | 2016 Q2: 4 | 4.88 | 4.88
|  |  |  | A1.7.15 | Flame Photometer | Goods | 110000 | 5 | 5.5 |  | 2016 Q2: 4 | 4.4 | 4.4
|  |  |  | A1.7.16 | Laminar Air Flow | Goods | 380000 | 5 | 19 |  | 2016 Q2: 4 | 15.2 | 15.2
|  |  |  | A1.7.17 | PH Analyzer | Goods | 75000 | 5 | 3.75 |  | 2016 Q2: 4 | 3 | 3
|  |  |  | A1.7.18 | Turbidimeter | Goods | 50000 | 5 | 2.5 |  | 2016 Q2: 4 | 2 | 2
|  |  |  | A1.7.19 | UV Spectro Photometer | Goods | 900000 | 5 | 45 |  | 2016 Q2: 4 | 36 | 36
|  |  |  | A1.7.20 | Water Quality Analyzer | Goods | 150000 | 5 | 7.5 |  | 2016 Q2: 4 | 6 | 6
|  |  |  | A1.7.21 | Water testing equipments /sediment sampling package | Goods | 0 | 0 | 0 |  | 2016 Q2: 4 | 0 | 0
|  |  |  | A1.7.22 | Water Softener | Goods | 40000 | 5 | 2 |  | 2016 Q2: 4 | 1.6 | 1.6
|  |  |  | A1.7.23 | Atomic absorption spectro photo meter | Goods | 1350000 | 5 | 67.5 |  | 2016 Q2: 4 | 54 | 54
|  |  |  | A1.7.24 | Other Water Quality Lab Equipment | Goods | 1000000 | 5 | 50 |  | 2016 Q2: 4 | 40 | 40
[7 empty] | 0 | 0 | 0
|  | A1.8 | Manual Observation Equipment | A1.8.01 | Total Station | Goods | 0 | 0 | 0
|  |  |  | A1.8.02 | Theodolite | Goods | 0 | 0 | 0
|  |  |  | A1.8.03 | Levels | Goods | 0 | 0 | 0
|  |  |  | A1.8.04 | GPS – Hand held | Goods | 40000 | 40 | 16 | 40 | 2016 Q4: 40 | 16 | 16
|  |  |  | A1.8.05 | Differential GPS | Goods | 1000000 | 1 | 10
0
|  | A1.9 | Field Surveys |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
| A2 | Field Surveys | Automated System Operation and Data Acquisition |  |  |  | 0 | 0 | 0
|  | A2.1 | SCADA system for Barrages |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | A2.2 | Canal SCADA System |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
0
|  | A2.3 | Automation of Tubewell Operation |  |  |  | 0 | 0 | 0
0
| A3 | Hydro Informatics Centers | Hydro Informatics Centers |  |  |  | 0 | 0 | 0
|  | A3.1 | Construction of National Data Centres |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | A3.2 | Rennovation of National Data Centres |  |  |  | 0 | 0 | 0
|  | A3.3 | Construction of State / River Basin Data Centres | A3.3.01 | Consultancy for design, architecture etc | CS | 1000000 | 1 | 10 | 1 | [32 empty] | 10 | 10 | bar: 2016 Q4
|  |  |  | A3.3.02 | Civil Works for Construction | Works | 110000000 | 1 | 1100 | 0.25 | 2017 Q2: 0.25 | 300
|  |  |  | A3.3.03 | Assistant Chemists (WQ) | NCS | 1500000 | 1 | 15
|  |  |  | A3.3.04 | Lab Assistants (WQ) | NCS | 1100000 | 2 | 22
|  |  |  | A3.3.05 | Data entry operators (State unit) | NCS | 1000000 | 5 | 50
|  |  |  | A3.3.06 | Lab Attenders (WQ) | NCS | 800000 | 1 | 8
|  |  |  | A3.3.07 | Office subordinate (State Unit) | NCS | 800000 | 5 | 40
0
|  | A3.4 | Rennovation of State / River Basin Data Centres | A3.4.01 | Consultancy for design, architecture etc | CS | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | A3.5 | Construction of Regional/ Divisional Data Centres | A3.5.01 | Consultancy for design, architecture etc | CS | 200000 | 2 | 4
|  |  |  | A3.5.02 | Civil Works for Construction | Works | 20000000 | 2 | 400
[7 empty] | 0 | 0 | 0
|  | A3.6 | Rennovation of Regional/ Divisional Data Centres | A3.6.01 | Civil Works for Construction | Works | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | A3.7 | Furnishing of Data Centres | A3.7.01 | Procurement of ACs | Goods | 50000 | 30 | 15 | 15 | 2017 Q1: 15 | 7.5
|  |  |  | A3.7.02 | Procurement of Office Furniture | Goods | 100000 | 15 | 15 | 15 | 2017 Q2: 15 | 15
0
|  | A3.8 | IT Equipment for Data Centres | A3.8.01 | Purchase of Computers with Software | Goods | 75000 | 20 | 15 |  | 2016 Q3: 20 | 15 | 15
|  |  |  | A3.8.02 | Purchase of Workstations with Software | Goods | 125000 | 20 | 25
|  |  |  | A3.8.03 | Purchase of Servers with Software (Database, Databackup system) | Goods | 1500000 | 2 | 30
|  |  |  | A3.8.04 | Purchase of Laptops with Software | Goods | 50000 | 20 | 10 | 20 | 2016 Q3: 20 | 10 | 10
|  |  |  | A3.8.05 | Purchase of Laptops(Workstations) with Software | Goods | 100000 | 20 | 20 | [33 empty] | 20
|  |  |  | A3.8.06 | Purchase of PDA, GPS Tablets | Goods | 30000 | 20 | 6 |  | 2016 Q3: 0
|  |  |  | A3.8.07 | Purchse of Mobile Phones | Goods | 0 | 0 | 0 |  | 2016 Q3: 0
|  |  |  | A3.8.08 | Network Equipment like Switches, Firewalls, Routers | Goods | 1000000 | 2 | 20 |  | 2016 Q3: 0
|  |  |  | A3.8.09 | Network Storage and backup devices | Goods | 200000 | 15 | 30 |  | 2016 Q3: 0
|  |  |  | A3.8.10 | Installation of Network, cabling etc | Goods | 25000 | 15 | 3.75 |  | 2016 Q3: 0
|  |  |  | A3.8.11 | Communication Services (Broadband, lease-line, MPLS etc) | Goods | 2500000 | 1 | 25 |  | 2016 Q3: 0
|  |  |  | A3.8.12 | Manpower for Operation and Maintanance of IT equipment | NCS | 2000000 | 1 | 20 |  | 2016 Q3: 0
|  |  |  | A3.8.13 | Procurement of Video Conference Facility | Goods | 2500000 | 1 | 25 |  | 2016 Q3: 0
|  |  |  | A3.8.14 | Procurement of Projectors | Goods | 50000 | 15 | 7.5 | 15 | 2016 Q3: 15 | 8 | 8
|  |  |  | A3.8.15 | Printers (BW) | Goods | 10000 | 20 | 2 | 10 | 2016 Q3: 10 | 2 | 2
|  |  |  | A3.8.16 | Printers (Color) | Goods | 25000 | 20 | 5 | 10 | 2016 Q3: 10 | 5 | 5
|  |  |  | A3.8.17 | Printers (A3,color) | Goods | 50000 | 15 | 7.5 |  | 2016 Q3: 0 | 2.25 | 2.25
|  |  |  | A3.8.18 | A4 Scanner | Goods | 15000 | 20 | 3 | 15 | 2016 Q3: 15 | 2.25
|  |  |  | A3.8.19 | A3 Scanner | Goods | 50000 | 2 | 1 |  | 2016 Q3: 0
|  |  |  | A3.8.20 | WiFi routers, hotspots, WiFi USB Dongles ( for each units) | Goods | 25000 | 20 | 5 | 15 | 2016 Q3: 15 | 1.25 | 1
|  |  |  | A3.8.21 | Plotter cum scanner (A0) | Goods | 1000000 | 1 | 10 |  | 2016 Q3: 0
|  |  |  | A3.8.22 | GSM Server | Goods | 0 | 0 | 0 |  | 2016 Q3: 0
|  |  |  | A3.8.23 | Power Supply and online UPS for Data Centers (5KVA) Districts Data Centers | Goods | 100000 | 15 | 15 | 15 | 2016 Q3: 15 | 15 | 15
|  |  |  | A3.8.24 | Power Supply and online UPS for Data Centers (5KVA) State Data Center | Goods | 100000 | 5 | 5 |  | 2016 Q3: 0
|  |  |  | A3.8.25 | Photocopier (B/W) | Goods | 100000 | 20 | 20 | 15 | 2016 Q3: 15 | 15 | 15
|  |  |  | A3.8.26 | Procurement of HW & SW for PDS Studies for Pilot study for community based water management in OE basins in Anathapur district | Goods | 500000 | 1 | 5 |  | 2016 Q3: 0
|  |  |  | A3.8.27 | Procurement of HW & SW for PDS Studies for Study of behaviour of multi aquifer system for sustainable GW development kunderu sub basin in West Godavari district |  | 500000 | 1 | 5 |  | 2016 Q3: 0
|  |  |  | A3.8.28 | Procurement of HW & SW for PDS Studies for Aquifer mappng in over-exploited GEC basin in Prakasam and Chittoor district | Goods | 500000 | 2 | 10 |  | 2016 Q3: 0
0
|  | A3.9 | Software for Data Centers | A3.9.01 | ERDAS Imagine (30 licences) | Goods | 275000 | 1 | 2.75 |  | 2016 Q3: 0
|  |  |  | A3.9.02 | Arc GIS Enterprise Server Advanced (Web Based) | Goods | 7000000 | 1 | 70 |  | 2016 Q3: 0
|  |  |  | A3.9.03 | Microsoft Office, Windows etc | Goods | 75000 | 30 | 22.5 | 15 | 2016 Q3: 15 | 11.5 | 12
|  |  |  | A3.9.04 | Antivirus | Goods | 500 | 100 | 0.5 | 50 | 2016 Q3: 50 | 0.5 | 1
|  |  |  | A3.9.05 | Firewall software | Goods | 200000 | 2 | 4
|  |  |  | A3.9.06 | Adobe PDF acrobat Standard | Goods | 20000 | 20 | 4 | 15 | 2016 Q3: 15 | 3 | 3
[7 empty] | 0 | 0 | 0
|  | A3.10 | Development of Hydrological instrumentation facility |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[5 empty] | Sub Component A Sub Total |  | 0 | 0 | 4777.75 | [33 empty] | 2686.41 | 1284.41
B |  | National Water Information Services | National Water Information Services (NWIS)
| B1 | National Spatial Information Development | National Water Resources Information System |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | B1.1 | Strengthening India WRIS |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | B1.2 | Database management and Repository |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | B1.3 | National Spatial Information Development |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | B1.4 | Data Digitization |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | B1.5 | Data Exchange |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | B1.6 | Web Hosting |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
| B2 | State Water Resources Information System | Regional Water Resources Information System |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | B2.1 | Strengthening Regional WRIS |  |  |  | 0 | 0 | 0
|  |  |  | B2.1.01 | Procurement of Survey of India Geo-Referenced Topo sheets for entire Andhra Pradesh | Goods | 1000000 | 1 | 10 | 1 | [32 empty] | 10 | bar: 2017 Q2
0
|  | B2.2 | Database management and Repository |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | B2.3 | Regional Spatial Information Development |  |  |  | 0 | 0 | 0
0
|  | B2.4 | Data Digitization | B2.4.01 | Consultancy services for Geo-tagging of all Groundwater abstraction structures, collection of related information and providing data in GIS format for uploading the data in Web Site. This information will be used in groundwater estimation. Chittoor, Kadapa, Kurnool and Anatapur district will be covered completly. (approx.7.50 lakhs structures) | CS | 7000000 | 4 | 280
|  | B2.5 | Data Exchange |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | B2.6 | Web Hosting | B2.6.01 | Servers for Hosting Website and Data Services (web hosting server, database server, UPS, Firewalls, Routers, switches etc) | Goods | 2500000 | 1 | 25
|  |  |  | B2.6.02 | Internet charges for Hosting (Static IP, broadband etc) | Goods | 2000000 | 1 | 20
|  |  |  | B2.6.03 | Consultancy Services for Hosting Website Upgrading existing website) | CS | 2500000 | 1 | 25 | 1 | [32 empty] | 25 | bar: 2017 Q1
|  |  |  | B2.6.04 | Development of Mobile Applications for datacapturing and validation | CS | 1000000 | 1 | 10 | 1 | [32 empty] | 10 | bar: 2017 Q2
[7 empty] | 0 | 0 | 0
[5 empty] | Sub Component B Sub Total |  | 0 | 0 | 370 | [33 empty] | 45
C |  | Water Resources Operation and Planning System | Water Resources Operation and Planning |  |  |  | 0 | 0 | 0
| C1 | Analytical and DSS tools | Analytical and DSS tools |  |  |  | 0 | 0 | 0
|  | C1.1 | Decision Support System for River Basins | [5 empty] | 0
|  | C1.2 | Decision Support System for Groundwater Management | C1.2.01 | Consultancy Services for Setup and Operation of DSS for urban hydrology for holistic water management in fast growing industrial city of Visakhapatnam with consultancy support of Andhra University | CS | 4000000 | 1 | 40
|  |  |  | C1.2.02 | Procurement of HW & SW for DSS for Urban Hydrology in Visakhapatnam | Goods | 2000000 | 1 | 20
|  |  |  | C1.2.03 | O&M Charges | Goods | 500000 | 1 | 5
|  |  |  | C1.2.04 | Hire vehicle | Goods | 1000000 | 1 | 10
0
|  | C1.3 | Studies for establising aquifer parameters of each GEC basin in groundwater estimations | C1.3.01 | Consultancy services for conducting well performance test in each GEC Basin | CS | 75000 | 736 | 552
|  |  |  | C1.3.02 | Drilling of pumping wells and observation wells for well performance tests | Works | 50000 | 736 | 368
0
| C2 | Irrigation operation and management systems | Purpose Driven Studies |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | C2.1 | Community Based Water Management |  |  |  | 0 | 0 | 0
|  |  |  | C2.1.01 | Consultancy services to Pilot study for community based water management in OE basins in Anathapur district | CS | 4000000 | 1 | 40
|  |  |  | C2.1.02 | O & M costs | Goods | 500000 | 1 | 5
|  |  |  | C2.1.03 | Hiring of vehicles | Goods | 1000000 | 1 | 10
0
|  | C2.2 | Conjunctive use and GW recharge studies | [5 empty] | 0
|  |  |  | C2.2.01 | Consultancy Services to Study of behaviour of multi aquifer system for sustainable GW development kunderu sub basin in West Godavari district (services of NIH) | CS | 4000000 | 1 | 40
|  |  |  | C2.2.02 | O & M costs | Goods | 500000 | 1 | 5
|  |  |  | C2.2.03 | Hiring of vehicles | Goods | 1000000 | 1 | 10
[7 empty] | 0 | 0 | 0
|  | C2.3 | Studies for Rainwater harvesting and Artificial recharge |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | C2.4 | Reservoir sedimentation assessment |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
| C3 | Groundwater Management | Knwoledge Products and Dissemination |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | C3.1 | Knowledgebase Products |  |  |  | 0 | 0 | 0
0
|  | C3.2 | Groundwater exploration and aquifer mapping | C3.2.01 | Consultancy Services for Setup and Operation of DSS for Aquifer mappng in over-exploited GEC basin in Prakasam and Chittoor district | CS | 4000000 | 2 | 80
|  |  |  | C3.2.02 | O & M costs aquifer mapping | Goods | 500000 | 1 | 5
|  |  |  | C3.2.03 | Hiring of vehicles for aquifer mapping | Goods | 1000000 | 1 | 10
0
[5 empty] | Sub Component C Sub Total |  |  |  | 1190 | [33 empty] | 0
D | WR Institutions Capacity Enhancement |  | Institutions Capacity Enhancement
| D1 | Water Resources Knowledge Centers | Water Resources Knowledge Centers |  |  |  | 0 | 0 | 0
|  | D1.1 | National level Centers of Excellence |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | D1.2 | State/Regional Centers of Excellence |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
| D2 | Professional Development | Professional Development |  |  |  | 0 | 0 | 0
|  | D2.1 | Trainings |  |  |  | 0 | 0 | 0
|  |  |  | D2.1.01 | International Trainings | Goods | 500000 | 5 | 25
|  |  |  | D2.1.02 | National Training (e-gems) | Goods | 15000 | 30 | 4.5
|  |  |  | D2.1.03 | Dedicated training courses (ArcGIS, ERDAS, etc.,) | Goods | 40000 | 15 | 6
|  |  |  | D2.1.04 | In-House training in GW Estimation, HIS, Data validation and Processing, WQ etc | Goods | 5000 | 200 | 10 | 30 | 2016 Q4: 30 | 1.5 | 2
|  |  |  | C3.2.04 | Trainings in aqufer mapping | Goods | 200000 | 1 | 2
|  |  |  | C2.2.04 | Trainings in PDS-I studies | Goods | 200000 | 1 | 2
[7 empty] | 0 | 0 | 0
|  | D2.2 | Technical Assistance for development of training |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | D2.3 | Workshops |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | D2.4 | International Study Tours |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | D2.5 | Diploma's and Higher Degree Courses |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
| D3 | Project Management and Technical assistance | Project Management and Technical assistance |  |  |  | 0 | 0 | 0
|  | D3.1 | Establishment of CPMU |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
|  | D3.2 | Establishment of State PMU |  |  |  | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
| D4 | Operating cost | Operational Cost |  |  |  | 0 | 0 | 0
|  | D4.1 | Incremental Staff Cost |  |  |  | 0 | 0 | 0
|  |  |  | D4.1.02 | Field Officers (District Units) | NCS | 1800000 | 13 | 234 | 13 | 2016 Q2: 13; 2016 Q3: 13; 2016 Q4: 13; 2017 Q1: 13; 2017 Q2: 13; 2017 Q3: 13; 2017 Q4: 13 | 102.38 | 43.8771
|  |  |  | D4.1.03 | Assistant Chemists (WQ) | NCS | 1500000 | 15 | 225 | 11 | 2016 Q2: 11; 2016 Q3: 11; 2016 Q4: 11; 2017 Q1: 11; 2017 Q2: 11; 2017 Q3: 11; 2017 Q4: 11 | 12.03 | 5.1557
|  |  |  | D4.1.04 | Data entry operators (District Units) | NCS | 1000000 | 26 | 260 | 26 | 2016 Q2: 26; 2016 Q3: 26; 2016 Q4: 26; 2017 Q1: 26; 2017 Q2: 26; 2017 Q3: 26; 2017 Q4: 26 | 54.6 | 23.4
|  |  |  | D4.1.05 | Field Staff for HM Station at Vijayawada | NCS | 1000000 | 2 | 20 | 2 | 2016 Q2: 2; 2016 Q3: 2; 2016 Q4: 2; 2017 Q1: 2; 2017 Q2: 2; 2017 Q3: 2; 2017 Q4: 2 | 2.1 | 0.9
|  |  |  | D4.1.06 | Lab Assistants (WQ) | NCS | 1000000 | 12 | 120 | 8 | 2016 Q2: 8; 2016 Q3: 8; 2016 Q4: 8; 2017 Q1: 8; 2017 Q2: 8; 2017 Q3: 8; 2017 Q4: 8 | 8 | 3.4286
|  |  |  | D4.1.07 | Lab Attenders (WQ) | NCS | 800000 | 10 | 80 | 6 | 2016 Q2: 6; 2016 Q3: 6; 2016 Q4: 6; 2017 Q1: 6; 2017 Q2: 6; 2017 Q3: 6; 2017 Q4: 6 | 3.5 | 1.5
|  |  |  | D4.1.08 | Office subordinate (State Unit) | NCS | 800000 | 6 | 48 | 6 | 2016 Q2: 6; 2016 Q3: 6; 2016 Q4: 6; 2017 Q1: 6; 2017 Q2: 6; 2017 Q3: 6; 2017 Q4: 6 | 4 | 1.7143
|  |  |  | D4.1.09 | Office subordinate (District Unit) | NCS | 800000 | 13 | 104 | [34 empty] | 0
|  | D4.2 | Recurrent cost for operation of offices | [40 empty] | 0
|  |  |  | D4.2.01 | Hiring of Vehicles | Goods | 2500000 | 15 | 375 | 15 | 2016 Q2: 15; 2016 Q3: 15; 2016 Q4: 15; 2017 Q1: 15; 2017 Q2: 15; 2017 Q3: 15; 2017 Q4: 15 | 63 | 27
|  |  |  | D4.2.02 | Stationary and other office expanses (O & M) | Goods | 1000000 | 15 | 150 | 15 | 2016 Q2: 15; 2016 Q3: 15; 2016 Q4: 15; 2017 Q1: 15; 2017 Q2: 15; 2017 Q3: 15; 2017 Q4: 15 | 25.2 | 10.8
[7 empty] | 0 | 0 | 0
[5 empty] | Sub Component D Sub Total |  | 0 | 0 | 1665.5 | [33 empty] | 276.31 | 119.7757
[5 empty] | Grand Total |  |  | 8466 | 8003.25 | [33 empty] | 3007.72 | 1404.1857

## Hydromet Calculator (hidden)
Item | Unit Cost | Quantity | Amount
Agro-Meteorological Monitoring |  |  | 0
Automatic Weather Stations |  |  | 0
Automatic Rain Gauges |  |  | 0
Snow Pillows |  |  | 0
Rain and Snow Gauge |  |  | 0
Snow Depth Sensors |  |  | 0
VSAT Telemetry |  |  | 0
GSM Telemetry |  |  | 0
Soil Moisture Sensors - TDR |  |  | 0
0
0
0
Surface Water Monitoring |  |  | 0
AWLR (Shaft/bubbler/Radar etc) |  |  | 0
Civil Works |  |  | 0
VSAT Telemetry |  |  | 0
GSM Telemetry |  |  | 0
ADCP |  |  | 0
Velocity Radar |  |  | 0
0
0
0
0
0
Total |  |  | 0

## Guide to Filling Columns (hidden)
Componant ID | Sub Comp ID | Activity ID | Componant | Item Code | Items | Type | Unit Cost | Quantity | Total Cost
No Change required in this column | No Change required in this column | Add the ID of Activity, consistant with Componant and Sub-Componant ID | Add the name of Activity here in Blue color | Add the ID of Item, consistant with Componant, Sub-Componant and Activity ID | Add the Name of Item here in Black Color | Works for Civil Works Goods for Goods and Equipment CS for Consultancy Services NCS for Non Consultancy Services | Unit cost of each Item | No of Items | Total Cost (Col H * Col I)

## TimeLine
Componant ID | Sub Comp ID | Activity ID | Item Code | Main Activities |  |  | Timeline [show bar chart against 12 months shown below] | [11 empty] | Responsibility | Remarks | Cost in Rs. Lakhs
[5 empty] | Quantity in Nos. | Quantity Proposed to be completed | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  | QTR1 | QTR2 | QTR3 | QTR4
A | A1 | A1.3 | A1.3.01 | All monitoring wells to be geo-referencing using DGPS | 3500 | 1000 | [12 empty] | Nodal Officer, A.P.Ground Water Department |  |  |  | 13 | 13 | bar: Timeline [show bar chart against 12 months shown below] 7 to Timeline [show bar chart against 12 months shown below] 12
|  | A1.4 | A1.4.04 | GW Monitoring Equipment (WL Indicator, measuring tape, stop watch) | 40 | 40 | [15 empty] | 10
|  | A1.4 | A1.4.09 | Geological Survey Kits | 20 | 20 | [15 empty] | 1
|  | A1.5 | A1.5.02 | Medium/Deep piezometers (Bore well+protection works) | 600 | 600 | [15 empty] | 150 | 150 | 150 | bar: Timeline [show bar chart against 12 months shown below] 4 to Timeline [show bar chart against 12 months shown below] 12
|  | A1.5 | A1.5.03 | Deep piezometers (Tube well+protection works) | 150 | 150 | [15 empty] | 150 | 150 | 150 | bar: Timeline [show bar chart against 12 months shown below] 4 to Timeline [show bar chart against 12 months shown below] 12
|  | A1.7 | A1.7.02 | WQ Field Kit 1
|  |  | A1.7.03 | WQ Field Kit 2 | 5 | 4 | [15 empty] | 1.6
|  |  | A1.7.04 | WQ Field Kit 3 | [17 empty] | 0
|  |  | A1.7.05 | WQ Field Kit 4 | [17 empty] | 0
|  |  | A1.7.06 | Analytical Balance Digital | 5 | 4 | [15 empty] | 5
|  |  | A1.7.07 | Autoclave | 5 | 4 | [15 empty] | 6 | bar: Timeline [show bar chart against 12 months shown below] 4 to Timeline [show bar chart against 12 months shown below] 6
|  |  | A1.7.08 | Automatic Loop Stabilizer | 5 | 4 | [15 empty] | 6
|  |  | A1.7.09 | Bacteriological Incubator | 5 | 4 | [15 empty] | 6
|  |  | A1.7.10 | Common Balance | 5 | 4 | [15 empty] | 1.6
|  |  | A1.7.11 | DO Sampler | 5 | 4 | [15 empty] | 1.6
|  |  | A1.7.12 | Double Distillation Apparatus | 5 | 4 | [15 empty] | 33.4
|  |  | A1.7.13 | EC-TDS Analyzer | 5 | 4 | [15 empty] | 4.88
|  |  | A1.7.14 | Electronic Balance | 5 | 4 | [15 empty] | 4.88
|  |  | A1.7.15 | Flame Photometer | 5 | 4 | [15 empty] | 4.4
|  |  | A1.7.16 | Laminar Air Flow | 5 | 4 | [15 empty] | 15.2
|  |  | A1.7.17 | PH Analyzer | 5 | 4 | [15 empty] | 3
|  |  | A1.7.18 | Turbidimeter | 5 | 4 | [15 empty] | 2
|  |  | A1.7.19 | UV Spectro Photometer | 5 | 4 | [15 empty] | 36
|  |  | A1.7.20 | Water Quality Analyzer | 5 | 4 | [15 empty] | 6
|  |  | A1.7.22 | Water Softener | 5 | 4 | [15 empty] | 1.6
|  |  | A1.7.23 | Atomic absorption spectro photo meter | 5 | 4 | [15 empty] | 54
|  |  | A1.7.24 | Other Water Quality Lab Equipment | 5 | 4 | [15 empty] | 40
|  | A1.8 | A1.8.04 | GPS – Hand held | 40 | 40 | [16 empty] | 16 | bar: Timeline [show bar chart against 12 months shown below] 7 to Timeline [show bar chart against 12 months shown below] 9
| A3 | A3.3 | A3.3.01 | Consultancy for design, architecture etc. for SDC | 1 | 1 | [17 empty] | 10 | bar: Timeline [show bar chart against 12 months shown below] 10 to Timeline [show bar chart against 12 months shown below] 12
|  | A3.8 | A3.8.01 | Purchase of Computers with Software | 20 | 20 | [16 empty] | 15 | bar: Timeline [show bar chart against 12 months shown below] 7 to Timeline [show bar chart against 12 months shown below] 9
|  |  | A3.8.04 | Purchase of Laptops with Software | 20 | 20 | [16 empty] | 10 | bar: Timeline [show bar chart against 12 months shown below] 7 to Timeline [show bar chart against 12 months shown below] 9
|  |  | A3.8.14 | Procurement of Projectors | 15 | 15 | [16 empty] | 8 | bar: Timeline [show bar chart against 12 months shown below] 7 to Timeline [show bar chart against 12 months shown below] 9
|  |  | A3.8.15 | Printers (BW) | 20 | 10 | [16 empty] | 5 | bar: Timeline [show bar chart against 12 months shown below] 7 to Timeline [show bar chart against 12 months shown below] 9
|  |  | A3.8.16 | Printers (Color) | 20 | 10 | [16 empty] | 2.25 | bar: Timeline [show bar chart against 12 months shown below] 7 to Timeline [show bar chart against 12 months shown below] 9
|  |  | A3.8.18 | A4 Scanner | 20 | 15 | [16 empty] | 2.25 | bar: Timeline [show bar chart against 12 months shown below] 7 to Timeline [show bar chart against 12 months shown below] 9
|  |  | A3.8.20 | WiFi routers, hotspots, WiFi USB Dongles ( for each units) | 20 | 15 | [16 empty] | 3.75 | bar: Timeline [show bar chart against 12 months shown below] 7 to Timeline [show bar chart against 12 months shown below] 9
|  |  | A3.8.23 | Power Supply and online UPS for Data Centers (5KVA) Districts Data Centers | 15 | 15 | [16 empty] | 15 | bar: Timeline [show bar chart against 12 months shown below] 7 to Timeline [show bar chart against 12 months shown below] 9
|  |  | A3.8.25 | Photocopier (B/W) | 20 | 15 | [16 empty] | 15 | bar: Timeline [show bar chart against 12 months shown below] 7 to Timeline [show bar chart against 12 months shown below] 9
|  | A3.9 | A3.9.03 | Microsoft Office, Windows etc | 15 | 15 | [16 empty] | 6 | bar: Timeline [show bar chart against 12 months shown below] 7 to Timeline [show bar chart against 12 months shown below] 9
|  |  | A3.9.04 | Antivirus | 100 | 50 | [16 empty] | 0.5 | bar: Timeline [show bar chart against 12 months shown below] 7 to Timeline [show bar chart against 12 months shown below] 9
|  |  | A3.9.06 | Adobe PDF acrobat Standard | 20 | 15 | [16 empty] | 3 | bar: Timeline [show bar chart against 12 months shown below] 7 to Timeline [show bar chart against 12 months shown below] 9
D | D2 | D2.1 | D2.1.04 | In-House training in GW Estimation, HIS, Data validation and Processing, WQ etc | 200 | 30 | [16 empty] | 1.5 | bar: Timeline [show bar chart against 12 months shown below] 10 to Timeline [show bar chart against 12 months shown below] 12
| D4 | D4.1 | D4.1.02 | Field Officers (District Units) | 13 | 13 | [15 empty] | 7.31 | 7.31 | 7.31 | bar: Timeline [show bar chart against 12 months shown below] 4 to Timeline [show bar chart against 12 months shown below] 12
|  |  | D4.1.04 | Assistant Chemists (WQ) | 15 | 11 | [15 empty] | 0.833 | 0.833 | 0.833 | bar: Timeline [show bar chart against 12 months shown below] 4 to Timeline [show bar chart against 12 months shown below] 12
|  |  | D4.1.05 | Data entry operators (District Units) | 26 | 26 | [15 empty] | 7.6 | 7.6 | 7.6 | bar: Timeline [show bar chart against 12 months shown below] 4 to Timeline [show bar chart against 12 months shown below] 12
|  |  | D4.1.06 | Field Staff for HM Station at Vijayawada | 2 | 2 | [15 empty] | 0.33 | 0.33 | 0.33 | bar: Timeline [show bar chart against 12 months shown below] 4 to Timeline [show bar chart against 12 months shown below] 12
|  |  | D4.1.07 | Lab Assistants (WQ) | 12 | 8 | [15 empty] | 0.66 | 0.66 | 0.66 | bar: Timeline [show bar chart against 12 months shown below] 4 to Timeline [show bar chart against 12 months shown below] 12
|  |  | D4.1.09 | Office subordinate (State Unit) | 6 | 6 | [15 empty] | 1 | 1 | 1 | bar: Timeline [show bar chart against 12 months shown below] 4 to Timeline [show bar chart against 12 months shown below] 12
[22 empty] | 561.893 | 433.983 | 340.733 | 1336.609

## PP (hidden)
Sl. No. | Contract Package Number | Contract Description | Unit | Qty/ Nos. | Estimated Price in Rs. lakhs | Procurement Method | Prior Review (Yes / No) | Planned Dates for |  |  |  | Remarks
[8 empty] | Finalizing Bid Document | Inviting Bids | Bid Opening | Contract Signing
1 |  | All monitoring wells to be geo-referencing using DGPS | Nos | 3500 | 26 | Consultancy | Yes | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | This work will be taken up under consultancy services
2 |  | GW Monitoring Equipment (WL Indicator, measuring tape, stop watch) & Geological Survey Kit | Nos | 40 + 20 | 11 | NSP Goods | Yes | 2016-06-01 | 2016-07-01 | 2016-07-01 | 2016-08-01 | First Document
3 |  | Medium/Deep piezometers (Bore well+protection works) | Nos | 600 | 450 | NSP Works | Yes | 2016-03-01 | 2016-04-01 | 2016-04-01 | 2016-05-01 | This work will be carried out by District Units under shopping procedures as the breakup for each district will be less than Rs.50.00 lakhs
4 |  | Deep piezometers (Tube well+protection works) | Nos | 150 | 450 | NCB Works | Yes (First Document) | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | This work will be carried out by District Units under NCB works.
5 |  | WQ equipment for 4 WQ Labs | Nos |  | 329 | NCB Goods | Yes (First Document) | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | This work will be taken up Director, APSGWD