## Goods
Country/Organisation:
Project/Programme: | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Loan #: |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Description* | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$'000 | Date Contract Award | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk | 1.5-3 wks
[5 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
List of Contracts
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  |  | 0 |  |  |  | Plan | [7 empty] | Plan | 0
|  |  | 0 |  |  |  | Actual | [7 empty] | Actual | 0
Fill gray cells only!

## Works
Country/Organisation:
Project/Programme: | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Loan #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Estimated Amount in US $ | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ '000 | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | Plan |  | 1 wk | 1.5-3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [5 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [5 empty] | 0
Fill gray cells only!

## Consultants 2
Country/Organisation:
Project/Programme: |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for EOI (where required)
Loan #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization |  |  |  | Contract Implementation
Description* | Selection Method | Lumpsum or Time-Based | Estimated Amount in US$ '000 | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  | 1 wk | 1 - 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
List of Contracts
Procurement Advisory Services | QCBS | TB | 2750 | Prior | Plan | 15 sep 04 | 27 sep 04 |  | 15 sept 04 | 30 sept 04 | 08 oct 04 | Plan | 11 oct 04 | 04 dec 04 | 27 dec 04 | 06 jan 05 | 18 jan 05 | 01 feb 05 | 14 feb 05 | Plan | 21 feb 05 | 01 mar 05 |  | 07 mar 05 | 21 mar 05 | Plan | 04 apr 05
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Total Cost |  |  | 2750 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  | Actual |  |  |  | 0
Fill gray cells only!