GOVERNMENT OF..........

PROJECT..........

BID [TENDER] NO..........

**NATIONAL COMPETITIVE BIDDING**

**(Two-Envelope Bidding Process with e-Procurement)**

**(*FOR ITEM RATE/ADMEASUREMENT CONTRACTS IN CIVIL WORKS)***

***(Upto US$ 20 Million)***

NAME OF WORK :

PERIOD OF SALE OF : FROM

BIDDING DOCUMENT TO

TIME AND DATE OF : DATE ———— TIME ———— HOURS

PRE-BID CONFERENCE

LAST DATE AND TIME FOR : DATE ———— TIME ———— HOURS

RECEIPT OF BIDS

**\*** TIME AND DATE OF OPENING : DATE ———— TIME ———— HOURS OF BIDS – Technical Part[[1]](#footnote-1)

PLACE OF OPENING OF BIDS :

:

:

OFFICER INVITING BIDS :

**\* *Should be 2 days after the deadline for submission of bids to allow submission of original documents like bid security, demand draft, affidavit etc****.*

**April 2017**

# INVITATION FOR BID

(IFB)

GOVERNMENT OF ……………..

**………………….………PROJECT**

**INVITATIONS FOR BIDS (IFB)**

**E-Procurement Notice**

**(Two Envelope Bidding Process with e-Procurement)**

NATIONAL COMPETITIVE BIDDING

**Date:**

**Bid No.:**

1. The Government of India has received/applied for/intends to apply for financing from the World Bank towards the cost of ……………..Project and intends to apply a part of the funds to cover eligible payments under the contracts[[2]](#footnote-2) for construction of works as detailed below.
2. Bidding will be conducted through National Competitive Bidding procedures agreed with the World Bank. Bidding is open to all eligible bidders as defined in the World Bank’s Guidelines: [Procurement of Goods, Works and Non-Consulting Services under IBRD Loans and IDA Credits & Grants by World Bank Borrowers, January 2011 *[modify if required, the date/month of applicable Guidelines edition as per legal agreement]*.](http://www.worldbank.org/html/opr/procure/guidelin.html)
3. Bidders from India should, however, be registered with the Government of ……………....or other State Governments/Government of India, or State/Central Government Undertakings. Bidders from India, who are not registered as above, on the date of bidding, can also participate provided they get themselves registered by the time of contract signing, if they become successful bidders. **Bidders are advised to note the clauses on eligibility (Section I Clause 4) and minimum qualification criteria (Section III – Evaluation and Qualification Criteria), to qualify for the award of the contract.** In addition, please refer to paragraphs 1.6 and 1.7 of the World Bank’s Guidelines setting forth the World Bank’s policy on conflict of interest.
4. The …………………………(***Implementing Agency***) invites online bids for the construction of works detailed below in the table. The bidders may submit bids for any or all of the works indicated therein.
5. Bidding documents are available online on ………….. *(website)* from……to…... *(dates)* for a non-refundable fee as indicated in the table, in the form of Demand Draft (DD) on any Scheduled/Nationalized bank payable at…………in favour of………………… (Demand draft is to be submitted subsequently as per the procedure described in paragraph 9 below). Bidders will be required to register on the website, which is free of cost. The bidders would be responsible for ensuring that any addenda available on the website is also downloaded and incorporated.
6. For submission of the bid, the bidder is required to have Digital Signature Certificate (DSC) from one of the Certifying Authorities authorised by Government of India for issuing DSC. Aspiring bidders who have not obtained the user ID and password for participating in e-procurement in this Project, may obtain the same from the website: ……………... A non-refundable fee of Rs……….. (inclusive of tax) is required to be paid (to be submitted along with other documents listed in paragraph 9 below) before the opening of the bid i.e. before <date>. The mode of payment shall be in the form of DD drawn in favour of …………………., payable at ………, from any scheduled Bank.

1. All Bids must be accompanied by a bid security of the amount specified for the work in the table below, drawn in favour of …………. Bid security will have to be in any one of the forms as specified in the bidding document and shall have to be valid for 45 days beyond the validity of the bid. Procedure for submission of bid security is described in Para 9.
2. Bids must be submitted online on ………….. *(website)* on or before ……… hours on…….. *(date)* and the ‘Technical Part’ of the bids will be opened online on ………… *(date)* at …… hours. The “Financial Part” shall remain unopened in the e-procurement system until the second public Bid opening for the financial part. Any bid or modifications to bid (including discount) received outside e-procurement system will not be considered. If the office happens to be closed on the date of opening of the bids as specified, the bids will be opened on the next working day at the same time. The electronic bidding system would not allow any late submission of bids.
3. The bidders are required to submit (a) original demand drafts towards the cost of bid document and registration on e-procurement website (if not previously registered); (b) original bid security in approved form; and (c) original affidavit regarding correctness of information furnished with bid document with *……………………(insert name and complete address)* before the opening of the technical part of the Bid i.e. before <date>, either by registered post/speed post/courier or by hand, failing which the bids will be declared non-responsive and will not be opened.
4. A pre-bid meeting will be held on………………….. at ………….hrs. at the office of …………………….to clarify the issues and to answer questions on any matter that may be raised at that stage as stated in ITB Clause 7.4 of ‘Instructions to Bidders’ of the bidding document. Bidders are advised to download the bidding document prior to the pre-bid meeting in order for bidders to have a good understanding of the scope of work under this contract for discussion and clarification at the pre-bid meeting.
5. Other details can be seen in the bidding documents. The Employer shall not be held liable for any delays due to system failure beyond its control. Even though the system will attempt to notify the bidders of any bid updates, the Employer shall not be liable for any information not received by the bidder. It is the bidders’ responsibility to verify the website for the latest information related to this bid.

TABLE

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Package No | Name of Work | Bid Security \*  (Rs.) | Cost of Document  (Rs.) | Period of Completion |
| 1 | 2 | 3 | 4 | 5 |
|  |  |  |  |  |

Seal of office

Address

***Note \* - The values should be rounded off to the nearest ten thousands of rupees.***

***The IFB should be identical to that which appeared in the press/ website.***

PART 1 – Bidding Procedures

**Section I. Instructions to Bidders**

*This Section of the Bidding Documents should provide the information necessary for bidders to prepare responsive bids, in accordance with the requirements of the Employer. It should also give information on bid submission, opening and evaluation, and on the award of Contract.*

*Matters governing the performance of the Contractor, payments under the Contract, or matters affecting the risks, rights, and obligations of the parties under the Contract are not normally included in this Section, but rather under Section VIII, General Conditions of Contract(GCC), and/or Section IX, Particular Conditions of Contract (PCC). If duplication of a subject is inevitable in the different sections of the documents, care must be exercised to avoid contradictions between clauses dealing with the same matter.*

*These Instructions to Bidders shall not be part of the Contract Agreement and shall cease to have effect once the Contract is signed.*

Section 1 - Instructions to Bidders

**Table of Clauses**

[A. General 10](#_Toc480542896)

[1. Scope of Bid 10](#_Toc480542897)

[2. Source of Funds 10](#_Toc480542898)

[3. Corrupt and Fraudulent Practices 11](#_Toc480542899)

[4. Eligible Bidders 11](#_Toc480542900)

[5. Eligible Materials, Equipment and Services 14](#_Toc480542901)

[B. Contents of Bidding Document 14](#_Toc480542902)

[6. Sections of Bidding Document 14](#_Toc480542903)

[7. Clarification of Bidding Document, Site Visit, Pre-Bid Meeting 15](#_Toc480542904)

[8. Amendment of Bidding Document 16](#_Toc480542905)

[C. Preparation of Bids 17](#_Toc480542906)

[9. Cost of Bidding 17](#_Toc480542907)

[10. Language of Bid 17](#_Toc480542908)

[11. Documents Comprising the Bid 17](#_Toc480542909)

[12. Process of Bid Submission 18](#_Toc480542910)

[13. Alternative Bids 19](#_Toc480542911)

[14. Bid Prices and Discounts 19](#_Toc480542912)

[15. Currencies of Bid and Payment 21](#_Toc480542913)

[16. Documents Comprising the Technical Proposal 21](#_Toc480542914)

[17. Documents Establishing the Qualifications of the Bidder 21](#_Toc480542915)

[18. Period of Validity of Bids 21](#_Toc480542916)

[19. Bid Security 22](#_Toc480542917)

[20. Format and Signing of Bid 23](#_Toc480542918)

[D. Online Submission and Opening of Bids 24](#_Toc480542919)

[21. Preparation of Bids 24](#_Toc480542920)

[22. Deadline for Submission of Bids 25](#_Toc480542921)

[23. Late Bids 25](#_Toc480542922)

[24. Withdrawal, Substitution, and Modification of Bids 25](#_Toc480542923)

[25. Public Opening of Technical Parts of Bids 25](#_Toc480542924)

[F. Evaluation of Bids – General Provisions 26](#_Toc480542925)

[26. Confidentiality 26](#_Toc480542926)

[27. Clarification of Bids 26](#_Toc480542927)

[28. Deviations, Reservations, and Omissions 27](#_Toc480542928)

[29. Nonconformities, Errors, and Omissions 27](#_Toc480542929)

[30. Evaluation of Technical Parts 27](#_Toc480542930)

[31. Determination of Responsiveness 28](#_Toc480542931)

[32. Qualification of the Bidder 28](#_Toc480542932)

[33. Subcontractors 29](#_Toc480542933)

[34. Public Opening of Financial Parts 29](#_Toc480542934)

[35. Evaluation of Financial Parts 30](#_Toc480542935)

[36. Correction of Arithmetical Errors 31](#_Toc480542936)

[37. Conversion to Single Currency 31](#_Toc480542937)

[38. Margin of Preference 31](#_Toc480542938)

[39. Comparison of Financial Parts 31](#_Toc480542939)

[40. Unbalanced or Front Loaded Bids 31](#_Toc480542940)

[41. Employer’s Right to Accept Any Bid, and to Reject Any or All Bids 31](#_Toc480542941)

[J. Award of Contract 32](#_Toc480542942)

[42. Award Criteria 32](#_Toc480542943)

[43. Notification of Award 32](#_Toc480542944)

[44. Signing of Contract, Publication of award and Recourse to unsuccessful Bidders 32](#_Toc480542945)

[45. Performance Security 33](#_Toc480542946)

[46. Adjudicator or Dispute Review Expert 33](#_Toc480542947)

Section I - Instructions to Bidders

|  |  |
| --- | --- |
| 1. General | |
| 1. Scope of Bid | 1.1 The Employer, as **indicated in the BDS**, issues this Bidding Document for the procurement of the Works as specified in Section VII (Work’s Requirements) & Invitation for Bids (IFB). The name, identification, and number of contracts of this bidding are **specified in the BDS**. |
|  | * 1. Throughout this Bidding Document:   (a) the term “in writing” means communicated in written form and delivered against receipt;  (b) except where the context requires otherwise, words indicating the singular also include the plural and words indicating the plural also include the singular; and  (c) “day” means calendar day. |
| 1. Source of Funds | 2.1 The Government of India or the Recipient (hereinafter called “Borrower”) **specified in the BDS** has received/applied for financing (hereinafter called “funds”) from the International Bank for Reconstruction and Development or the International Development Association (hereinafter called “the Bank”) in an amount **specified in the BDS**, towards the cost of the project **specified in the BDS**. The Borrower intends to apply a portion of the funds to eligible payments under the contract(s) for which this Bidding Document is issued.  2.2 Payment by the Bank will be made only at the request of the Borrower and upon approval by the Bank, and will be subject, in all respects, to the terms and conditions of the Loan (or other financing) Agreement. The Loan (or other financing) Agreement prohibits a withdrawal from the Loan (or other financing) account for the purpose of any payment to persons or entities, or for any import of goods, if such payment or import, is prohibited by a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations. No party other than the Borrower shall derive any rights from the Loan (or other financing) Agreement or have any claim to the proceeds of the Loan (or other financing). |
| 1. Corrupt and Fraudulent Practices | 3.1 The Bank requires compliance with its policy in regard to corrupt and fraudulent practices as set forth in Section VI.  3.2 In further pursuance of this policy, Bidders shall permit and shall cause its agents (whether declared or not), sub-contractors, sub-consultants, service providers, or suppliers and any personnel thereof, to permit the Bank to inspect all accounts, records and other documents relating to any prequalification process, bid submission, and contract performance (in the case of award), and to have them audited by auditors appointed by the Bank. |
| 1. Eligible Bidders | * + 1. A Bidder may be a firm that is a private entity, or a government-owned entity—subject to ITB 4.5—or any combination of such entities in the form of a joint venture (JV), under an existing agreement, or with the intent to constitute a legally-enforceable joint venture, unless otherwise **specified in the BDS**.     2. Bids submitted by a joint venture of two or more firms as members when permitted as per BDS ITB Clause 4.1.1 shall comply with the following requirements:   [a] the bid shall include all the information listed in Bidders Qualification Forms for all the Members. The maximum number of members in the Joint Venture shall be as **specified in the** **BDS;**  [b] the bid and, in case of a successful bid, the Agreement, shall be signed so as to be legally binding on all members;  [c] one of the members shall be nominated as being in charge, and this authorization shall be evidenced by submitting a power of attorney signed by legally authorized signatories of all the members;  [d] the member in charge shall be authorized to incur liabilities and receive instructions for and on behalf of any and all members of the joint venture and the entire execution of the contract, including payment, shall be done exclusively with the member in charge;  [e] all members of the joint venture shall be liable jointly and severally for the execution of the contract in accordance with the contract terms, and a statement to this effect shall be included in the authorization mentioned under (c) above, as well as in the bid and in the Agreement [*in case of a successful bid*];  [f] The joint venture agreement should indicate precisely the role of all members of JV in respect of planning, design, construction equipment, key personnel, work execution, and financing of the project. All members of JV should have active participation in the execution during the currency of the contract. This should not be varied/modified subsequently without prior approval of the Employer;  [g] The joint venture agreement should be registered in place **specified in** **BDS** so as to be legally valid and binding on members; and  [h] a copy of the Joint Venture Agreement entered into by the members shall be submitted with the bid. Alternatively, a Letter of Intent to execute a Joint Venture Agreement in the event of a successful bid shall be signed by all members and submitted with the bid, together with a copy of the proposed Agreement. |
|  | A Bidder shall not have a conflict of interest. All Bidders found to have a conflict of interest shall be disqualified. A Bidder may be considered to have a conflict of interest for the purpose of this bidding process, if the Bidder:   * + 1. directly or indirectly controls, is controlled by or is under common control with another Bidder; or     2. receives or has received any direct or indirect subsidy from another Bidder; or     3. has the same legal representative as another Bidder; or     4. has a relationship with another Bidder, directly or through common third parties, that puts it in a position to influence the bid of another Bidder, or influence the decisions of the Employer regarding this bidding process; or     5. participates in more than one bid in this bidding process. Participation by a Bidder in more than one Bid will result in the disqualification of all Bids in which such Bidder is involved. However, this does not limit the inclusion of the same subcontractor in more than one bid; or     6. any of its affiliates participated as a consultant in the preparation of the design or technical specifications of the works that are the subject of the bid; or     7. any of its affiliates has been hired (or is proposed to be hired) by the Employer or Borrower as Project Manager (Engineer) for the Contract implementation; or     8. would be providing goods, works, or non-consulting services resulting from or directly related to consulting services for the preparation or implementation of the project specified in the BDS ITB 2.1 that it provided or were provided by any affiliate that directly or indirectly controls, is controlled by, or is under common control with that firm; or     9. has a close business or family relationship with a professional staff of the Borrower (or of the project implementing agency, or of a recipient of a part of the loan) who: (i) are directly or indirectly involved in the preparation of the bidding documents or specifications of the contract, and/or the bid evaluation process of such contract; or (ii) would be involved in the implementation or supervision of such contract unless the conflict stemming from such relationship has been resolved in a manner acceptable to the Bank throughout the procurement process and execution of the contract. |
|  | 4.3 A Bidder may have the nationality of any country, subject to the restrictions pursuant to ITB 4.7. A Bidder shall be deemed to have the nationality of a country if the Bidder is constituted, incorporated or registered in and operates in conformity with the provisions of the laws of that country, as evidenced by its articles of incorporation (or equivalent documents of constitution or association) and its registration documents, as the case may be. This criterion also shall apply to the determination of the nationality of proposed sub-contractors or sub-consultants for any part of the Contract including related Services. |
|  | 4.4 A Bidder that has been sanctioned by the Bank in accordance with the above ITB 3.1, including in accordance with the Bank’s Guidelines on Preventing and Combating Corruption in Projects Financed by IBRD Loans and IDA Credits and Grants (“Anti-Corruption Guidelines”), shall be ineligible to be prequalified for, bid for, or be awarded a Bank-financed contract or benefit from a Bank-financed contract, financially or otherwise, during such period of time as the Bank shall have determined. The list of debarred firms and individuals is available at the electronic address **specified in the BDS**. |
|  | 4.5 Bidders that are Government-owned enterprises or institutions in the Employer’s Country may participate only if they can establish that they (i) are legally and financially autonomous (ii) operate under commercial law, and (iii) are not dependent agencies of the Employer. To be eligible, a government-owned enterprise or institution shall establish to the Bank’s satisfaction, through all relevant documents, including its Charter and other information the Bank may request, that it: (i) is a legal entity separate from the government (ii) does not currently receive substantial subsidies or budget support; (iii) operates like any commercial enterprise, and, inter alia, is not obliged to pass on its surplus to the government, can acquire rights and liabilities, borrow funds and be liable for repayment of its debts, and can be declared bankrupt; and (iv) is not bidding for a contract to be awarded by the department or agency of the government which under their applicable laws or regulations is the reporting or supervisory authority of the enterprise or has the ability to exercise influence or control over the enterprise or institution. |
|  | 4.6 Not used. |
|  | 4.7 Firms and individuals may be ineligible if so indicated in Section V and (a) as a matter of law or official regulations, the Borrower’s country prohibits commercial relations with that country, provided that the Bank is satisfied that such exclusion does not preclude effective competition for the supply of goods or the contracting of works or services required; or (b) by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Borrower’s country prohibits any import of goods or contracting of works or services from that country, or any payments to any country, person, or entity in that country. |
|  | 4.8 Bidder shall provide such evidence of eligibility satisfactory to the Employer, as the Employer shall reasonably request  4.9 Not used |
| 1. Eligible Materials, Equipment and Services | 5.1 The materials, equipment and services to be supplied under the Contract and financed by the Bank may have their origin in any country subject to the restrictions specified in Section V, Eligible Countries, and all expenditures under the Contract will not contravene such restrictions. At the Employer’s request, Bidders may be required to provide evidence of the origin of materials, equipment and services. |
| 1. Contents of Bidding Document | |
| 1. Sections of Bidding Document | 6.1 The Bidding Document consist of Parts 1, 2*,* and 3*,* which include all the Sections indicated below, and should be read in conjunction with any Addenda issued in accordance with ITB 8.  **PART 1 Bidding Procedures**  Section I - Instructions to Bidders (ITB)  Section II - Bid Data Sheet (BDS)  Section III - Evaluation and Qualification Criteria  Section IV - Bidding Forms  Section V - Eligible Countries  Section VI - Bank Policy-Corrupt and Fraudulent Practices  **PART 2 Work’s Requirements**  Section VII - Works Requirements  **PART 3 Conditions of Contract and Contract Forms**  Section VIII - General Conditions of Contract (GCC)  Section IX - Particular Conditions of Contract (PCC)  Section X - Contract Forms |
|  | * 1. The Invitation for Bids issued by the Employer is not part of the Bidding Document. |
|  | 6.3 Unless obtained directly from the Employer, the Employer is not responsible for the completeness of the Bidding Documents, responses to requests for clarification, the minutes of the pre-Bid meeting (if any), or Addenda to the Bidding Documents in accordance with ITB 8. In case of any contradiction, documents obtained directly from the Employer shall prevail. |
|  | 6.4 The Bidder is expected to examine all instructions, forms, terms, and specifications in the Bidding Documents and to furnish with its bid all information and documentation as required by the Bidding Documents. |
| 1. Clarification of Bidding Document, Site Visit, Pre-Bid Meeting | 7.1 The electronic bidding system **specified in the BDS** provides for online clarifications. A prospective Bidder requiring any clarification on the Bidding Document may notify the Employer online or raise his inquiries during the pre-bid meeting if provided for in accordance with ITB 7.4. Clarifications requested through any other mode shall not be considered by the Employer. The Employer will respond to any request for clarification, provided that such request is received prior to the deadline for submission of bids, within a period **specified in the BDS**. Description of clarification sought and the response of the Employer shall be uploaded for information of all Bidders without identifying the source of request for clarification. Should the clarification result in changes to the essential elements of the Bidding Documents, the Employer shall amend the Bidding Documents following the procedure under ITB 8 and ITB 22.2. |
|  | * 1. The Bidder is advised to visit and examine the Site of Works and its surroundings and obtain for itself, on its own risk and responsibility, all information that may be necessary for preparing the bid and entering into a contract for construction of the Works. The costs of visiting the Site shall be at the Bidder’s own expense. |
|  | 7.3 The Bidder and any of its personnel or agents will be granted permission by the Employer to enter upon its premises and lands for the purpose of such visit, but only upon the express condition that the Bidder, its personnel, and agents will release and indemnify the Employer and its personnel and agents from and against all liability in respect thereof, and will be responsible for death or personal injury, loss of or damage to property, and any other loss, damage, costs, and expenses incurred as a result of the inspection. |
|  | 7.4 If so **specified in the BDS**, the Bidder’s designated representative is invited to attend a pre-bid meeting. The purpose of the meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage. |
|  | 7.5 The Bidder is requested, to submit any questions only through the e-procurement portal, not later than one week before the meeting. Clarifications requested through any other mode shall not be considered by the Employer. |
|  | 7.6 Minutes of the pre-bid meeting, including the text of the questions raised, without identifying the source, and the responses given, together with any responses prepared after the meeting, will be uploaded online on e-procurement system. Any modification to the Bidding Documents that may become necessary as a result of the pre-bid meeting shall be made by the Employer exclusively through the issue of an addendum pursuant to ITB 8 and not through the minutes of the pre-bid meeting. It is the bidder’s responsibility to check on the e- procurement system, for any addendum/ amendment/ corrigendum to the bidding documents. |
|  | 7.7 Nonattendance at the pre-bid meeting will not be a cause for disqualification of a Bidder. |
| 1. Amendment of Bidding Document | 8.1 At any time prior to the deadline for submission of bids, the Employer may amend the Bidding Documents by issuing addenda. The addendum will appear on the e-procurement system under “Latest Corrigendum” and email notification is also automatically sent to those bidders who have started working on the tender, or as **otherwise specified in BDS**. |
|  | * 1. Any addendum thus issued shall be part of the Bidding Document and shall be deemed to have been communicated to all bidders. |
|  | 8.3 To give prospective Bidders reasonable time in which to take an addendum into account in preparing their bids, the Employer may, at its discretion, extend the deadline for the submission of bids, pursuant to ITB 22.2 |
| 1. Preparation of Bids | |
| 1. Cost of Bidding | 9.1 The Bidder shall bear all costs associated with the preparation and submission of its Bid, and the Employer shall in no case be responsible or liable for those costs, regardless of the conduct or outcome of the bidding process. |
| 1. Language of Bid | 10.1 The Bid, as well as all correspondence and documents relating to the bid exchanged by the Bidder and the Employer, shall be written in English. |
| 1. Documents Comprising the Bid | 11.1 The Bid shall comprise two Parts, namely the Technical Part and the Financial Part. These two Parts shall be submitted simultaneously.  11.2 The Technical Part shall contain the following:   1. Letter of Bid – Technical Part; 2. completed Schedules, in accordance with ITB 12, as **specified in BDS**; 3. Bid Security, in accordance with ITB 19; 4. alternative bids – technical part, if permissible, in accordance with ITB 13; 5. written confirmation authorizing the signatory of the Bid to commit the Bidder, in accordance with ITB 20.2; 6. documentary evidence in accordance with ITB 17 establishing the Bidder’s qualifications to perform the contract, if its Bid is accepted; 7. Technical Proposal in accordance with ITB 16; 8. Construction methodology proposed as detailed in Para 1.1 of Section III Evaluation Criteria; and 9. bids submitted by a JV (where permitted) shall include a copy of the Joint Venture Agreement entered into by all members. Alternatively, a letter of intent to execute a Joint Venture Agreement in the event of a successful bid shall be signed by all members and submitted with the bid, together with a copy of the proposed Agreement. 10. Any other document **required in the BDS**.   11.3 The **Financial Part** shall contain the following:   * + 1. **Letter of Bid – Financial Part:** prepared in accordance with ITB 12 and ITB 14;     2. **Bill of Quantities** completed online in accordance with ITB 12 and ITB 14**;**     3. **Alternative Bid - Financial Part:** if permissible in accordance with ITB 13; and     4. any other document **required in the BDS.**   11.4 The Technical Part shall not include any information related to the Bid price. Where material financial information related to the Bid price is contained in the Technical Part the Bid shall be declared non-responsive.  11.5 The Bidder shall furnish in the Letter of Bid – Financial Part information on commissions and gratuities, if any, paid or to be paid to agents or any other party relating to this Bid. |
| 1. Process of Bid Submission | 12.1 The Letter of Bid – Technical Part, Letter of Bid – Financial Part, Schedules, and Bill of Quantities, shall be prepared using the relevant forms in Section IV (Bidding Forms). The forms must be completed without any alterations to the text, and no substitutes shall be accepted. All blank spaces shall be filled in with the information requested.   * 1. Entire Bid including the Letter of Bid and filled-up Bill of Quantity shall be submitted online on e-procurement system specified in ITB 7.1. Details and process of online submission of the tender and relevant documents are given in the website mentioned above. Scanned copies of documents listed in ITB clauses 11 and 12.3 should also be uploaded on this website.   12.3 **Submission of Original Documents:** The bidders are required to separately submit (i) original demand drafts towards the cost of bid document and registration on e-procurement website (if not previously registered) (as per IFB); and (ii) original bid security in approved form; and (iii) original affidavit regarding correctness of information furnished with bid document, with the office **specified in the BDS**, before the opening of the technical part of the Bid, either by registered/speed post/courier or by hand, failing which the bids will be declared non-responsive and will not be opened. Hard copy of rest of the bid or any other document are not to be submitted. |
| 1. Alternative Bids | 13.1 Bidders shall submit offers that comply with the requirements of the bidding documents, including the basic technical design as indicated in the drawing and specifications. Alternatives will not be considered. |
| 1. Bid Prices and Discounts | 14.1 The prices and discounts (including any price reduction) quoted by the Bidder in the Letter of Bid - Financial Part, and in the Schedules shall conform to the requirements specified below. |
|  | * 1. The Bidder shall submit a bid for the whole of the works described in ITB 1.1 by filling in prices for all items of the Works (both in figures and words), as identified in Section IV, Bidding Forms alongwith the total bid price (both in figures and words). The Bidder shall fill in rates and prices for all items of the Works described in the Bill of Quantities. **Items against which no rate or price is entered by the Bidder will not be paid for by the Employer when executed and shall be deemed covered by the rates for other items and prices in the Bill of Quantities.** Corrections if any in the bid can be carried out by editing the information before electronic submission on e-procurement portal. |
|  | 14.3 The price to be quoted in the Letter of Bid - Financial Part in accordance with ITB 12.1, shall be the total price of the Bid, excluding any discounts offered. |
|  | 14.4 Unconditional discounts, if any, and the methodology for their application shall be quoted in the Letter of Bid - Financial Part, in accordance with ITB 12.1. |
|  | 14.5 Unless otherwise **specified in the BDS** and the Conditions of Contract, the rates and prices quoted by the Bidder shall be fixed  14.6 If so indicated in ITB 1.1, bids are invited for individual lots (contracts) or for any combination of lots/contracts (packages). Bidders wishing to offer any price reduction for the award of more than one Contract shall specify in their bid the price reductions applicable to each package, or alternatively, to individual Contracts within the package. Price reductions or discounts shall be submitted in accordance with ITB 14.4, provided the bids for all lots/contracts are submitted and opened at the same time. |
|  | 14.7 All duties, taxes, and other levies payable by the Contractor under the Contract, or for any other cause, as applicable on the deadline for submission of Bids, shall be included in the rates and prices and the total bid price submitted by the Bidder. |
|  | 14.8 Bidders may like to ascertain availability of excise/custom duty exemption benefits available in India to the contracts financed under World Bank loan/credits. They are solely responsible for obtaining such benefits which they have considered in their bid and in case of failure to receive such benefits for reasons whatsoever, the Employer will not compensate the bidder (contractor). The bidder shall furnish alongwith his bid a declaration to this effect in the Declaration Format provided in Section IV of the bidding documents.  Where the bidder has quoted taking into account such benefits, it must give all information required for issue of certificates in terms of the Government of India Central Excise Notification and Customs Notification as per form stipulated in Section IV. In case the bidder has not provided the required information or has indicated to be furnished later on in the Declaration Format, the same shall be construed that the goods/construction equipment for which certificate is required is Nil.  To the extent the Employer determines the quantity indicated therein are reasonable keeping in view the quantities in bill of quantities, construction program and methodology, the certificates will be issued within 60 days of signing of the contract and no subsequent changes will be permitted. In case of materials pertaining to Variation items and quantities the certificate shall be issued only on request from the contractor when in need and duly certified by the Project Manager.  No certificate will be issued for items where no quantity/capacity of equipment is indicated in the statement.  If the bidder has considered the customs/excise duty exemption for materials/construction equipment to be bought for the work, the bidder shall confirm and certify that the Employer will not be required to undertake any responsibilities of the Government of India Scheme or the said exemptions being available during the contract execution, except issuing the required certificate. The bids which do not conform to the above provisions or any condition by the bidder which makes the bid subject to availability of customs/excise duty exemption for materials/construction equipment or compensation on withdrawal of any variations to the said exemptions will be treated as non-responsive and rejected.  Any delay in procurement of the construction equipment/machinery/goods as a result of the above shall not be a cause for granting any extension of time. |
| 1. Currencies of Bid and Payment | 15.1 The unit rates and prices shall be quoted by the Bidder and shall be paid for, entirely in Indian Rupees. |
| 1. Documents Comprising the Technical Proposal | 16.1 The Bidder shall furnish a Technical Proposal in the Technical Part of the Bid, including a statement of work methods, equipment, personnel, schedule and any other information as per details stipulated in Section IV (Bidding Forms), in sufficient detail to demonstrate the adequacy of the Bidders’ proposal to meet the work requirements and the completion time. |
| 1. Documents Establishing the Qualifications of the Bidder | 17.1 To establish Bidder’s eligibility in accordance with ITB 4, Bidders shall complete the Letter of Bid – Technical Part, included in Section IV, Bidding Forms.    17.2 To establish its qualifications to perform the Contract in accordance with Section III (Evaluation and Qualification Criteria) the Bidder shall provide the complete information as requested in the corresponding information sheets included in Section IV(Bidding Forms). |
| 1. Period of Validity of Bids | 18.1 Bids shall remain valid for 90 days or for a period **specified in the BDS** after the bid submission deadline date prescribed by the Employer in accordance with ITB 22.1. A bid valid for a shorter period shall be rejected by the Employer as nonresponsive. |
|  | * 1. In exceptional circumstances, prior to the expiration of the bid validity period, the Employer may request Bidders to extend the period of validity of their bids. The request and the responses shall be made in writing. If a bid security is requested in accordance with ITB 19, it shall also be extended for forty five (45) days beyond the deadline of the extended validity period. A Bidder may refuse the request without forfeiting its bid security. A Bidder granting the request shall not be required or permitted to modify its bid. |
|  | 18.3 If the award is delayed by a period exceeding fifty-six (56) days beyond the expiry of the initial bid validity, the Contract price shall be determined as follows*:*   * + 1. In the case of fixed price contracts, the Contract price shall be the bid price adjusted by the factor **specified in the BDS**.     2. In the case of adjustable price contracts, no adjustment shall be made.     3. In any case, bid evaluation shall be based on the bid price without taking into consideration the applicable correction from those indicated above. |
| 1. Bid Security | 19.1 Unless otherwise **specified in the BDS**, the Bidder shall furnish as part of the Technical Part of its bid, in original form, a bid security for the amount **shown in BDS,** for this particular work*.* |
|  | 19.2 The bid security shall be a demand guarantee, at the Bidder’s option, in any of the following forms:   1. an unconditional bank guarantee, issued by a Nationalized/ Scheduled bank located in India; 2. an irrevocable letter of credit issued by a Nationalized or Scheduled bank located in India; 3. a cashier’s or certified check; or demand draft from a Nationalized or Scheduled Bank located in India; 4. another security **indicated in the BDS.**   *In case of a bank guarantee, the bid security shall be submitted using the Bid Security form included in the Section IV (Bidding Forms).* The form must include the complete name of the Bidder. The bid security shall be valid for forty five (45) days beyond the original validity period of the bid, or beyond any period of extension if requested under ITB 18.2. |
|  | 19.3 If a Bid Security is specified pursuant to ITB 19.1, any bid not accompanied by a substantially responsive Bid Security shall be rejected by the Employer as non-responsive. |
|  | 19.4 If a bid security is specified pursuant to ITB 19.1, the bid security of unsuccessful Bidders shall be returned as promptly as possible upon the successful Bidder’s signing the contract and furnishing of the performance security pursuant to ITB 45. |
|  | 19.5 If a bid security is specified pursuant to ITB 19.1, the bid security of the successful Bidder shall be returned as promptly as possible once the successful Bidder has signed the Contract and furnished the required performance security. |
|  | 19.6 The bid security may be forfeited:   1. if a Bidder withdraws/modifies/substitutes its bid during the period of bid validity specified by the Bidder on the Letter of Bid - Technical Part and repeated in the Letter of Bid - Financial Part, or any extension thereto provided by the Bidder in accordance with ITB 18.2 or 2. if the Bidder does not accept the correction of its Bid Price pursuant to ITB 36 or 3. if the successful Bidder fails to:  sign the Contract in accordance with ITB 44; orfurnish a performance security in accordance with ITB 45. |
|  | 19.7 The Bid Security of a JV shall be in the name of the JV that submits the bid. If the JV has not been constituted into a legally-enforceable JV*,* at the time of bidding, the Bid Security shall be in the names of all future members as named in the letter of intent mentioned in ITB 4.1.2 and ITB 11.2. |
| 1. Format and Signing of Bid | 20.1 The Bidder shall prepare the Bid as per details given in ITB 21. |
|  | 20.2 The bid shall be signed by a person duly authorized to sign on behalf of the Bidder. This authorization shall be uploaded along with the Bid. |
|  | 20.3 In case the Bidder is a JV, the Bid shall be signed by an authorized representative of the JV on behalf of the JV, and so as to be legally binding on all the members as evidenced by a power of attorney signed by their legally authorized representatives  20.4 Documents establishing authority to sign the bid on behalf of the JV shall be uploaded along with the bid.  20.5 The Bidder shall furnish information as described in the letter of Bid on commissions or gratuities, if any, paid or to be paid to agents relating to this Bid, and to contract execution if the Bidder is awarded the contract. |
| 1. Online Submission and Opening of Bids | |
| 1. Preparation of Bids | 221.1 Bids, both Technical and Financial Parts, shall be submitted online on the e-procurement system specified in BDS 7.1. Detailed guidelines for viewing bids and submission of online bids are given on the website. The Invitation for Bids under this Project is published on this website. Any citizen or prospective bidder can logon to this website and view the Invitation for Bids and can view the details of works for which bids are invited. A prospective bidder can submit its bid online; however, the bidder is required to have enrolment/registration in the website, and should have valid Digital Signature Certificate (DSC) in the form of smart card/e-token obtained from any certifying agency authorised by the Government of India (for class of DSC **specified in BDS**). The bidder should register in the website using the relevant option available. Then the Digital Signature registration has to be done with the e-token, after logging into the website. The bidder can then login the website through the secured login by entering the password of the e-token & the user id/ password chosen during registration. After getting the bid schedules, the Bidder should go through them carefully and submit the specified documents, alongwith the bid, otherwise the bid will be rejected. |
|  | 21.2 The completed bid comprising of documents indicated in ITB 12, should be uploaded on the e-procurement portal along with scanned copies of requisite certificates as are mentioned in different sections in the bidding document and scanned copy of the bid security. |
|  | 21.3 All the documents are required to be signed digitally by the bidder. After electronic on line bid submission, the system generates a unique bid identification number which is time stamped as per server time. This shall be treated as acknowledgement of bid submission. |
|  | 21.4 Physical, E-mail, Telex, Cable or Facsimile bids will be rejected as non-responsive. |
| 1. Deadline for Submission of Bids | 22.1 Bids must be uploaded online no later than the date and time **indicated in the BDS**. |
|  | * 1. The Employer may, at its discretion, extend the deadline for the submission of bids by amending the Bidding Document in accordance with ITB 8, in which case all rights and obligations of the Employer and Bidders previously subject to the deadline shall thereafter be subject to the deadline as extended. |
| 1. Late Bids | 23.1 The electronic bidding system would not allow any late submission of bids after due date & time as per server time. |
| 1. Withdrawal, Substitution, and Modification of Bids | 24.1 Bidders may modify their bids by using the appropriate option for bid modification on e-procurement portal, before the deadline for submission of bids. For this the bidder need not make any additional payment towards the cost of bid document. For bid modification and consequential re-submission, the bidder is not required to withdraw his bid submitted earlier. The last modified bid submitted by the bidder within the bid submission time shall be considered as the bid. For this purpose, modification/withdrawal by other means will not be accepted. In online system of bid submission, the modification and consequential re-submission of bids is allowed any number of times. A bidder may withdraw his bid by using the appropriate option for bid withdrawal, before the deadline for submission of bids, however, if the bid is withdrawn, re-submission of the bid is not allowed (or allowed **if specified in BDS).** |
|  | * 1. Bids requested to be withdrawn in accordance with ITB 24.1 shall not be opened. |
|  | 24.3 No bid may be withdrawn, substituted, or modified in the interval between the deadline for submission of bids and the expiration of the period of bid validity specified by the Bidder on the Letter of Bid or any extension thereof. This will result in the forfeiture of the Bid Security pursuant to ITB 19.6. |
| **E. Public Opening of Technical Parts of Bids** | |
| 1. Public Opening of Technical Parts of Bids | 25.1 The Employer shall publicly open Technical Parts of all bids received by the deadline, at the date, time and place **specified in the BDS** in the presence of Bidders’ designated representatives and anyone who choose to attend, and this could also be viewed by the bidders online. The Financial Parts of the bids shall remain unopened in the e-procurement system, until the subsequent public opening, following the evaluation of the Technical Parts of the Bids. In all cases, original documents submitted as specified in ITB 12.3 shall be first scrutinized, and Bids that do not comply with the provisions of ITB 12.3 will be declared non-responsive and will not be opened. Thereafter bidder’s names, and such other details as the Employer may consider appropriate will be notified online as Technical Part bid opening summary.  In the event of the specified date of bid opening being declared a holiday for the Employer, the bids will be opened at the appointed time and location on the next working day. |
|  | * 1. The electronic summary of the bid opening will be generated and uploaded online. The Employer will also prepare minutes of the Bid opening, including the information disclosed and upload the same for viewing online. Only Technical Parts of Bids that are opened at Bid opening shall be considered further for evaluation. |
| F. Evaluation of Bids – General Provisions | |
| 1. Confidentiality | 26.1 Information relating to the examination, evaluation, comparison, and post-qualification of bids and recommendation of contract award, shall not be disclosed to Bidders or any other persons not officially concerned with such process until information on Contract award is communicated to all Bidders in accordance with ITB 44. |
|  | * 1. Any attempt by a Bidder to influence the Employer in the evaluation of the bids or Contract award decisions may result in the rejection of its bid. |
|  | 26.3 Notwithstanding ITB 26.2, from the time of bid opening to the time of Contract award, if any Bidder wishes to contact the Employer on any matter related to the bidding process, it may do so in writing. |
| 1. Clarification of Bids | 27.1 To assist in the examination, evaluation, and comparison of the bids, and qualification of the Bidders, the Employer may, at its discretion, ask any Bidder for a clarification of its bid including breakdown of unit rates, giving a reasonable time for response. Any clarification submitted by a Bidder that is not in response to a request by the Employer shall not be considered. The Employer’s request for clarification and the response shall be in writing. No change, including any voluntary increase or decrease in the prices or substance of the bid shall be sought, offered, or permitted, except to confirm the correction of arithmetic errors discovered by the Employer in the evaluation of the bids, in accordance with ITB 36. |
|  | * 1. If a Bidder does not provide clarifications of its bid by the date and time set in the Employer’s request for clarification, its bid may be rejected. |
| 1. Deviations, Reservations, and Omissions | 28.1 During the evaluation of bids, the following definitions apply:  (a) “Deviation” is a departure from the requirements specified in the Bidding Document;  (b) “Reservation” is the setting of limiting conditions or withholding from complete acceptance of the requirements specified in the Bidding Document; and  (c) “Omission” is the failure to submit part or all of the information or documentation required in the Bidding Document. |
| 1. Nonconformities, Errors, and Omissions | 29.1 Provided that a bid is substantially responsive, the Employer may waive any non-conformities in the bid which do not constitute a material deviation, reservation or omission. |
|  | 29.2 Provided that a bid is substantially responsive, the Employer may request that the Bidder submit the necessary information or documentation, within a reasonable period of time, to rectify nonmaterial nonconformities in the bid related to documentation requirements. Requesting information or documentation on such nonconformities shall not be related to any aspect of the price or substance of the bid. Failure of the Bidder to comply with the request may result in the rejection of its bid.  29.3 Provided that a bid is substantially responsive, the Employer shall rectify quantifiable nonmaterial nonconformities related to the Bid Price. To this effect, the Bid Price may be adjusted, for comparison purposes only, to reflect the price of a missing or non-conforming item or component in the manner **specified in the BDS**. |
| **G. Evaluation of Technical Parts of Bids** | |
| 1. Evaluation of Technical Parts | 30.1 In evaluating the Technical Parts of each Bid, the Employer shall use the criteria and methodologies listed in this ITB and Section III, Evaluation and Qualification Criteria. No other evaluation criteria or methodologies shall be permitted. |
| 1. Determination of Responsiveness | 31.1 The Employer’s determination of a Bid’s responsiveness is to be based on the contents of the Bid itself, as defined in ITB 11.  31.2 A substantially responsive Bid is one that meets the requirements of the bidding document without material deviation, reservation, or omission. A material deviation, reservation, or omission is one that:  (a) if accepted, would: (i) affect in any substantial way the scope, quality, or performance of the Works specified in the Contract; or(ii) limit in any substantial way, inconsistent with the bidding document, the Employer’s rights or the Bidder’s obligations under the proposed Contract; or (b) if rectified, would unfairly affect the competitive position of other Bidders presenting substantially responsive Bids. |
|  | 31.3 The Employer shall examine the technical aspects of the Bid submitted in accordance with ITB 16, Technical Proposal, in particular, to confirm that all requirements of Section VII, Works’ Requirements have been met without any material deviation, reservation or omission. |
|  | 31.4 If a Bid is not substantially responsive to the requirements of the bidding document, it shall be rejected by the Employer and may not subsequently be made responsive by correction of the material deviation, reservation, or omission. |
| 1. Qualification of the Bidder | 32.1 The Employer shall determine to its satisfaction whether the eligible Bidders that have submitted substantially responsive Bid - Technical Parts meet the qualifying criteria specified in Section III, Evaluation and Qualification Criteria. |
|  | 32.2 The determination shall be based upon an examination of the documentary evidence of the Bidder’s qualifications submitted by the Bidder, pursuant to ITB 17. The determination shall not take into consideration the qualifications of other firms such as the Bidder’s subsidiaries, parent entities, affiliates, subcontractors (other than Specialized Subcontractors if permitted in the bidding document), or any other firm(s) different from the Bidder. |
|  | 32.3 If a Bidder does not meet the qualifying criteria specified in Section III, Evaluation and Qualification Criteria, its Bid shall be rejected by the Employer and may not subsequently be made responsive by correction of the material deviation, reservation, or omission. |
|  | 32.4 Only Bids that are both substantially responsive to the bidding document, and meet all Qualification Criteria shall have the Financial Parts of their Bids opened at the second public opening. |
| 1. Subcontractors | 33.1 Unless otherwise **stated in the BDS**, the Employer does not intend to execute any specific elements of the Works by subcontractors selected in advance by the Employer.  33.2 The Employer may permit subcontracting for certain specialized works as indicated in Section III. When subcontracting is permitted by the Employer, the specialized sub-contractor’s experience shall be considered for evaluation. Section III describes the qualification criteria for sub-contractors.  33.3 Bidders may propose subcontracting up to the percentage of total value of contracts or the volume of works as **specified in the BDS**. Subcontractors proposed by the Bidder shall be fully qualified for their parts of the Works. |
| **H. Public Opening of Financial Parts of Bids** | |
| 1. Public Opening of Financial Parts | 34.1 Following the completion of the evaluation of the Technical Parts of the Bids, and the Bank has issued its no objection (if applicable), the Employer shall notify in writing those Bidders whose Bids were considered non-responsive to the bidding document or failed to meet the Qualification Criteria, advising them of the following information:   * + 1. the grounds on which their Technical Part of Bid failed to meet the requirements of the bidding document;     2. their Financial Part of Bid shall not be opened; and   (c) notify them of the date and time for public opening of Financial Parts of the Bids. |
|  | 34.2 The Employer shall, simultaneously, notify in writing those Bidders whose Technical Part have been evaluated as substantially responsive to the bidding document and met all Qualifying Criteria, advising them of the following information:   * + 1. their Bid has been evaluated as substantially responsive to the bidding document and met the Qualification Criteria;     2. their Financial Part of Bid will be opened at the public opening of the Financial Parts; and     3. notify them of the date, time, and place of the second public opening of the Financial Parts of the Bids, **as specified in the BDS.** |
|  | 34.3 The opening date should allow Bidders sufficient time to make arrangements for attending the opening. The Financial Part of the Bids shall be opened publicly in the presence of Bidders’ designated representatives and anyone who choose to attend, and this could also be viewed by the bidders online. The bidder’s names, the Bid prices, the total amount of each bid, per lot (contract) if applicable, including any discounts, and such other details as the Employer may consider appropriate, will be notified online by the Employer at the time of bid opening.  In the event of the specified date of bid opening being declared a holiday for the Employer, the bids will be opened at the appointed time and location on the next working day. |
| **I. Evaluation of Financial Parts of Bids** | |
| 1. Evaluation of Financial Parts | 35.1 To evaluate the Financial Part, the Employer shall consider the following: |
|  | (a) the Bid price, excluding Provisional Sums and the provision, if any, for contingencies in the Summary Bill of Quantities but excluding Daywork items, where priced competitively; |
|  | (b) Not used; |
|  | (c) price adjustment due to discounts offered in accordance with ITB 14.4; |
|  | (d) Not used; |
|  | (e) price adjustment due to quantifiable nonmaterial nonconformities in accordance with ITB 29.3; and |
|  | (f) the additional evaluation factors as specified in Section III, Evaluation and Qualification Criteria. |
|  | 1. The estimated effect of the price adjustment provisions of the Conditions of Contract, applied over the period of execution of the Contract, shall not be taken into account in Bid evaluation. |
|  | 1. If this bidding document allows Bidders to quote separate prices for different lots (contracts), and to award multiple contracts to a single Bidder, the methodology to determine the lowest evaluated price of the contract combinations, including any discounts offered in the Letter of Bid – Financial Part, is specified in Section III, Evaluation and Qualification Criteria |
| 1. Correction of Arithmetical Errors | 36.1 The e-procurement system automatically calculates the total amount from unit rates and quantities and the system also automatically populates the amount in words from the amount in figures and therefore there is no scope of discrepancy and need for arithmetic correction. |
| 1. Conversion to Single Currency | 37.1 Not used. |
| 1. Margin of Preference | 38.1 Not used. |
| 1. Comparison of Financial Parts | 39.1 The Employer shall compare the evaluated prices of all substantially responsive bids established in accordance with ITB 35.1 to determine the lowest evaluated bid. |
| 1. Unbalanced or Front Loaded Bids | 1. If the bid, which results in the lowest Evaluated Bid Price, is seriously unbalanced, front loaded or substantially below updated estimates in the opinion of the Employer, the Employer may require the Bidder to produce detailed price analyses (with breakdown of unit rates) for any or all items of the Bill of Quantities, to demonstrate the internal consistency and justification of those prices with the construction methods and schedule proposed. After evaluation of the price analyses, taking into consideration the schedule of estimated contract payments, the Employer may require that the amount of the performance security be increased at the expense of the Bidder to a level sufficient to protect the Employer against financial loss in the event of default of the successful Bidder under the Contract. |
| 1. Employer’s Right to Accept Any Bid, and to Reject Any or All Bids | 41.1 The Employer reserves the right to accept or reject any bid, and to annul the bidding process and reject all bids at any time prior to contract award, without thereby incurring any liability to Bidders. In case of annulment, all documents submitted and specifically, bid securities, shall be promptly returned to the Bidders. |
| J. Award of Contract | |
| 1. Award Criteria | 42.1 Subject to ITB 41*,* the Employer shall award the Contract to the successful Bidder that meets the Qualification Criteria, whose offer has been determined to be the lowest evaluated bid and is substantially responsive to the Bidding Document. |
| 1. Notification of Award | 43.1 Prior to the expiration of the period of bid validity, the Employer shall notify the successful Bidder, in writing, via the Letter of Acceptance included in the Contract Forms, that its bid has been accepted. The Letter of Acceptance shall specify the sum that the Employer will pay the Contractor in consideration of the execution and completion of the Works (hereinafter and in the Conditions of Contract and Contract Forms called “the Contract Price”). |
|  | * 1. Until a formal contract is prepared and executed, the notification of award shall constitute a binding Contract. |
| 1. Signing of Contract, Publication of award and Recourse to unsuccessful Bidders | 44.1 The Contract Agreement shall incorporate all agreements between the Employer and the successful Bidder. It shall be kept ready in the office of the Employer for the signature of the Employer and the successful Bidder, within 21 days following the date of Letter of acceptance. Within 21 days of receipt of Letter of acceptance, the successful Bidder shall sign the Agreement and furnish the performance security in accordance with ITB Clause 45 and revised construction methodology. If the successful bidder is a JV, it shall also furnish the JV agreement duly signed by all the members, if it had submitted only a letter of intent to execute the JV agreement alongwith the bid. |
|  | 44.2 The Employer within 3 weeks of issue of notification of award shall publish in a national website (<http://tenders.gov.in> or GoI Central Public Procurement Portal <https://eprocure.gov.in/cpppp/>) or on the Employer’s website with free access if available, or in the official gazette, the results identifying the bid and lot numbers and the following information: (i) name of each bidder who submitted the bid; (ii) bid prices as read out at bid opening; (iii) name and evaluated prices of each bid that was evaluated; (iv) name of bidders whose bids were rejected and the reasons for their rejection; and (v) name of the winning bidder, and the price it offered, as well as the duration and summary scope of the contract awarded.  44.3 The Employer shall promptly respond in writing to any unsuccessful Bidder who, after publication of contract award, requests the Employer in writing to explain on which grounds its bid was not selected. |
| 1. Performance Security | 45.1 Within twenty-one (21) days of the receipt of notification of award from the Employer, the successful Bidder shall furnish the performance security in accordance with the conditions of contract, subject to ITB 40.1, using for that purpose the Performance Security and ESHS Security Forms included in Section X (Contract Forms). The performance security of a Joint Venture shall be in the name of the Joint Venture specifying the names of all members. |
|  | * 1. Failure of the successful Bidder to submit the above-mentioned Performance Security or to sign the Contract Agreement shall constitute sufficient grounds for the annulment of the award and forfeiture of the bid security. In that event the Employer may award the Contract to the next lowest evaluated Bidder whose offer is substantially responsive and is determined by the Employer to be qualified to perform the Contract satisfactorily. |
|  | 45.3 Upon the successful Bidder’s signing the Agreement and furnishing of the Performance Security pursuant to ITB Clause 45.1, the Employer shall promptly notify the name of the winning bidder to each unsuccessful bidder and shall discharge the Bid Securities of the bidders pursuant to ITB Clause 19.4 and 19.5. |
| 1. Adjudicator or Dispute Review Expert | 46.1 The Employer proposes the person **named in the BDS** to be appointed as Adjudicator (or Dispute Review Expert) under the Contract, at the daily rate **specified in the BDS**, plus reimbursable expenses (actual boarding, lodging, travel and other incidental expenses). If the Bidder disagrees with this proposal, the Bidder should so state in Letter of Bid. If, in the Letter of Acceptance, the Employer does not agree on the appointment of the Adjudicator [or Disputes Review Expert] proposed by the Bidder, the Employer will request the Appointing Authority designated in the Particular Conditions of Contract (PCC) pursuant to Clause 23.1 of the General Conditions of Contract (GCC), to appoint the Adjudicator [or Disputes Review Expert]. |

Section II - Bid Data Sheet (BDS)

A. General

|  |  |
| --- | --- |
| **ITB 1.1** | The Employer is: ***[insert complete name of Employer]*** |
| **ITB 1.1** | The name of the work is: ***[insert complete name]***  The identification number of the work is: ***[insert identification number of bid]***  The number and identification of lots comprising this bidding process is: ***[insert number of lots and identification number of each lot, if applicable]*** |
| **ITB 2.1** | The Borrower is Government of India. The Sub-Borrower is ………………………….: The Employer is ………….. ***[insert name of the Sub-Borrower and statement of relationship with the Employer, if different from the Borrower/Sub-Borrower. This insertion should correspond to the information provided in the Invitation for Bids.]*** |
| **ITB 2.1** | The name of the Project is: ***[insert name of the Project]***  Loan or Financing Agreement amount: ***[insert amount]*** |
| **ITB 4.1.1** | (*State here whether Joint Ventures are acceptable or not*) Bids from Joint ventures are/are not acceptable. |
| **ITB 4.1.2 (a)** | Maximum number of members in the JV shall be***: [Insert number where JVs are acceptable. Otherwise delete****]* |
| **ITB 4.1.2 (g)** | Place where the agreement to form JV to be registered is……………  *[****Fill in the name of the city where the construction contract agreement is to be signed****]* |
| **ITB 4.4** | A list of debarred firms and individuals is available at the Bank’s external website www.worldbank.org/debarr. |

B. Contents of Bidding Documents

|  |  |
| --- | --- |
| **ITB 7.1** | **Electronic –Procurement System**  The Employer shall use the following electronic-procurement system to manage this Bidding process:  ***[insert name of the e-system and url address or link]***  Requests for clarification should be received by the Employer no later than **14 *days prior to deadline for submission of bids.*** |
| **ITB 7.4** | A Pre-Bid meeting *[****insert “shall” or “shall not”****]* take place. If a Pre-Bid meeting will take place, it will be at the following date, time and place: ***[insert date, time & place below, if applicable]***  Date:  Time:  Place:  [***The pre-bid meeting should be held no later than 2 weeks before the deadline for submission].*** |
| **ITB 8.1** | The addendum will appear on the e-procurement system under ……….. and email notification is also automatically sent to those bidders who have started working on this tender.  *[Note – insert/ modify the above if any change is required in the provisions of ITB 8.1, otherwise delete this BDS entry]* |

C. Preparation of Bids

|  |  |
| --- | --- |
| **ITB 11.2 (b)** | The following schedules shall be submitted with the bid: ***[insert schedules that must be submitted with the Bid, including the priced Bill of Quantities]*** |
| **ITB 11.2 (j)** | The Bidder shall submit with its bid the following additional documents: ***[list any additional documents not already listed in ITB 11.2 that must be submitted with the Bid – Technical Part. The list of additional documents should include the following:]***  (i) Contractor Registration certificate as per IFB, if applicable  (ii) Comprehensive and concise Environmental, Social, Health and Safety Management Strategies and Implementation Plans including Code of Conduct that will apply to its employees and subcontractors, to ensure compliance with its Environmental, Social, Health and Safety (ESHS) obligations including compliance with applicable Laws/ Rules/ Regulations for protection of environment, public health and safety, and the applicable parts of the Environment Management Plan of the project under the contract[[3]](#footnote-3). |
| **ITB 11.3 (d)** | The Bidder shall submit the following additional documents in its Bid: ***[list any additional document not already listed in ITB 11.3 that must be submitted with the Bid – Financial Part]*** |
| **ITB 12** | **Note for Bidders:** Bidders have to submit the bids on the e-procurement portal along with the relevant required documents. For this purpose, the bidders shall fill up online, the forms that are available for online filling on the e-portal. The rest of the forms shall be download by the bidders and filled up. The filled up pages shall then be scanned and uploaded on the e-procurement portal along with the scanned copies of the supporting documents. |
| **ITB 12.3** | For submission of original documents, the Employer’s address is:  Attention: ………*[****insert full name of person, if applicable]***  Street Address: …………[***insert street address and number****]*  Floor/ Room number: …….[***insert floor and room number, if applicable***  City: ………[***insert name of city or town***]  PIN/Postal Code: ………[***insert postal (PIN) code, if applicable***]  Country: INDIA |
| **ITB 13.1** | Alternative bids ***shall not be*** permitted. |
| **ITB 14.5** | The prices quoted by the Bidder *[insert “shall be” or “shall not be”]* subject to adjustment during the performance of the Contract. The adjustment of contract price, if provided, will be done in accordance with GCC Clause 45 read with corresponding provisions under SCC and Appendix 2 to SCC. |
| **ITB 18.1** | The bid validity period shall be: 90 days.  ***[insert a bid validity period of other than 90 days, if considered necessary]*** |
| **ITB 18.3 (a)** | The factor is … % per annum. *[To be fixed based on average inflation in India during the past one year.]* |
| **ITB 19.1** | The Bidder shall furnish a bid security in the amount of …………….. ***[insert amount in Indian Rupees.*** *It should not exceed 2 (two)% of the estimated value of works.****]***  ***[In case of lots, please insert amount of the Bid Security for each lot].***  Note: Bid Security is required for each lot as per amounts indicated against each lot. Bidders have the option of submitting one Bid Security for all lots (for the combined total amount of all lots) for which Bids have been submitted. However, if the amount of Bid Security is less than the total required amount, the Employer will determine (based on lowest cost combination of bids) for which lot or lots the Bid Security amount shall be applied. |
| **ITB 19.2 (d)** | Other types of acceptable securities are:  Fixed Deposit/Time Deposit certificate issued by a Nationalized or Scheduled Bank located in India for equivalent or higher values are acceptable as bid security provided it is pledged in favour of ………………..(implementing agency) and such pledging has been noted and suitably endorsed by the bank issuing the certificate.  *[Insert other types of acceptable bid securities as above. Insert ‘None’ if no other form of bid securities besides those listed in ITB 19.2 (a) to (c) is acceptable.]* |
| **ITB 20.2** | The written confirmation of authorization to sign on behalf of the Bidder shall consist of:  *[insert “*   1. *Legally valid Power of Attorney is required to demonstrate the authority of the signatory to sign the Bid; and* 2. *In the case of Bids submitted by an existing or intended JV, if permitted as per ITB 4.1, the authorization shall be evidenced by a Power of Attorney signed by legally authorized signatories of all the members.”]* |

D. Online Submission and Opening of Bids

|  |  |
| --- | --- |
| **ITB 21.1** | Class of DSC required is: …………………. |
| **ITB 22.1** | **The deadline for uploading of bids is:**  Date:  Time:  ***[The date and time should be the same as those provided in the Invitation for Bids unless subsequently amended pursuant to ITB 22.2]*** |
| **ITB 24.1** | Re-submission of the bid is ­­\_\_\_\_\_\_\_\_\_\_*\_\_\_\_\_\_\_\_\_\_\_****[Insert “allowed” or “not allowed”]***, if withdrawn. |
| **E. Public Opening of Technical Parts of Bids** | |
| **ITB 25.1** | The online bid opening of Technical Parts of Bids shall take place at: ***[insert all required and applicable information]***  Street Address:  Floor/Room number:  City:  Country: INDIA  Date:  Time:  *[Note: this date should be 2 days after deadline for submission of technical part of bids to allow submission of original documents].* |

F. Evaluation of Bids – General Provisions

|  |  |  |
| --- | --- | --- |
| **ITB 29.3** | | The adjustment shall be based on the highestprice of the item or component as quoted in other substantially responsive Bids, subject to a maximum of the estimated price of the item. If the price of the item or component cannot be derived from the price of other substantially responsive Bids, the Employer shall use its best estimate. |
| **G. Evaluation of Technical Parts of Bids** | | |
| **ITB 33.1** | | At this time the Employer \_\_\_\_\_\_\_\_\_\_\_ *[Insert “intends” / “does not intend”]* to execute certain specific parts of the Works by sub-contractors selected in advance.  [If the above states “intends” list the specific parts of the works and the respective sub-contractors] |
| **ITB 33.2** | | ***[Indicate N/A if not applicable]***  The parts of the Works for which the Employer permits Bidders to propose Specialized Subcontractors are designated as follows:   1. \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ 2. \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ 3. \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_   For the above-designated parts of the Works that may require Specialized Subcontractors, the relevant qualifications of the proposed Specialized Subcontractors will be added to the qualifications of the Bidder for the purpose of evaluation. |
| **ITB 33.3** | | (a) Contractor’s proposed subcontracting: Maximum percentage of subcontracting permitted is: *\_\_\_\_\_\_\_% of the total contract amount or \_\_\_\_\_\_\_% of the volume of work\_\_\_\_\_\_\_\_\_\_\_\_\_.*  (b) Bidders planning to subcontract more than 10% of total volume of work shall specify, in the Bid Submission Form, the activity (ies) or parts of the works to be subcontracted alongwith complete details of the sub-contractors and their qualification and experience. The qualification and experience of the sub-contractors must meet the minimum criteria for the relevant work to be sub-contracted failing which such sub-contractors will not be permitted to participate. (c) Sub-contractors’ qualification and experience will not be considered for evaluation of the Bidder. The Bidder on its own (without taking into account the qualification and experience of the sub-contractor) should meet the qualification criteria.*[Note: Work should not be split into small parts and sub-contracted].* |
| **H. Public Opening of Financial Parts of Bids** | | |
| **ITB 34.2 (c)** | Following the completion of the evaluation of the Technical Parts of the Bids, the Employer will notify all Bidders of the place, date and time of the public opening of Financial Parts.  The online bid opening of Financial Parts of Bids shall take place on:  Place:  Date:  Time:  In addition to the above the Employer shall publish a notice of the public opening of the Financial Parts of the Bid on its website…………... ***[insert address of the website]*** | |
| **J. Award of Contract** | | |
| **ITB 45.1 and 45.2** | | The successful Bidder shall also be required to submit an Environmental, Social, Health and Safety (ESHS) Performance Security.  ***[Note: throughout this bidding document the term ’performance security’, unless the context clearly indicates otherwise, means and includes both ‘the performance security and the ESHS performance security’ to be submitted by the successful bidder in the amounts specified in GCC/ PCC 50]*** |
| **ITB 46.1** | | The Adjudicator/Dispute Review Expert proposed by the Employer is***: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ [insert name and address of proposed Adjudicator or Dispute Review expert, as applicable]***. The daily fee for this proposed Adjudicator/Dispute Review Expert shall be: \_\_\_\_\_\_\_\_\_\_ ***[insert amount in Rupees – not less than Rs. 5000 per day].*** The biographical data of the proposed Adjudicator/Dispute Review Expert is as follows: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ ***[provide relevant information, such as education, experience, age, nationality, and present position; attach additional pages as necessary]***  **Note:**  *Institutions such as Indian Council of Arbitration (ICA) also maintain panel of experienced and trained adjudicators and if needed, such institutions could be approached for providing a list of potential adjudicators. If this option is to be used, above clause may be modified as:*  “The Adjudicator proposed by the Employer is: ………… and has been identified from the list provided by …………. *[insert name of the Institution]*. The daily fee payable to Adjudicator is Rs……... as per the rules of the Institution.” |

**Section III - Evaluation and Qualification Criteria**

*This section contains all the criteria that the Employer shall use to evaluate bids and qualify Bidders if the bidding was not preceded by a prequalification exercise and post qualification is applied. In accordance with ITB 32 and ITB 35, no other methods, criteria and factors shall be used. The Bidder shall provide all the information requested in the forms included in Section IV (Bidding Forms).*

*[The Employer shall select the criteria deemed appropriate for the procurement process, insert the appropriate wording using the samples below or other acceptable wording, and delete the text in italics]*

1. Technical Part

1.1 Adequacy of Technical Proposal

# Evaluation of the Bidder’s Technical Proposal will include:

# (i) an assessment of the Bidder’s technical capacity to mobilize key equipment and personnel for the contract consistent with its proposal regarding work methods, scheduling, material sourcing and Quality Control/Assurance in sufficient detail and fully in accordance with the requirements stipulated in Section VII (Works Requirements).

# For this purpose the Bidder should also submit:

# A detailed note outlining its proposed methodology and program of construction including implementation of the Environmental Management Plan, and safety Assurance under the contract backed with equipment planning and deployment, materials and manpower planning and deployment, duly supported with broad calculations and quality control system/assurance procedures proposed to be adopted, justifying their capability of execution and completion of the work as per technical specifications within the stipulated period of completion as per milestones.

# (ii) an assessment of the details of subcontracting elements of works amounting to more than 10% of the bid price; for each element proposed to be sub contracted furnish details whether the identified Sub-contractor possesses the required qualifications and experiences to execute that element satisfactorily.[*Work should not be split into small parts and sub-contracted*].

1.2 Multiple Contracts if permitted under ITB 35.3, will be evaluated as under.

If works are grouped in multiple contracts pursuant to Sub-Clause 35.3 of the Instructions to Bidders, the criteria for qualification will be an assessment of the Bidder’s capacity to meet the aggregated requirements regarding:

* Experience
* Financial situation
* Current contract commitments,
* Cash flow capacity,
* Equipment to be allocated, and
* Personnel to be fielded.
* Bid Capacity

**1.3 Specialised Subcontractors**

*[Note: provide details if the clause is relevant. Insert ‘Not Applicable’ or delete the clause, if not relevant]*

If permitted under ITB 33, only the specific experience of sub-contractors for specialized works permitted by the Employer will be considered. The general experience and financial resources of the specialized sub-contractors shall not be added to those of the Bidder for purposes of qualification of the Bidder.

The specialized sub-contractors proposed shall be fully qualified for their work proposed, and meet the following criteria:

2. Qualification

|  |  | |  |  | |  | |  |  | |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Eligibility and Qualification Criteria | | | | Compliance Requirements | | | | | | Documentation | |
| No. | Subject | | Requirement | Single Entity | | Joint Venture where permitted | | | | Submission Requirements | |
| **All Parties Combined** | | **Each Member** | **One Member** |
| 2.1 Eligibility | | | | | | | | | | | |
| 2.1.1 | Nationality | | Nationality in accordance with ITB Sub-Clause 4.3. | Must meet requirement | | Existing or intended JV must meet requirement | | Must meet requirement | N / A | Forms ELI –1.1 and ELI-1.2  With attachments | |
| 2.1.2 | Conflict of Interest | | No conflicts of interest in ITB Sub-Clause 4.2. | Must meet requirement | | Existing or intended JV must meet requirement | | Must meet requirement | N / A | Letter of Bid | |
| 2.1.3 | Bank eligibility | | Not having been declared ineligible by the Bank, as described in ITB Sub-Clause 4.4. & 4.7. | Must meet requirement | | Existing JV must meet requirement | | Must meet requirement | N / A | Letter of Bid | |
| 2.1.4 | Government Owned Entity | | Bidder to meet conditions of ITB Sub-Clause 4.5. The entity should not be a dependent agency of the borrower or sub-borrower or Employer. | Must meet requirement | | Must meet requirement | | Must meet requirement | N / A | Forms ELI -1.1 and 1.2 with attachments | |
| 2.1.5 | United Nations resolution or Borrower’s country law | | Not having been excluded as a result of prohibition in the Borrower’s country laws or official regulations against commercial relations with the Bidder’s country, or by an act of compliance with UN Security Council resolution, both in accordance with ITB 4.7 and Section V. | Must meet requirement | | Must meet requirement | | Must meet requirement | N / A | Forms ELI -1.1 and 1.2 with attachments | |
| 2.2 Historical Contract Non-Performance | | | | | | | | | | | |
| 2.2.1 | History of Non-Performing Contracts | Non-performance of a contract[[4]](#footnote-4) did not occur as a result of contractor default since 1st January *[Insert year]*. | | | Must meet requirement by itself or as member to past or existing JV | | Must meet the requirement | Must meet requirement by itself or as member to past or existing JV | N / A | Form CON - 2 | |
| 2.2.2 | **Suspension due to withdrawal of the Bid within Bid validity** | Not under suspension due to withdrawal of the Bid pursuant ITB 19.6. | | | Must meet requirement | | Must meet requirement | Must meet requirement | N/A | Letter of Bid | |
| 2.2.3 | Pending Litigation | Bidder’s financial position and prospective long term profitability sound according to criteria established in 2.3.1 below and assuming that all pending litigation will be resolved against the Bidder | | | Must meet requirement by itself or as member to past or existing JV | | N / A | Must meet requirement by itself or as member to past or existing JV | N / A | Form CON - 2 | |
| 2.2.4 | Litigation History | No consistent history of court/arbitral award decisions against the Bidder[[5]](#footnote-5) since 1st January *[insert year]* | | | Must meet requirement by itself or as member to past or existing JV | | Must meet requirement | Must meet requirement by itself or as member to past or existing JV | N/A | Form CON - 2 | |
| 2.5 | **Declaration: Environmental, Social, Health, and Safety (ESHS) past performance** | Declare any civil work contracts that have been suspended or terminated and/or performance security called by an employer for reasons related to the non-compliance of any environmental, or social, or health or safety requirements or regulations in the past five years[[6]](#footnote-6). | | | Must make the declaration. Where there are Specialized Sub-contractor/s, the Specialized Sub-contractor/s must also make the declaration. | | N/A | Each must make the declaration. Where there are Specialized Sub-contractor/s, the Specialized Sub-contractor/s must also make the declaration. | N/A | Form CON-3 ESHS Performance Declaration | |

|  |  |  |  |  | | | |  | | |  | |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Qualification Criteria | | | Compliance Requirements | | | | | | | | | Documentation | |
| No. | Subject | Requirement | Single Entity | Joint Venture where permitted | | | | | | | | Submission Requirements | |
|  |  |  |  | All Parties Combined | | | Each Member | | One Member | | |  | |
| 2.3 Financial Situation and Performance | | | | | | | | | | | | | |
| 2.3.1 | Financial Capabilities | (a) The Bidder shall demonstrate that it has access to, or has available, liquid assets, unencumbered real assets, lines of credit, and other financial means (independent of any contractual advance payment) sufficient to meet the construction cash flow requirements estimated as Rs*\_\_\_\_\_\_\_\_\_\_\_\_\_(****about 3 months cash flow at peak construction period)\_*for** the subject contract(s) net of the Bidders other commitments  (b) The Bidders shall also demonstrate, to the satisfaction of the Employer, that it has adequate sources of finance to meet the cash flow requirements on works currently in progress and for future contract commitments  (c) The audited balance sheets or, if not required by the laws of the Bidder’s country, other financial statements acceptable to the Employer, for the last *five* years shall be submitted and must demonstrate the current soundness of the Bidder’s financial position and indicate its prospective long-term profitability. | (a) Must meet requirement  (b) Must meet requirement  (c) Must meet requirement | | (a) Must meet  the requirement  (b) Must meet requirement  N/A | (a) Must meet at least 25% of the requirement  as a minimum  N/A  (c) Must meet requirement | | | | (a) Must meet at least 50% of the requirement  as a minimum  N/A  N/A | | Form FIN - 3.1 with attachments | |
| **NOTE:**   *The construction cash flow requirement should be for a number of months determined as the total time needed to pay contractor invoice by the Employer. The cash flow should not normally exceed 3 months peak contract requirements and availability should be certified by Bank (Nationalized or Scheduled Bank in India) in form 3.1 A* | | | | | | | | | | | | | |
| 2.3.2 | Annual Construction Turnover | Achieved in at least two financial years (in the last five years) a minimum annual financial turnover[[7]](#footnote-7) in civil engineering construction work of ………..***\_[insert amount in Rs. ……in words and figures]\_\_,*** calculated as total certified payments received for contracts in progress or completed, | Must meet requirement | Must meet requirement | | Must meet twenty five percent (25%) of the requirement | | | | Must meet fifty percent (50%) of the requirement | | Form FIN - 3.2 | |

*Note-The amount stated should normally not be less than twice the estimated annual turnover or cash flow in the proposed Works contract (based on a straight-line projection of the Employer's estimated cost, over the contract duration).*

|  |  | |  | |  | |  | | |  | | |  | | |  | |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Qualification Criteria | | | | | Compliance Requirements | | | | | | | | | Documentation | | | |
| No. | Subject | | Requirement | | Single Entity | | Joint Venture where permitted | | | | | | | Submission Requirements | | | |
|  |  | |  | |  | | All Parties Combined | | Each Member | | One Member | | |  | | | |
| 2.4 Experience | | | | | | | | | | | | | | | | | |
| 2.4.1 | General Construction Experience | Experience under construction contracts for similar works such as those pertaining to ………….. [Indicate details of acceptable similar works] in the role of contractor, JV member, sub-contractor, or management contractor for at least the last five [5] years prior to the bid submission deadline. | | Must meet requirement | | N/A | | Must meet requirement of having executed works of similar nature | | | | N/A | | | Form EXP – 4.1 | |

|  |  |  |  |  | | |  | | |  | |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Qualification Criteria | | | Compliance Requirements | | | | | | | | Documentation | |
| No. | Subject | Requirement | Single Entity | Joint Venture where permitted | | | | | | | Submission Requirements | |
|  |  |  |  | All Parties Combined | | Each Member | | One Member | | |  | |
| 2.4.2 (a) | Specific Construction Experience | Bidder should have successfully completed as a prime contractor, JV member[[8]](#footnote-8), management contractor or sub-contractor, minimum one (1) contract substantially *(not less than 90% of contract value*) within the last five (5) years (FY…..to FY …..), with a value[[9]](#footnote-9) of at least \_\_\_\_\_\_\_\_\_\_\_\_, which is similar to the proposed works. (*Indicate here what works will be considered as similar here*.) The similarity shall be based on the physical size, complexity, methods/technology or other characteristics as described in Section VII, Employer’s requirements. | Must meet requirement | Must meet requirement | Must meet requirement for one contract of 25% value | | | | Must meet requirement for one contract of 50% in value | | Form EXP 4.2(a). The contractor should have borne responsibility for execution of works to the extent he claims experience. A contractor should not claim experience for the works he has never executed. | |
| *The value of the completed contract for similar works should not be less than 80% of the estimated contract value of the work for which bids are invited. A work where 90% of contract value is paid is considered as completed.*  *In the case of JV, the value of contracts completed by its members shall not be aggregated to determine whether the requirement of the minimum value of a single contract has been met. Instead, each contract performed by each member shall satisfy the minimum value of a single contract as required for single entity. In determining whether the JV meets the requirement of total number of contracts, only the number of contracts completed by all members each of value equal or more than the minimum value required shall be aggregated* | | | | | | | | | | | | |

| Qualification Criteria | | | Compliance Requirements | | | | Documentation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Subject | Requirement | Single Entity | Joint Venture where permitted | | | Submission Requirements |
|  |  |  |  | All Parties Combined | Each Member | One Member |  |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.4.2  (b) | Specific Experience | | b) For the above or other contracts executed during the period stipulated in 2.4.2(a) above, at least in one year a minimum construction experience in the following key activities: | Must meet requirements | Must meet requirement | Should meet the criteria in full, at least for one of key activities listed in column 3. | Must meet requirement for the key activities listed below (list key activities for this member and corresponding minimum requirements)  …………..  …………..  …………..  ………….. | Form EXP-4.2(b) |
| *NOTE: List the monthly or annual production rate for the key construction activity (or activities) in the proposed contract or works, e.g., “one million M3 of rock placed in rock fill dams in one year; X tons of asphalt concrete per month placed in road paving; Y M3 of concrete placed in ... etc.” The rates should be a percentage (say about 80 percent) of the estimated production rate of the key activity (or activities) in the contract or Works as needed to meet the expected construction schedule with due allowance for adverse climatic conditions.*  *\* Borrower should fill this after careful review of the requirements for the work. Where the elements of work are specialized and it is proposed to accept employment of specialist sub-contractors, this could be specified for that activity and bidders may be requested to name the sub-contractors and furnish their qualification and experience.* | | | | | | | | |
| **2.4.2 (c)** For a bidder (either individually as a single entity or as a JV member) to qualify for a group of lots (contracts), he must demonstrate having experience and resources sufficient to meet the aggregate of the qualifying criteria for all the contracts in question. | | | | | | | | |
| **2.4.2 (d)** | | Bidders who meet the minimum qualification criteria will be qualified only if their available bid capacity for construction work is equal to or more than the total bid value of the work. The available bid capacity will be calculated as under:  Assessed Available bid capacity = (A\*N\*1.5-B)  Where,  A = Maximum value of civil engineering works executed in any one year during the last five years (updated to the price level of the financial year ….. at the rate of 5% per year), taking into account the completed as well as works in progress).  N = Number of years prescribed for completion of the works for which bids are invited (period upto 6 months to be taken as half-year and more than 6 months as one year).  B = Value, at the current price level, of existing commitments on on-going works to be completed during the period of completion of the works for which bids are invited.  Note: *the statements in Section IV showing the value of existing commitments of on-going works as well as the stipulated period of completion remaining for each of the works listed should be countersigned by the Engineer in charge, not below the rank of an Executive Engineer or equivalent.* | | | | | | |
| **2.4.2 (e)** | | Even though the bidders may meet the above qualifying criteria, they are subject to be disqualified if they have: -   * + made misleading or false representations in the forms, statements, affidavits, and attachments submitted in proof of the qualification requirement;   + record of poor performance such as abandoning the works, not properly completion or financial failures etc.   + consistent history of litigation or arbitration awards against the bidder or any member or the joint venture.   + Participated in the previous bidding (if this is a re-bidding) for the same work and had quoted unreasonably high bid price and could not furnish any rational justification for the same to the Employer. | | | | | | |
|  | |  | | | | | | |

2.5 Personnel

The Bidder must demonstrate that it will have the personnel for the key positions that meet the following requirements:

*[Specify requirements for each lot as applicable]*

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| S. No. | Designation of Personnel (Position) | No. | Minimum Qualification | Minimum years of experience | Minimum experience in similar works. |
| 1.  2.  3.  4.  xx | Environment, Health and Safety Engineer |  | Graduate in Civil or Environmental Engineering with specialization and/or additional qualification in Occupational Health and Safety. | *[7]* |  |

*[Indicate designation, qualification, and experience required for each position. Bidder should furnish Curriculum Vitae to confirm their meeting the requirements].*

The Bidder must not have in his employment:

[i] the near relations (defined as first blood relations, and their spouses, of the bidder or the bidder’s spouse) of persons of the following Government Departments.

……………………..

……………………..

………………….….

[ii] without Government permission, any person who retired as gazetted officer within the last two years.

The Bidder shall provide details of the proposed personnel and their experience records in the relevant Forms included in Section IV, Bidding Forms.

Note:

*The managerial and technical competence of a contractor is largely related to the key personnel on site. The extent to which the Bidder should demonstrate having staff with extensive experience should be limited to those requiring critical operational or technical skills. The criteria should therefore refer to a limited number of such key personnel, for instance, the project or contract manager and others working under the project manager who will be responsible for major components (e.g., specialized in dredging, piling, earthworks, environmental, health and safety, or social issues, as required for each particular project). Criteria of acceptability should be based on:*

*(a) a minimum number of years of experience in a similar position; and*

*(b) a minimum number of years of experience and/or number of comparable projects carried out in a specified number of preceding years.*

*The requirement of specified education and academic qualifications is normally unnecessary for such positions, as contractors often employ competent staff who have learned their profession “on the job” rather than through academic training. It is appropriate to specify that certain positions are filled by individuals who have held posts of comparable authority for, say, three years with the Bidder, so that key staff in executive site positions have sufficient knowledge of the Bidder's management, policy, procedures, and practices to act with confidence and authority within that framework.*

2.6 Equipment

The Bidder must demonstrate that it will have access to the key Contractor’s equipment listed hereafter:

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **Equipment Type and Characteristics** | **Capacity** | **Minimum Number required** |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
|  |  |  |  |
|  |  |  |  |

*[NOTE:*

#### *Based on the studies, carried out by the Project Manager the minimum suggested major equipment to attain the completion of works in accordance with the prescribed construction schedule is shown in the above list. The bidders should, however, undertake their own studies and furnish with their bid, a detailed construction planning and methodology supported with layout and necessary drawings and calculations (detailed) as stated in Section IV to allow the employee to review their proposals. The numbers, types and capacities of each plant/equipment shall be shown in the proposals alongwith the cycle time for each operation for the given production capacity to match the requirements.]*

The Bidder shall provide further details of proposed items of equipment using the relevant Form in Section IV.

**2. Financial Part**

2.1 Multiple Contracts if permitted under ITB 35.3, will be evaluated as under.

If works are grouped in multiple contracts pursuant to Sub-Clause 35.3 of the Instructions to Bidders, the Employer will evaluate and compare Bids on the basis of a contract, or a combination of contracts, or as a total of contracts in order to arrive at the least cost combination for the Employer by taking into account discounts offered by Bidders in case of award of multiple contracts, subject to the selected Bidder(s) meeting the required qualification criteria for lot or combination of lots as the case may be.

**2.2 Other Criteria** (if permitted under ITB 35.1 (f)

In addition to the criteria listed in ITB 35.1 (a) – (e) the following criteria shall apply:

Section IV - Bidding Forms

Letter of Bid – Technical Part

|  |
| --- |
| *The Bidder must prepare the Letter of Bid on stationery with its letterhead clearly showing the Bidder’s complete name and address.*  ***Note: All italicized text is for use in preparing these forms and shall be deleted from the final products.*** |

Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Invitation for Bid No.: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

To: ***(Insert name of the Employer)***

We, the undersigned, hereby submit our bid, in two parts, namely:

1. the Technical Part, and
2. the Financial Part

In submitting our Bid, we make the following declarations:

1. We have examined and have no reservations to the Bidding Documents, including Addenda issued in accordance with Instructions to Bidders (ITB 8);
2. We meet the eligibility requirements and have no conflict of interest in accordance with ITB 4;
3. We offer to execute in conformity with the Bidding Documents the following Works: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_;
4. Our bid shall be valid for a period of \_\_\_\_\_\_\_\_ ***[insert validity period as specified in ITB 18.1****.]* days from the date fixed for the bid submission deadline in accordance with the Bidding Documents, and it shall remain binding upon us and may be accepted at any time before the expiration of that period;
5. We accept the appointment of ***[insert name proposed in Bid Data Sheet****]* as the Adjudicator/Dispute Review Expert

***[or]***

We do not accept the appoint of *[****insert name proposed in Bid Data Sheet****]* as he Adjudicator/Dispute Review Expert, and propose instead that *[****insert name****]* be appointed[[10]](#footnote-10) as Adjudicator/Dispute Review Expert, whose daily fees and biographical data are attached;

1. If our bid is accepted, we commit to obtain a performance security in accordance with the Bidding Document;
2. We are not participating, as a Bidder, in more than one bid in this bidding process in accordance with ITB 4.2,
3. Our firm, its affiliates or subsidiaries, including any Subcontractors or Suppliers for any part of the contract, has not been declared ineligible by the Bank, under the Employer’s country laws or official regulations or by an act of compliance with a decision of the United Nations Security Council (ITB 4.7);
4. We are not a government owned entity / We are a government owned entity but meet the requirements of ITB 4.5[[11]](#footnote-11);
5. We hereby certify that we have taken steps to ensure that no person acting for us or on our behalf will engage in any type of fraud and corruption.
6. We also undertake that, in competing for (and, if the award is made to us, in executing) the above contract, we will strictly observe the laws against fraud and corruption in force in India on date namely “Prevention of Corruption Act 1988.”
7. We understand that this bid, together with your written acceptance thereof included in your notification of award, shall constitute a binding contract between us, until a formal contract is prepared and executed;
8. We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive; and
9. If awarded the contract, the person named below shall act as Contractor’s Representative: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

|  |  |
| --- | --- |
|  | Name of the Bidder**\*** ***[insert complete name of person signing the Bid]***  Name of the person duly authorized to sign the Bid on behalf of the Bidder***\*\* [insert complete name of person duly authorized to sign the Bid]***  Title of the person signing the Bid ***[insert complete title of the person signing the Bid]***  Signature of the person named above  *[****insert signature of person whose name and capacity are shown above****]*  Date signed ***[insert date of signing]*** day of ***[insert month]***, ***[insert year]***  **\***: In the case of the Bid submitted by joint venture specify the name of the Joint Venture as Bidder  \*\*: Person signing the Bid shall have the power of attorney given by the Bidder to be attached with the Bid Schedules. |
|  |  |

Technical Proposal

Technical Proposal Forms

* **Site Organization**
* **Method Statement**
* **Mobilization Schedule**
* **Construction Schedule**
* **ESHS Management Strategies and Implementation Plans**
* **Code of Conduct (ESHS)**
* **Equipment**
* **Personnel**
* **Sub-contracting elements or works which in aggregate adds to more than 10% of Bid price (*for each the qualifications and experiences on the identified subcontractor in the relevant field should be given.***
* ***Note: Work should not be split into small parts and sub-contracted; but sub-contracting specialized elements of works is acceptable*.**
* **Others**
* ***Form of Bid Security - Bank Guarantee***

Appendix to Technical Part

Technical Proposal – Site Organization

*[Insert Site Organization information]*

Technical Proposal – Method Statement

*[insert method Statement – A detailed note should be submitted outlining bidders proposed methodology and program of construction including Environmental Management Plan, backed with equipment, materials and manpower planning and deployment, duly supported with broad calculations and quality control system/assurance procedures proposed to be adopted, justifying their capability of execution and completion of the work as per technical specifications within the stipulated review of completion as per mile stones]*

Technical Proposal – Mobilization Schedule

*[Insert Mobilization Schedule]*

Technical Proposal – Construction Schedule

*[Insert Construction Schedule]*

Technical Proposal – Sub Contracting

*[Insert proposal of sub-contracting elements of works amounting to more than 10% of the bid price for each element and indicate the name of the sub-contractor, its qualifications and experiences to execute that element satisfactorily]*

Appendix to Technical Part

ESHS Management Strategies and Implementation Plans

(ESHS-MSIP)

#### ***[Note to Employer: modify the text in italics in the numbered points below, to name the appropriate documents.]***

#### The Bidder shall submit comprehensive and concise Environmental, Social, Health and Safety Management Strategies and Implementation Plans (ESHS-MSIP) as required by ITB 11.2 (j) of the Bid Data Sheet. These strategies and plans shall describe in detail the actions, materials, equipment, management processes etc. that will be implemented by the Contractor, and its subcontractors.

#### In developing these strategies and plans, the Bidder shall have regard to the ESHS provisions of the contract including those as may be more fully described in the following:

#### *[the Works Requirements described in Section VII];*

#### *[Environmental and Social Impact Assessment (ESIA)];*

#### *[Environmental and Social Management Plan (ESMP)];*

#### *[Resettlement Action Plan (RAP)];*

#### *[Consent Conditions (regulatory authority conditions attached to any permits or approvals for the project)]; and*

#### *[specify any other relevant document/s]*

Code of Conduct: Environmental, Social, Health and Safety (ESHS)

#### ***[Note to Employer: modify the text in italics in the numbered points below, to name the appropriate documents.]***

#### The Bidder shall submit the Code of Conduct that will apply to the Contractor’s employees and subcontractors as required by ITB 11.2 (j) of the Bid Data Sheet. The Code of Conduct shall ensure compliance with the ESHS provisions of the contract, including those as may be more fully described in the following:

#### *[the Works Requirements described in Section VII];*

#### *[Environmental and Social Impact Assessment (ESIA)];*

#### *[Environmental and Social Management Plan (ESMP)];*

#### *[Consent Conditions (regulatory authority conditions attached to any permits or approvals for the project)]; and*

#### *[specify any other relevant document*/s]

#### In addition, the Bidder shall submit an outline of how this Code of Conduct will be implemented. This will include: how it will be introduced into conditions of employment/engagement, what training will be provided, how it will be monitored and how the Contractor proposes to deal with any breaches.

Appendix to Technical Part

Forms for Personnel

**Form PER – 1: Proposed Personnel**

Bidders should provide the names of suitably qualified personnel to meet the specified requirements for each of the positions listed in Section III (Evaluation and Qualification Criteria). The data on their experience should be supplied using the Form below for each candidate.

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. | Position | Name | Qualification | Years of Experience | Years of Experience in proposed position | | | |
|  |  |  |  |  | Road \* works | Building\* works | Others\* | Total |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |

*(\* Modify this as appropriate to suit the works for which bids are invited).*

Appendix to Technical Part

**Form PER – 2: Resume of Proposed Personnel**

The Bidder shall provide all the information requested below. Fields with asterisk (\*) shall be used for evaluation.

|  |  |  |
| --- | --- | --- |
| **Position\*** | | |
| **Personnel information** | **Name \*** | **Date of birth** |
|  | **Professional qualifications** | |
| **Present employment** | **Name of** Employer | |
|  | **Address of** Employer | |
|  | **Telephone** | **Contact (manager / personnel officer)** |
|  | **Fax** | **E-mail** |
|  | **Job title** | **Years with present** Employer |

Summarize professional experience in reverse chronological order. Indicate particular technical and managerial experience relevant to the project.

|  |  |  |
| --- | --- | --- |
| From\* | To\* | Company, Project , Position, and Relevant Technical and Management Experience\* |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

Appendix to Technical Part

Form for Equipment

The bidder shall provide adequate information to demonstrate clearly that it has the capability to meet the requirements for the key equipment listed in Section III (Evaluation and Qualification Criteria). The Bidder shall provide all the information requested below.

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. | Item of Equipment | Description | Make | Capacity | Age (years) | Condition | No. available and present location | Owned | Leased | Purchased |
|  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |

Appendix to Technical Part

Form SC-Sub Contracting

SCHEDULE OF SUBCONTRACTORS

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Item | Element of work | Approximate value of sub-contract | % of bid price | Name and address of sub-contractor | Qualification and experience of sub-contractor on similar works of the elements executed |
|  |  |  |  |  |  |

The Bidder shall enter in this schedule a list of the major sections and appropriate value of the work for which he proposes to use subcontractors [*for those costing more than 10% of the bid price for each element], together with the names, addresses and experiences of the proposed subcontractors.*

The capability of the sub-contractor will also be assessed (on the same lines as for the main Contractor) before according approval to him.

*(Work should not be split into small parts and sub-contracted; but, sub-contracting specialized elements of works is acceptable).*

Appendix to Technical Part

Bidder’s Qualification

To establish its qualifications to perform the contract in accordance with Section III (Evaluation and Qualification Criteria) the Bidder shall provide the information requested in the corresponding Information Sheets included hereunder

Appendix to Technical Part

**Form-ELI -1.1: Bidder Information Form**

Date: *[insert day, month, year]*

NCB No. and title: *[insert NCB number and title]*

Page *[insert page number]* of *[insert total number]* pages

|  |  |  |  |
| --- | --- | --- | --- |
| **1.1 Bidder Information** | | | |
| Bidder’s legal name |  |  |  |
| In case of JV, legal name of each member |  |  |  |
| Bidder’s country of constitution |  |  |  |
| Bidder’s year of constitution |  |  |  |
| Bidder’s legal address in country of constitution |  |  |  |
| Bidder’s authorized representative  (name, address, telephone numbers, fax numbers, e-mail address) |  |  |  |
| Attached are copies of the following original documents.   1. In case of single entity, articles of incorporation or constitution of the legal entity names above, in accordance with ITB 4.1.1 and 4.3. 2. Authorization to represent the firm or JV named in above, in accordance with ITB 20.2. 3. In case of JV, letter of intent to form JV or JV agreement: in accordance with ITB 4.1.2 read with BDS 4. In case of government-owned entity, documents establishing legal and financial authority and compliance with the principles of commercial law in accordance with ITB 4.5 read with Sub-clause 2.1.4 of Qualification Criteria. 5. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership. | | | |

**Appendix to Technical Part**

**Form-ELI -1.2: JV Information Form**

(Where permitted as per BDS ITB 4.1.1)

*Each member of a JV must fill in this form*

*Date: [insert day, month, year]*

*NCB No. and title: [insert NCB number and title]*

*Page [insert page number] of [insert total number] pages*

|  |  |  |  |
| --- | --- | --- | --- |
| **JV/Specialist Subcontractor Information** | | | |
| Bidder’s legal name |  |  |  |
| JV Member’s or Subcontractor’s legal name |  |  |  |
| JV Member’s or Subcontractor’s country of constitution |  |  |  |
| JV Member’s or Subcontractor’s year of constitution |  |  |  |
| JV Member’s or Subcontractor’s legal address in country of constitution |  |  |  |
| JV Member’s or Subcontractor’s authorized representative information  (name, address, telephone numbers, fax numbers, e-mail address) |  |  |  |
| Attached are copies of the following original documents.   1. Articles of incorporation or constitution of the legal entity named above, in accordance with ITB 4.1.1 read with BDS and ITB 4.1.2. 2. Authorization to represent the firm names above, in accordance with ITB 20.2. 3. In the case of government-owned entity, documents establishing legal and financial autonomy and compliance with commercial law, in accordance with ITB Sub-Clause 4.5 read with Sub-Clause 2.1.4 of Qualification Criteria. 4. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership. | | | |

**Appendix to Technical Part**

**DETAILS OF PARTICIPATION IN THE JOINT VENTURE**

|  |  |  |  |
| --- | --- | --- | --- |
| **PARTICIPATION DETAILS** | **FIRM ‘A’**  **(Lead Member)** | **FIRM ‘B’** | **FIRM ‘C’** |
| Financial |  |  |  |
| Name of the Banker(s) |  |  |  |
| Planning |  |  |  |
| Construction Equipment |  |  |  |
| Key Personnel |  |  |  |
| Execution of Work (Give details on proposed contribution of each) |  |  |  |

The Joint Venture should indicate the details of participation as above.

**Appendix to Technical Part**

**Form CON – 2**

Historical Contract Non-Performance, Pending Litigation and Litigation History

*[The following table shall be filled in for the Bidder and for each member of a Joint Venture]*

*Bidder’s* Name: *[insert full name]*Date: *[insert day, month, year]*Joint Venture Party Name:*[insert full name]*NCB No. and title: *[insert NCB number and title]*Page *[insert page number]* of *[insert total number]* pages

|  |  |  |  |
| --- | --- | --- | --- |
| Non-Performed Contracts in accordance with Section III, Qualification Criteria and  Requirements | | | |
| 🞎 Contract non-performance did not occur during the (*number)* years specified in Section III, Qualification Criteria and Requirements, Sub-Factor 2.2.1.  🞎 Contract(s) not performed during the *(number)*of years specified in Section III, Qualification Criteria and Requirements, requirement 2.2.1 | | | |
| **Year** | **Non- performed portion of contract** | **Contract Identification** | **Total Contract Amount (in Indian Rupees)** |
| *[insert year]* | *[insert amount and percentage]* | Contract Identification: *[indicate complete contract name/ number, and any other identification]*  Name of Employer: *[insert full name]*  Address of Employer: *[insert street/city/country]*  Reason(s) for non-performance: *[indicate main reason(s)]* | *[insert amount]* |
| Pending Litigation, in accordance with Section III, Qualification Criteria and Requirements | | | |
| 🞎 No pending litigation in accordance with Section III, Qualification Criteria and Requirements, Sub-Factor 2.2.3. | | | |
| 🞎 Pending litigation in accordance with Section III, Qualification Criteria and Requirements, Sub-Factor 2.2.3 as indicated below. | | | |

|  |  |  |  |
| --- | --- | --- | --- |
| **Year of dispute** | **Amount in dispute (Rupees)** | **Contract Identification** | **Total Contract Amount (Rupees)** |
| *[insert year]* | *[insert amount]* | Contract Identification: [indicate complete contract name, number, and any other identification]  Name of Employer: *[insert full name]*  Address of Employer: *[insert street/city/country]*  Matter in dispute: *[indicate main issues in dispute]*  Party who initiated the dispute: *[indicate “Employer” or “Contractor”]*  Status of dispute: *[Indicate if it is being treated by the Adjudicator, under Arbitration or being dealt with by the Judiciary]* | *[insert amount]* |
| 🞎 No pending litigation in accordance with Section III, Qualification Criteria and Requirements, Sub-Factor 2.2.3.  🞎 Pending litigation in accordance with Section III, Qualification Criteria and Requirements, Sub-Factor 2.2.3 as indicated below. | | | |
| **Year of award** | **Outcome as percentage of Net Worth** | **Contract Identification** | **Total Contract Amount (Rupees)** |
| *[insert year]* | *[insert percentage]* | Contract Identification: [indicate complete contract name, number, and any other identification]  Name of Employer: *[insert full name]*  Address of Employer: *[insert street/city/country]*  Matter in dispute: *[indicate main issues in dispute]*  Party who initiated the dispute: *[indicate “Employer” or “Contractor”]*  Status of dispute: *[Indicate if it is being treated by the Adjudicator, under Arbitration or being dealt with by the Judiciary]* | *[insert amount]* |

**Appendix to Technical Part**

Form CON – 3:

**ESHS Performance Declaration**

*[The following table shall be filled in for the Bidder, each member of a Joint Venture and each Specialized Subcontractor]*

Bidder’s Name: *[insert full name]*Date: *[insert day, month, year]*Joint Venture Member’s or Specialized Subcontractor’s Name: *[insert* *full name]*RFB No. and title: *[insert RFB number and title]*Page *[insert page number]* of *[insert total number]* pages

|  |  |  |  |
| --- | --- | --- | --- |
| Environmental, Social, Health, and Safety Performance Declaration  in accordance with Section III, Qualification Criteria, and Requirements | | | |
| 🞎 **No suspension or termination of contract**: An employer has not suspended or terminated a contract and/or called the performance security for a contract for reasons related to Environmental, Social, Health, or Safety (ESHS) performance since the date specified in Section III, Qualification Criteria, and Requirements, Sub-Factor 2.5.  🞎 **Declaration of suspension or termination of contract**: The following contract(s) has/have been suspended or terminated and/or Performance Security called by an employer(s) for reasons related to Environmental, Social, Health, or Safety (ESHS) performance since the date specified in Section III, Qualification Criteria, and Requirements, Sub-Factor 2.5. Details are described below: | | | |
| **Year** | **Suspended or terminated portion of contract** | **Contract Identification** | **Total Contract Amount (current value, currency, exchange rate and US$ equivalent)** |
| *[insert year]* | *[insert amount and percentage]* | Contract Identification: *[indicate complete contract name/ number, and any other identification]*  Name of Employer: *[insert full name]*  Address of Employer: *[insert street/city/country]*  Reason(s) for suspension or termination: *[indicate main reason(s)]* | *[insert amount]* |
| *[insert year]* | *[insert amount and percentage]* | Contract Identification: *[indicate complete contract name/ number, and any other identification]*  Name of Employer: *[insert full name]*  Address of Employer: *[insert street/city/country]*  Reason(s) for suspension or termination: *[indicate main reason(s)]* | *[insert amount]* |
| *…* | *…* | *[list all applicable contracts]* | *…* |
| **Performance Security called by an employer(s) for reasons related to ESHS performance** | | | |
| Year | Contract Identification | | Total Contract Amount (current value, currency, exchange rate and US$ equivalent) |
| *[insert year]* | Contract Identification: *[indicate complete contract name/ number, and any other identification]*  Name of Employer: *[insert full name]*  Address of Employer: *[insert street/city/country]*  Reason(s) for calling of performance security: *[indicate main reason(s)]* | | *[insert amount]* |
|  |  | |  |

**Appendix to Technical Part**

Financial Situation

**FORMAT 3.1 Historical Financial Performances**

Bidder’s Legal Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

JV Member Legal Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Bidding No.: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Page \_\_\_\_\_\_\_ of \_\_\_\_\_\_\_ pages

To be completed by the Bidder and, if JV, by each member

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **SUMMARY OF FINANCIAL STATEMENTS**  **Name of bidder/JV Member:** | | | | | | | |
|  | **(Equivalent Rs. Million)** | | | | | | | |
|  | **S. No.** | **Financial Information in Rupee equivalent with exchange rate at the end of concerned year** | **Actuals for Previous five years excluding the current financial year** | | | | | **Ref. of Page Nos. of Balance Sheets** |
|  | (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |
|  | 1.  2.  3.  4.  5.  6.  7.  8.  9.  10.  11.  12.  13.  14. | Total Assets  Total Turnover  Current Assets  Current Assets + Loan & Advances  Total Liabilities  Current Liabilities  Current liabilities & provision  Profit before Interest and Tax  Profit before Tax  Profit after Tax  Shareholder’s Funds (Net Worth)=(Paid up equity +Reserves)-(revaluation reserves + Miscellaneous expenditure not written off)  Depreciation  Current Ration (2)/(5)  Net cash accruals= Profit after Tax + depreciation |  |  |  |  |  |  |
| This information should be extracted from the Annual Financial Statements/ Balance sheets, which should be enclosed. Year 1 will be the latest year for which audited financial statements are available. Year 2 shall be the year immediately preceding year 1 and year 3 shall be the year immediately preceding Year 2. | | | | | | | | |

**2. Financial documents**

The Bidder and its parties shall provide copies of the balance sheets and/or financial statements for *[number]* years pursuant Section III, Qualifications Criteria and Requirements, Sub-factor 2.3.1. The financial statements shall:

(a) reflect the financial situation of the *Bidder* or member to a JV, and not sister or parent companies.

1. (b) be audited by a certified Chartered Accountant.
2. (c) be complete, including all notes to the financial statements.

(d) Correspond to accounting periods already completed and audited (no statements for partial periods shall be requested or accepted).

* Attached are copies of financial statements (balance sheets, including all related notes, and income statements) for the *[number]* years required above; and complying with the requirements (If the most recent set of financial statements is for a period earlier than 12 months from the date of bid, the reason for this should be justified)
* Attached is a copy of certificate given from the commercial bank assuring cash flow (working capital for contraction) in the format attached.

**Appendix to Technical Part**

**FORM FIN – 3.1(A)**

**FORMAT FOR EVIDENCE OF ACCESS TO OR AVAILABILITY OF CASH FLOW**

[To be given from a Nationalized or Scheduled Bank in India-No substitute other than this will be acceptable)]

**Clause 2.3.1(b) of Section II – Qualification Criteria**

**(1) AVAILABILITY OF CASH FLOW (WORKING CAPITAL)**

This is to certify that M/s. \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ is a reputed company with a good financial standing.

If the contract for the works, namely \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ [funded by the World Bank] is awarded to the above firm, we shall be able to provide overdraft/credit facilities to the extent of Rs. \_\_\_\_\_\_\_ to meet their capital requirements for executing the above contract.

-- Sd. --

Name of Bank Manager

Senior Bank Manager

Address of the Bank

|  |
| --- |
| **\* Change the text as follows for Joint venture:**  *This is to certify that M/s. ………………………………. who has formed a JV with M/s. ………………………….. and M/s. …………………………….. for participating in this bid, is a reputed company with a good financial standing.*  *If the contract for the work, namely …………………………………………………………. [funded by the World Bank] is awarded to the above Joint Venture, we shall be able to provide overdraft/credit facilities to the extent of Rs. …………… to meet the working capital requirements for executing the above contract.*  *[This should be given by the JV members in proportion to their financial participation.]* |

**Appendix to Technical Part**

**Form FIN - 3.2**

Annual Construction Turnover

*[The following table shall be filled in for the Bidder and for each member of a Joint Venture]*

*Bidder*'s/Joint Venture Member's Legal Name: *[insert full name]*Date: *[insert day, month, year]*JV Party Legal Name: *[insert full name]*NCB No. and title: *[insert NCB number and title]*Page *[insert page number]*of *[insert total number]*pages

|  |  |  |
| --- | --- | --- |
| **Annual turnover data (construction only)\*** | | |
| **Year** | **Amount in Rupees** |  |
| *[indicate year]* | *[insert amount]* |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

\* ***Annual construction turnover calculated as total certified payments received for work in progress or completed, for 5 years. Specified in Section III, Qualification Criteria and Requirements, Sub-Factor 2.3.2. This should be certified by a Chartered Accountant*.**

Page …of…..Pages

**Appendix to Technical Part**

**JOINT VENTURE**

|  |
| --- |
| **Names of all members of a joint venture** |
| **1. Member in charge** |
| **2. Member** |
| **3. Member** |

**Total value of annual construction turnover, in terms of work billed to clients, in Rupees**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Annual Turnover Data (construction only; in Rupees \*)** | | | | | | | |
| **Member** | **Form 2 page no.** | **Year 1** | **Year 2** | **Year 3** | **Year 4** | **Year 5** | **Average** |
| **1. Member in charge** |  |  |  |  |  |  |  |
| **2. Member** |  |  |  |  |  |  |  |
| **3. Member** |  |  |  |  |  |  |  |
| **TOTALS** |  |  |  |  |  |  |  |

**\* To be certified by a chartered accountant**

#### 1. **Name and address of Bankers to the Joint Venture**

Provide details regarding financial responsibility and participation (percentage share in the total) of each firm in the Joint Venture. Attach a Memorandum of Understanding for the Proposed Agreement of joint Venture which should lay down responsibility regarding work and financial arrangements in respect of each of the firm in the Joint Venture (Refer also ITB Clause 4.1).

**Appendix to Technical Part**

**Form EXP - 4.1**

General Construction Experience

*[The following table shall be filled in for the Bidder and for each member of a Joint Venture]*

*Bidder*'s/Joint Venture Member's Legal Name: *[insert full name]*Date: *[insert day, month, year]* JV Party Legal Name: *[insert full name]*NCB No. and title: *[insert NCB number]*Page *[insert page number]*of *[insert total number]*pages

*[Identify contracts that demonstrate continuous construction work over the past [5] years pursuant to Section III, Qualification Criteria and Requirements, Sub-Factor 2.4.1. List contracts chronologically, according to their commencement (starting) dates.]*

|  |  |  |  |
| --- | --- | --- | --- |
| Starting  Month /  Year | Ending  Month /  Year | Contract Identification | Role of  *Bidder* |
| *[indicate month/year]* | *[indicate month/year]* | Contract name: *[insert full name]*  Brief Description of the Works performed by the  Bidder: *[describe works performed briefly]*  Amount of contract: *[insert amount in Rupees]*  Name of Employer: *[indicate full name]*  Address: *[indicate street/number/town or city/country]* | *[insert “Contractor” or “Subcontractor” or “Contract Manager”]* |
|  |  | Contract name: *[insert full name]*  Brief Description of the Works performed by the  Bidder: *[describe works performed briefly]*  Amount of contract: *[insert amount in Rupees]*  Name of Employer: *[indicate full name]*  Address: *[indicate street/number/town or city/country]* | *[insert “Contractor” or “Subcontractor” or “Contract Manager”]* |
|  |  | Contract name: *[insert full name]*  Brief Description of the Works performed by the  Bidder: *[describe works performed briefly]*  Amount of contract: *[insert amount in Rupees*  Name of Employer: *[indicate full name]*  Address: *[indicate street/number/town or city/country]* | *[insert “Contractor” or “Subcontractor” or “Contract Manager”]* |

**Appendix to Technical Part**

**Form EXP - 4.2(a)**

Similar Construction Experience

*[The following table shall be filled in for contracts performed by the Bidder, each member of a Joint Venture, and specialist sub-contractors]*

*Bidder*'s/Joint Venture Member's Legal Name: *[insert full name]*Date: *[insert day, month, year]*JV Party Name: *[insert full name]  
N*CB No. and title: *[insert NCB number and title]*

*Page [insert page number] of [insert total number] pages*

* + 1. **Work performed as prime Contractor or Sub-Contractor or Management Contractor** (*in the same name and style*) on construction works of a similar nature and volume over the last five years[[12]](#footnote-12). [*Attach certificate from the Engineer-in-charge.*]

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name | Name of Employer | Description of work | Contract No. | Value of contract | Date of Issue of Work Order | Stipulated Date of Completion | Actual Date of Completion | Remarks explaining reasons for Delay, if any |
|  |  |  |  |  |  |  |  |  |

**Appendix to Technical Part**

**Form EXP - 4.2(b)**

Construction Experience in Key Activities

Bidder’s/ Joint Venture Member’s Legal Name: *[insert full name]* Date: *[insert day, month, year]*

*JV Party Name: [insert full name]*

Nominated Sub-contractor's Legal Name[[13]](#footnote-13) *NCB No. and title: [insert NCB number and title]*

*Page [insert page number] of [insert total number] pages*

**(B) Quantities of work executed as prime contractor or Sub-Contractor** (in the same name and style) in the last five years:[[14]](#footnote-14)

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Year | Name of the Work | Name of the Employer \* | Quantity of Work performed (cum) @ | | | | Remarks \* (indicate contract agreement Ref for each year) |
|  |  |  | Cement Concrete | Masonry | Earth Work | Piling |  |
| 20…20…  20…20…  20…20…  20…20…  20…20… |  |  |  |  |  |  |  |

**@ *the items or work for which date is requested should tally with that specified in Qualification Criteria***

**\* *Attach certificates from Engineer in-charge***

Appendix to Technical Part

Form for Current Contract Commitments/Works in Progress

Bidders and each member to a JV should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued.

(A) Existing commitments and on-going works:

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Description Place Contract No. Name Value of Stipulated Value of works\* Anticipated

of & & Date and Contract period of remaining to be date of

Work State Address (Rupees) completion completed completion

of Employer (Rupees)

(1) (2) (3) (4) (5) (6) (7) (8)

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

(B) Works for which bids already submitted and likely to be awarded – expected additional commitment.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Description Place Name and Estimated Stipulated Date when Remarks

of & Address of value of works period of decision is if any

Work State Employer (Rupees) completion expected

(1) (2) (3) (4) (5) (6) (7)

**\*** *Attach certificate(s) from the Engineer(s)-in-Charge*.

Form…..

**Appendix to Technical Part**

*(Name of the Project)*

**(*Declaration regarding customs/ excise duty exemption for materials/construction equipment bought for the work)***

(*Bidder’s Name and Address*)

To: …………………..

(*Name of the Employer& address*)

Dear Sir:

Re: [*Name of Work*]…………………….

Certificate for Import/Procurement of Goods/Construction Equipment

1. We confirm that we are solely responsible for obtaining customs/excise duty waivers which we have considered in our bid and in case of failure to receive such waivers for reasons whatsoever, the Employer will not compensate us.

2. We are furnishing below the information required by the Employer for issue of the necessary certificates in terms of the Government of India Central Excise Notification No.108/95 read alongwith all subsequent amendments including the amendment dated 01-03-2008 and Customs Notification No. 85/99.

3. The goods/construction equipment for which certificates are required are as under:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Items  *(modify the list suitably for each specific work)* | Make/Brand Name | Capacity [*where applicable*] | Quantity | Value | State whether it will be procured locally or imported *[if so from which country]* | Remarks regarding justification for the quantity and their usage in works. |
| **Goods** | | | | | | |
| [a] Bitumen |  |  |  |  |  |  |
| [b] Cement |  |  |  |  |  |  |
| [c] Steel |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
| **Construction Equipment** | | | | | | |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |

4. We agree that no modification to the above list is permitted after bids are opened.

5. We agree that the certificate will be issued only to the extent considered reasonable by the Employer for the work, based on the Bill of Quantities and the construction program and methodology as furnished by us alongwith the bid.

6. We confirm that the above goods and construction equipment will be exclusively used for the construction of the above work and the construction equipment will not be sold or otherwise disposed of in any manner for a period of five years from the date of acquisition.

Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (*Signature*) \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Place:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (*Printed Name*)\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

(*Designation*)\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

(*Common Seal*) \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

[***This certificate will be issued within 60 days of signing of contract and no subsequent changes will be permitted.*]**

**\* *Modify the above to suit the requirements given in Central Excise/Customs Notification as current of date of bidding.***

**Appendix to Technical Part**

**Form of Bid Security - Bank Guarantee**

*[Guarantor letterhead or SWIFT identifier code]*

Bid Guarantee No…………………….*[insert guarantee reference number]*

Date………………………….*[insert date of issue of the guarantee]*

WHEREAS, \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[name of Bidder][[15]](#footnote-15)* (hereinafter called "the Bidder") has submitted his Bid dated \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[date]* or will submit his Bid for the construction of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[name of Contract]* (hereinafter called "the Bid") under Invitations for Bids No……………………….*[insert number]* (hereinafter called “the IFB”)

KNOW ALL PEOPLE by these presents that We \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[name of bank]* of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[name of country]* having our registered office at \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter called "the Bank") are bound unto \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*[name of Employer]* (hereinafter called "the Employer") in the sum of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_[[16]](#footnote-16) for which payment well and truly to be made to the said Employer the Bank binds itself, his successors and assigns by these presents.

SEALED with the Common Seal of the said Bank this \_\_\_\_\_\_\_\_\_ day of \_\_\_\_\_\_\_\_\_\_ 20\_\_\_\_.

THE CONDITIONS of this obligation are:

(1) If after Bid opening the Bidder (a) withdraws his bid during the period of Bid validity specified in the Letter of Bid; or (b) does not accept the correction of the Bid Price pursuant to ITB 36;

or

(2) If the Bidder having been notified of the acceptance of his bid by the Employer during the period of Bid validity:

(a) fails or refuses to execute the Contract Agreement in accordance with the Instructions to Bidders, if required; or

(b) fails or refuses to furnish the Performance Security, in accordance with the Instruction to Bidders.

we undertake to pay to the Employer up to the above amount upon receipt of his first written demand, without the Employer having to substantiate his demand, provided that in his demand the Employer will note that the amount claimed by him is due to him owing to the occurrence of one or any of the four conditions, specifying the occurred condition or conditions.

This Guarantee will remain in force up to and including the date \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_[[17]](#footnote-17) days after the deadline for submission of Bids as such deadline is stated in the Instructions to Bidders or as it may be extended by the Employer, notice of which extension(s) to the Bank is hereby waived. Any demand in respect of this guarantee should reach the Bank not later than the above date.

DATE \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ SIGNATURE OF THE BANK \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

WITNESS \_\_\_\_\_\_\_\_\_\_\_\_ SEAL \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

[signature, name, and address]

***Note: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.***

**Letter of Bid – Financial Part**

|  |
| --- |
| *The Bidder must prepare the Letter of Bid on stationery with its letterhead clearly showing the Bidder’s complete name and address.*  ***Note: All italicized text is for use in preparing these forms and shall be deleted from the final products.*** |

Date: \_\_\_\_\_\_\_\_\_\_\_\_\_

Invitation for Bid No.: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

To: ***(Insert name of the Employer)***

We, the undersigned, hereby submit the second part of our Bid, the Bid Price and Bill of Quantities. This accompanies the Letter of Technical Part:

In submitting our Bid, we make the following declarations:

1. Our bid shall be valid for a period of \_\_\_\_\_\_\_\_ ***[insert validity period as specified in ITB 18.1****.]* days from the date fixed for the bid submission deadline in accordance with the Bidding Documents, and it shall remain binding upon us and may be accepted at any time before the expiration of that period;
2. The total price of our Bid, excluding any discounts offered in item (c) below is:

-In case of only one lot, total price of the Bid ***[insert the total price of the bid in words and figures]*;**

-In case of multiple lots, total price of each *lot* ***[insert the total price of each lot in words and figures]*;**

-In case of multiple lots, total price of all lots (sum of all lots) ***[insert the total price of all lots in words and figures***;

1. The discounts offered and the methodology for their application are:

(i) The discounts offered are: ***[Specify in detail each discount offered.****]*

(ii) The exact method of calculations to determine the net price after application of discounts is shown below*: [****Specify in detail the method that shall be used to apply the discounts****]*;

1. We have paid, or will pay the following commissions, gratuities, or fees with respect to the bidding process or execution of the Contract:***[[18]](#footnote-18)***

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Recipient |  | Address |  | Reason |  | Amount |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |

|  |  |
| --- | --- |
|  | Name of the Bidder**\*** ***[insert complete name of person signing the Bid]***  Name of the person duly authorized to sign the Bid on behalf of the Bidder***\*\* [insert complete name of person duly authorized to sign the Bid]***  Title of the person signing the Bid ***[insert complete title of the person signing the Bid]***  Signature of the person named above  *[****insert signature of person whose name and capacity are shown above****]*  Date signed ***[insert date of signing]*** day of ***[insert month]***, ***[insert year]***  **\***: In the case of the Bid submitted by joint venture specify the name of the Joint Venture as Bidder  \*\*: Person signing the Bid shall have the power of attorney given by the Bidder to be attached with the Bid Schedules. |
|  |  |

# Appendix to Financial Part

# Bill of Quantities

***Objectives***

*The objectives of the Bill of Quantities are:*

*(a) to provide sufficient information on the quantities of Works to be performed to enable bids to be prepared efficiently and accurately; and*

*(b) when a Contract has been entered into, to provide a priced Bill of Quantities for use in the periodic measurement and valuation of Works executed.*

*In order to attain these objectives, Works should be itemized in the Bill of Quantities in sufficient detail to distinguish between the different classes of Works, or between Works of the same nature carried out in different locations or in other circumstances which may give rise to different considerations of cost. Consistent with these requirements, the layout and contents of the Bill of Quantities should be as simple and brief as possible.*

***Provisional Sums***

*A general provision for physical contingencies (quantity overruns) may be made by including a provisional sum in the Summary Bill of Quantities. Similarly, a contingency allowance for possible price increases should be provided as a provisional sum in the Summary priced Bill of Quantities. Additional provisional sums for ESHS outcomes may also be added, if required. The inclusion of such provisional sums often facilitates budgetary approval by avoiding the need to request periodic supplementary approvals as the future need arises. Where such provisional sums or contingency allowances are used, the Special Conditions of Contract should state the manner in which they shall be used, and under whose authority (usually the Project Manager’s).*

*The estimated cost of specialized work to be carried out, or of special goods to be supplied, by other contractors should be indicated in the relevant part of the Bill of Quantities as a particular provisional sum with an appropriate brief description. A separate procurement procedure is normally carried out by the Employer to select such specialized contractors. To provide an element of competition among the bidders in respect of any facilities, amenities, attendance, etc., to be provided by the successful Bidder as prime Contractor for the use and convenience of the specialist contractors, each related provisional sum should be followed by an item in the Bill of Quantities inviting the Bidder to quote a sum for such amenities, facilities, attendance, etc.*

*These notes for Preparing a Bill of Quantities are intended only as information for the Employer or the person drafting the Bidding Documents. They should not be included in the final documents.*

**Appendix to Financial Part**

**Bill of Quantities**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Rate | |  |
| Serial. No. | Description of item (with brief specification and reference to Book of specification | Quantity | Unit | In figures | In words[[19]](#footnote-19) | Amount[[20]](#footnote-20) |
|  |  |  |  |  |  |  |
| **Total Bid Price (in figures)** | | | | | | |
| **Total Bid Price (in words)** | | | | | | |

**Note:**

1. *Item for which no rate or price has been entered in will not be paid for by the Employer when executed and shall be deemed covered by the other rates and prices in the Bill of Quantities (refer: ITB Clause 14.2 and GCC Clause 41.3)*
2. *Unit rates and prices shall be quoted by the bidder in Indian Rupees [ITB Clause 14.1 and ITB Clause 15.1]*
3. *Where there is a discrepancy between the unit rate and the line item total resulting from multiplying the unit rate by quantity, the unit rate quoted shall govern as explained in ITB Clause 36. [Note: delete this point if the e-procurement system automatically calculates the total from the unit rate and quantity]*
4. *Where there is a discrepancy between the rate in figures and words, the rates in words will govern as explained in ITB Clause 36. [Note: delete this point if the e-procurement system automatically populates the amount in words from the amount in figures]*

Section V - Eligible Countries

**Eligibility for the Provision of Goods, Works and Services in Bank-Financed Procurement**

1. In reference to ITB 4.7, and 5.1, for the information of the Bidders, at the present time firms, goods and services from the following countries are excluded from this bidding process:

Under ITB 4.7 (a) and 5.1 *: None*

Under ITB 4.7 (b) and 5.1 *: None*

Section VI. Bank Policy - Corrupt and Fraudulent Practices

(Section VI shall not be modified)

**Guidelines for Procurement of Goods, Works, and Non-Consulting Services under IBRD Loans and IDA Credits & Grants by World Bank Borrowers, dated January 2011:**

“**Fraud and Corruption:**

1.16 It is the Bank’s policy to require that Borrowers (including beneficiaries of Bank loans), bidders, suppliers, contractors and their agents (whether declared or not), sub-contractors, sub-consultants, service providers or suppliers, and any personnel thereof, observe the highest standard of ethics during the procurement and execution of Bank-financed contracts.[[21]](#footnote-21) In pursuance of this policy, the Bank:

(a) defines, for the purposes of this provision, the terms set forth below as follows:

(i) “corrupt practice” is the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence improperly the actions of another party;[[22]](#footnote-22);

(ii) “fraudulent practice” is any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation;[[23]](#footnote-23)

(iii) “collusive practice” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party;[[24]](#footnote-24)

(iv) “coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party;[[25]](#footnote-25)

(v) “obstructive practice” is

(aa) deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation, or

(bb) acts intended to materially impede the exercise of the Bank’s inspection and audit rights provided for under paragraph 1.16(e) below.

(b) will reject a proposal for award if it determines that the bidder recommended for award, or any of its personnel, or its agents, or its sub-consultants, sub-contractors, service providers, suppliers and/or their employees, has, directly or indirectly, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices in competing for the contract in question;

(c) will declare misprocurement and cancel the portion of the loan allocated to a contract if it determines at any time that representatives of the Borrower or of a recipient of any part of the proceeds of the loan engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices during the procurement or the implementation of the contract in question, without the Borrower having taken timely and appropriate action satisfactory to the Bank to address such practices when they occur, including by failing to inform the Bank in a timely manner at the time they knew of the practices;

(d) will sanction a firm or individual, at any time, in accordance with the prevailing Bank’s sanctions procedures,[[26]](#footnote-26) including by publicly declaring such firm or individual ineligible, either indefinitely or for a stated period of time: (i) to be awarded a Bank-financed contract; and (ii) to be a nominated[[27]](#footnote-27);

(e) will require that a clause be included in bidding documents and in contracts financed by a Bank loan, requiring bidders, suppliers and contractors, and their sub-contractors, agents, personnel, consultants, service providers, or suppliers, to permit the Bank to inspect all accounts, records, and other documents relating to the submission of bids and contract performance, and to have them audited by auditors appointed by the Bank.”

**PART 2 – Works Requirements**

Section VII - Works Requirements

Specifications

A set of precise and clear Specifications is a prerequisite for bidders to respond realistically and competitively to the requirements of the Employer without qualifying or conditioning their bids. The Specifications must be drafted to permit the widest possible competition and, at the same time, present a clear statement of the required standards of workmanship, materials, and performance of the goods and services to be procured. Only if this is done shall the objectives of economy, efficiency, and fairness in procurement be realized, responsiveness of bids be ensured, and the subsequent task of Bid evaluation facilitated. The Specifications should require that all goods and materials to be incorporated in the Works be new, unused, of the most recent or current models, and incorporate all recent improvements in design and materials unless provided otherwise in the Contract.

Samples of Specifications from previous similar projects in India are useful in to prepare Specifications. The use of metric units is encouraged by the World Bank. Most Specifications are normally written specially by the Employer or Project Manager to suit the Contract Works in hand. There is no standard set of Specifications for universal application in all sectors, but there are established principles and practices, which are reflected in these documents.

There are considerable advantages in standardizing General Specifications for repetitive Works in recognized public sectors, such as highways, ports, railways, urban housing, irrigation, and water supply, in the same country or region where similar conditions prevail. The General Specifications should cover all classes of workmanship, materials, and equipment commonly involved in construction, although not necessarily to be used in a particular Works Contract. Deletions or addendums should then adapt the General Specifications to apply them to the particular Works.

Care must be taken in drafting Specifications to ensure that they are not restrictive. In the Specifications of standards for goods, materials, and workmanship, recognized Indian standards should be used as much as possible. Where other particular standards are used, the Specifications should state that goods, materials, and workmanship that meet other authoritative standards, and which ensure substantially equal or higher quality than the standards mentioned, shall also be acceptable. To that effect, the following sample clause may be inserted in the Special Conditions or Specifications.

**“Equivalency of Standards and Codes**

Wherever reference is made in the Contract to specific standards and codes to be met by the goods and materials to be furnished, and work performed or tested, the provisions of the latest current edition or revision of the relevant standards and codes in effect shall apply, unless otherwise expressly stated in the Contract. Where such standards and codes do not relate to Indian Standards, other authoritative standards that ensure a substantially equal or higher quality than the standards and codes specified shall be accepted subject to the Project Manager’s prior review and written consent. Differences between the standards specified and the proposed alternative standards shall be fully described in writing by the Contractor and submitted to the Project Manager at least 28 days prior to the date when the Contractor desires the Project Manager’s consent. In the event the Project Manager determines that such proposed deviations do not ensure substantially equal or higher quality, the Contractor shall comply with the standards specified in the documents.”

The method of measurement of completed work for payment shall be in accordance with ***[insert the name of a standard reference guide, or full details of the methods to be used so that the bidder can take note of that while quoting prices]*.[[28]](#footnote-28)**

*With reference to ESIA/ESMP reports, consent/permit conditions, and WBG ESHS Guidelines, include specific specifications if any, for ESHS working, over and above the requirements of labour and other laws that are applicable to construction industry in India.*

These Notes for Preparing Specifications are intended only as information for the Employer or the person drafting the bidding documents. They should not be included in the final documents.

Drawings

*Insert here a list of Drawings. The actual Drawings, including site plans, should be attached to this section or annexed in a separate folder.*

Supplementary Information

PART 3 – Conditions of Contract and Contract Forms

Section VIII. General Conditions of Contract

These General Conditions of Contract (GCC), read in conjunction with the Particular Conditions of Contract (PCC) and other documents listed therein, should be a complete document expressing fairly the rights and obligations of both parties.

These General Conditions of Contract have been developed on the basis of considerable international experience in the drafting and management of contracts, bearing in mind a trend in the construction industry towards simpler, more straightforward language.

**General Conditions of Contract**

A. General

|  |  |
| --- | --- |
| 1. Definitions | * 1. Boldface type is used to identify defined terms.  1. The Accepted Contract Amount means the amount accepted in the Letter of Acceptance for the execution and completion of the Works and the remedying of any defects. 2. Not used. 3. The Adjudicator or Dispute Review Expert is the person appointed jointly by the Employer and the Contractor to resolve disputes in the first instance, as provided for in GCC 23. 4. Bank means the financing institution **named in the PCC**. 5. Bill of Quantities means the priced and completed Bill of Quantities forming part of the Bid. 6. Compensation Events are those defined in GCC Clause 42 hereunder. 7. The Completion Date is the date of completion of the Works as certified by the Project Manager, in accordance with GCC Sub-Clause 53.1. 8. The Contract is the Contract between the Employer and the Contractor to execute, complete, and maintain the Works. It consists of the documents listed in GCC Sub-Clause 2.3 below. 9. The Contractor is the party whose Bid to carry out the Works has been accepted by the Employer. 10. The Contractor’s Bid is the completed bidding document submitted by the Contractor to the Employer. 11. The Contract Price is the Accepted Contract Amount stated in the Letter of Acceptance and thereafter as adjusted in accordance with the Contract. 12. Days are calendar days; months are calendar months. 13. Not used. 14. A Defect is any part of the Works not completed in accordance with the Contract. 15. The Defects Liability Certificate is the certificate issued by Project Manager upon correction of defects by the Contractor. 16. The Defects Liability Period is the period named in the PCCpursuant to Sub-Clause 34.3 and calculated from the Completion Date. 17. Drawings means the drawings of the Works, as included in the Contract, and any additional and modified drawings issued by (or on behalf of) the Employer in accordance with the Contract, include calculations and other information provided or approved by the Project Manager for the execution of the Contract. 18. The Employer is the party who employs the Contractor to carry out the Works, as **specified in the PCC**. 19. Equipment is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works. 20. “In writing” or “written” means hand-written, type-written, printed or electronically made, and resulting in a permanent record; 21. The Initial Contract Price is the Contract Price listed in the Employer’s Letter of Acceptance. 22. The Intended Completion Date is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is **specified in the PCC**. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order. 23. Materials are all supplies, including consumables, used by the Contractor for incorporation in the Works. 24. Plant is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function. 25. The Project Manager is the person **named in the PCC** (or any other competent person appointed by the Employer and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract. 26. PCC means Particular Conditions of Contract 27. The Site is the area **defined as such in the PCC**. 28. Site Investigation Reports are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site. 29. Specification means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager. 30. The Start Date is **given in the PCC**. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any of the Site Possession Dates. 31. A Subcontractor is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site. 32. Temporary Works are works designed, constructed, installed, and removed by the Contractor that are needed for construction or installation of the Works. 33. A Variation is an instruction given by the Project Manager which varies the Works. 34. The Works are what the Contract requires the Contractor to construct, install, and turn over to the Employer, **as defined in the PCC**. |
| 1. Interpretation | * 1. In interpreting these GCC, words indicating one gender include all genders. Words indicating the singular also include the plural and words indicating the plural also include the singular. Headings have no significance. Words have their normal meaning under the language of the Contract unless specifically defined. The Project Manager shall provide instructions clarifying queries about these GCC.   2. If sectional completion is **specified in the PCC**, references in the GCC to the Works, the Completion Date, and the Intended Completion Date apply to any Section of the Works (other than references to the Completion Date and Intended Completion Date for the whole of the Works).   3. The documents forming the Contract shall be interpreted in the following order of priority:  1. Agreement, 2. Letter of Acceptance, 3. Contractor’s Bid& Priced Bill of Quantities, 4. Particular Conditions of Contract, 5. General Conditions of Contract including Appendices, 6. Specifications, 7. Drawings, and 8. Joint Venture Agreement [where applicable] 9. any other document **listed in the PCC** as forming part of the Contract. |
| 1. Language and Law | * 1. The language of the Contract and the law governing the Contract are **stated in the PCC**.   Salient features of major labour and other laws that are applicable to construction industry in India are given as Appendix 1 to these General Conditions of Contract.   * 1. Throughout the execution of the Contract, the Contractor shall comply with the import of goods and services prohibitions in the India when   (a) as a matter of law or official regulations, India prohibits commercial relations with that country; or  (b) by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, India prohibits any import of goods from that country or any payments to any country, person, or entity in that country. |
| 1. Project Manager’s Decisions | * 1. Except where otherwise specifically stated, the Project Manager shall decide contractual matters between the Employer and the Contractor in the role representing the Employer.   However, if the Project Manager is required, under the rules and regulations and orders of the Employer, to obtain approval of some other authorities for specific actions, he will so obtain the approval. Provided further that any requisite approval shall be deemed to have been given by the Employer for any such authority exercised by the Project Manager. |
| 1. Delegation | * 1. Unless otherwise **specified in the PCC**, the Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator/Dispute Review Expert, after notifying the Contractor, and may revoke any delegation after notifying the Contractor. |
| 1. Communica­tions | * 1. Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. All oral instructions shall be confirmed in writing in seven working days. |
| 1. Subcontracting | * 1. The Contractor may subcontract with the approval of the Project Manager upto a ceiling **specified in PCC**, but may not assign the Contract without the approval of the Employer in writing. Subcontracting shall not alter the Contractor’s obligations.   7.2 The Project Manager should satisfy himself before recommending to the Employer whether:  a) the circumstances warrant such sub-contracting; and,  b) the sub-Contractor so proposed for the Work possesses the experience, qualifications and equipment necessary for the job proposed to be entrusted to him in proportion to the quantum of Works to be sub-contracted.  7.3 If payments are proposed to be made directly to that sub-contractor, this should be subject to specific authorization by the prime contractor so that his arrangement does not alter the contractor’s liability or obligations under the contract.  7.4 The Contractor shall not be required to obtain any consent from the Employer for:  (a) the sub-contracting of any part of the Works for which the Sub-Contractor is already named in the contract;  (b) the provision for labour, or labour component, and,  (c) the purchase of materials which are in accordance with the standards specified in the contract.  (*Note: 1. All bidders are expected to indicate clearly in the bid, if they proposed sub-contracting elements of the works amounting to more than 10 percent of the Bid Price. For each such proposal the qualification and the experience of the identified sub-contractor in the relevant field should be furnished alongwith the bid to enable the Employer to satisfy himself about their qualifications before agreeing for such sub-contracting and include it in the contract. In view of the above, normally no additional sub-contracting should arise during execution of the contract.*  *2. However, [a] sub-contracting for certain specialized elements of the work is not unusual and acceptable for carrying out the works more effectively; but vertical splitting of the works for sub-contracting is not acceptable. [b] in any case, proposal for sub-contracting in addition to what was specified in bid and stated in contract agreement will not be acceptable if the value of such additional sub-contracting exceeds 25% of value of work which was to be executed by Contractor without sub-contracting.*  *3. Assignment of the contract may be acceptable only under exceptional circumstances such as insolvencies/liquidation or merger of companies etc.)* |
| 1. Other Contractors | * 1. The Contractor shall cooperate and share the Site with other contractors, public authorities, utilities, and the Employer between the dates given in the Schedule of Other Contractors, as **referred to in the PCC.** The Contractor shall also provide facilities and services for them as described in the Schedule. The Employer may modify the Schedule of Other Contractors, and shall notify the Contractor of any such modification. |
| 1. Personnel and Equipment | * 1. The Contractor shall employ the key personnel and use the equipment identified in its Bid and **referred to in the PCC**, to carry out the Works or other personnel and equipment approved by the Project Manager. The Project Manager shall approve any proposed replacement of key personnel and equipment only if their relevant qualifications or characteristics are substantially equal to or better than those proposed in the Bid.   9.2 The Project Manager may require the Contractor to remove from the Site of Works, a member of the Contractor’s staff or his work force, who:  (a) persists in any misconduct or lack of care,  (b) carries out duties incompetently or negligently,  (c) fails to conform with any provisions of the Contract, or  (d) persists in any conduct which is prejudicial to safety, health, or the protection of the environment.  9.3 If the Employer, Project Manager or Contractor determines, that any employee of the Contractor be determined to have engaged in corrupt, fraudulent, collusive, coercive, or obstructive practice during the execution of the Works, then that employee shall be removed in accordance with Clause 9.2 above  9.4 In all the above cases, the contractor shall ensure that the person leaves the site within seven days and has no further connection with the work in the contract. The Contractor shall appoint a suitable replacement within 28 days or earlier as may be agreed to between the Project manager and the Contractor.  9.5 The Contractor shall not employ any retired Gazetted officer who has either not completed two years after the date of retirement or has not obtained permission from the Government authorities for employment with the Contractor[[29]](#footnote-29). |
| Compliance with Labour Regulations | 9.6 The Contractor shall, unless otherwise provided in the Contract, make his own arrangements for the engagement of all staff and labour, local or other, and for their payment, housing, feeding and transport. The Contractor shall, if required by the Project Manager, deliver to the Project Manager a return in detail, in such form and at such intervals as the Project Manager may prescribe, showing the staff and the numbers of the several classes of labour from time to time employed by the Contractor on the Site and such other information as the Project Manager may require.  9.7 During continuance of the Contract, the Contractor and his Sub-Contractors shall abide at all times by all existing labour enactments and rules made there under, regulations, notifications and bye laws of the State or Central Government or local authority and any other labour laws (including rules), regulations, bye laws that may be passed or notification that may be issued under any labour law prevailing on the Base Date either by the State or the Central Government or the local authority. The Contractor shall keep the Employer indemnified in case any action is taken against the Employer by the competent authority on account of contraventions including amendments. If the Employer is caused to pay or reimburse, such amounts as may be necessary to cause or observe, or for non-observance of the provisions stipulated in the notifications/bye laws/Acts/Rules/regulations including amendments, if any, on the part of the Contractor, the Project Manager/ Employer shall have the right to deduct any money due to the Contractor including his amount of performance security. The Employer/ Project Manager shall also have right to recover from the Contractor any sum required or estimated to be required for making good the loss or damage suffered by the Employer.  9.8 The employees of the Contractor and the Sub-Contractor in no case shall be treated as the employees of the Employer at any point of time.  9.9 The Contractor shall duly comply with the provisions of the Apprentices Act 1961 (III of 1961) and the rules made there under, and comply, failure or neglect to shall be subject to all liabilities and penalties provided in the said Act and Rules. |
| 1. Employer’s and Contractor’s Risks | * 1. The Employer carries the risks which this Contract states are Employer’s risks, and the Contractor carries the risks which this Contract states are Contractor’s risks. |
| 1. Employer’s Risks | * 1. From the Start Date until the Defects Liability Certificate has been issued, the following are Employer’s risks:  1. The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to    1. use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works or    2. negligence, breach of statutory duty, or interference with any legal right by the Employer or by any person employed by or contracted to him except the Contractor. 2. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Employer or in the Employer’s design, or due to war or radioactive contamination directly affecting the country where the Works are to be executed.    1. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is an Employer’s risk except loss or damage due to 3. a Defect which existed on the Completion Date, 4. an event occurring before the Completion Date, which was not itself an Employer’s risk, or 5. the activities of the Contractor on the Site after the Completion Date. |
| 1. Contractor’s Risks | 12.1 From the Starting Date until the Defects Liability Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) which are not Employer’s risks are Contractor’s risks. |
| 1. Insurance | * 1. The Contractor shall provide, in the joint names of the Employer and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts and deductibles **stated in the PCC** for the following events which are due to the Contractor’s risks:  1. loss of or damage to the Works, Plant, and Materials [which are incorporated in works]; 2. loss of or damage to Construction Equipment; 3. loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and 4. personal injury or death.    1. Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for the Project Manager’s approval before the Start Date. All such insurance shall provide for compensation to be payable in the types and proportions of currencies required to rectify the loss or damage incurred.    2. If the Contractor does not provide any of the policies and certificates required, the Employer may effect the insurance which the Contractor should have provided and recover the premiums the Employer has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due.    3. Alterations to the terms of insurance shall not be made without the approval of the Project Manager.    4. Both parties shall comply with any conditions of the insurance policies. |
| 1. Site Data | * 1. The Contractor shall be deemed to have examined any Site Data **referred to in the PCC**, supplemented by any information available to the Contractor. |
| 1. Contractor to Construct the Works including protection of environment and assurance of public health and safety | * 1. The Contractor shall construct and install the Works in accordance with the Specifications and Drawings and as per instructions of Project Manager.      1. The Contractor shall take all reasonable steps to protect the environment on and off the Site and to avoid damage or nuisance to persons or to property of the public or others resulting from pollution, noise or other cause arising as a consequence of his methods of operation.      2. During continuance of the contract, the contractor and his sub-contractors shall abide at all times by all existing enactments on environmental protection and rules made thereunder, regulations, notifications and by-laws of the Sate or Central Government, or local authorities and other law, bye-law, regulations that may be passed or notification that may be issued in this respect in future by the State or Central Government or the local authority. Salient features of the major laws are given in Appendix 1 to the General Conditions of Contract. |
| 1. The Works to Be Completed by the Intended Completion Date | * 1. The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| 1. Approval by the Project Manager | * 1. The Contractor shall submit Specifications and Drawings showing the proposed Temporary Works to the Project Manager, for his approval.   2. The Contractor shall be responsible for design of Temporary Works.   3. The Project Manager’s approval shall not alter the Contractor’s responsibility for design of the Temporary Works.   4. The Contractor shall obtain approval of third parties to the design of the Temporary Works, where required.   5. All Drawings prepared by the Contractor for the execution of the temporary or permanent Works, are subject to prior approval by the Project Manager before this use. |
| 1. Safety | * 1. The Contractor shall be responsible for the safety of all activities on the Site. |
| 1. Discoveries | * 1. Anything of historical or other interest or of significant value unexpectedly discovered on the Site shall be the property of the Employer. The Contractor shall notify the Project Manager of such discoveries and carry out the Project Manager’s instructions for dealing with them. |
| 1. Possession of the Site | * 1. The Employer shall give possession of all parts of the Site to the Contractor. If possession of a part is not given by the date **stated in the PCC,** the Employer shall be deemed to have delayed the start of the relevant activities, and this shall be a Compensation Event. |
| 1. Access to the Site | * 1. The Contractor shall allow the Project Manager and any person authorized by the Project Manager access to the Site and to any place where work in connection with the Contract is being carried out or is intended to be carried out. |
| 1. Instructions, Inspections and Audits | * 1. The Contractor shall carry out all instructions of the Project Manager which comply with the applicable laws where the Site is located.   22.2 The Contractor shall keep, and shall make all reasonable efforts to cause its Subcontractors and sub-consultants to keep, accurate and systematic accounts and records in respect of the Works in such form and details as will clearly identify relevant time changes and costs.  22.3 The Contractor shall permit and shall cause its Subcontractors and sub-consultants to permit, the Bank and/or persons appointed by the Bank to inspect the Site and/or the accounts and records relating to the performance of the Contract and the submission of the bid, and to have such accounts and records audited by auditors appointed by the Bank if requested by the Bank. The Contractor’s and its Subcontractors’ and sub-consultants’ attention is drawn to Sub-Clause 25.1 which provides, inter alia, that acts intended to materially impede the exercise of the Bank’s inspection and audit rights provided for under Sub-Clause 22.2 constitute a prohibited practice subject to contract termination (as well as to a determination of ineligibility pursuant to the Bank’s prevailing sanctions procedures). |
| 1. Appointment of the Adjudicator or Dispute Review Expert | * 1. The Adjudicator/Dispute Review Expert [DRE] named in PCC shall be appointed jointly by the Employer and the Contractor, at the time of the Employer’s issuance of the Letter of Acceptance. If, in the Letter of Acceptance, the Employer does not agree on the appointment of the Adjudicator/DRE, the Employer will request the Appointing Authority **designated in the PCC**, to appoint the Adjudicator/DRE within 14 days of receipt of such request.   23.1.1 The Adjudicator/DRE should be in position before “notice to proceed with work” is issued to the Contractor and an agreement should be signed with the Adjudicator/DRE jointly by the Employer and the Contractor in the form attached – Appendix 3.   * 1. Should the Adjudicator/DRE resign or die, or should the Employer and the Contractor agree that the Adjudicator/DRE is not functioning in accordance with the provisions of the Contract; a new Adjudicator/DRE shall be jointly appointed by the Employer and the Contractor. In case of disagreement between the Employer and the Contractor, within 30 days, the Adjudicator/DRE shall be designated by the Appointing Authority **designated in the PCC** at the request of either party, within 14 days of receipt of such request. |
| 1. Procedure for Disputes   25. Corrupt And Fraudulent Practices | * 1. If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator/DRE within 14 days of the notification of the Project Manager’s decision.   2. The Adjudicator/DRE shall give a decision in writing within 28 days of receipt of a notification of a dispute.   3. The Adjudicator/DRE shall be paid daily at the rate **specified in the PCC,** together with reimbursable expenses of the types **specified in the PCC**, and the cost shall be divided equally between the Employer and the Contractor. Whatever decision is reached by the Adjudicator/DRE, either party may refer that decision to an Arbitrator within 28 days of the Adjudicator’s /DRE’s written decision. If neither party refers the dispute to arbitration within the above 28 days, the Adjudicator’s /DRE’s decision shall be final and binding.   4. The arbitration shall be conducted in accordance with the arbitration procedures published by the institution named and in the place **specified in the PCC.**   The Arbitrator(s) shall give a decision in writing within 120 days of start of the proceedings unless otherwise agreed to by the Parties. The Arbitrators shall entertain only those issues which have been earlier referred to the Adjudicator/Dispute Review Expert and either party is dissatisfied with the decision given by the Adjudicator/Dispute Review Expert.  25.1 The Bank requires compliance with its policy in regard to corrupt and fraudulent practices as set forth in Appendix to the GCC.  25.2 The Employer requires the Contractor to disclose any commissions or fees that may have been paid or are to be paid to agents or any other party with respect to the bidding process or execution of the Contract. The information shall be disclosed as and when such payments are made or agreed to, and compliance with the disclosure requirement shall be furnished, while submitting each monthly statement for payments; such disclosure must include at least the name and address of the agent or other party, the amount and currency, and the purpose of the commission, gratuity or fee. |

B. Time Control

|  |  |
| --- | --- |
| * + 1. 2   **26. Program** | 26.1 Within the time **stated in the PCC**, after the date of the Letter of Acceptance, the Contractor shall submit to the Project Manager for approval a revised Program (revising the program given alongwith the bid) including Environmental Management Plan (to comply with the applicable Laws/ Rules/ Regulations for protection of environment, public health and safety, and the applicable parts of the Environment Management Planof the project) showing the general methods, arrangements, order, and timing for all the activities in the Works alongwith monthly cash flow forecasts.  26.2 An update of the Program shall be a program showing the actual progress achieved on each activity and the effect of the progress achieved on the timing of the remaining work, including any changes to the sequence of the activities.  26.3 The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period **stated in the PCC.** If the Contractor does not submit an updated Program within this period, the Project Manager may withhold the amount **stated in the PCC** from the next payment certificate and continue to withhold this amount until the next payment after the date on which the overdue Program has been submitted.  26.4 The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events.  26.5 The Contractor shall furnish monthly progress reports as directed by the Project Manager by 7th of the succeeding month. The report shall include charts and detailed descriptions of the progress of identified activities, photographs showing status of progress at site, records of Contractor’s personnel and equipment, Quality Assurance documents, comparison of actual and planned progress as per program. This report will also include progress on the ESHS Management Strategies and Implementation Plans (ESHS-MSIP), and compliance to the applicable Laws/ Rules/ Regulations for protection of environment, public health and safety, and the applicable parts of the Environment Management Planof the project. |
| 27. Extension of the Intended Completion Date | 27.1 The Project Manager shall extend the Intended Completion Date including milestones if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date as per agreed milestones without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost.  27.2 The Project Manager shall decide whether and by how much to extend the Intended Completion Date/milestones within 21 days of the Contractor asking the Project Manager for a decision upon the effect of a Compensation Event or Variation and submitting full supporting information. If the Contractor has failed to give early warning of a delay or has failed to cooperate in dealing with a delay, the delay by this failure shall not be considered in assessing the new Intended Completion Date/milestones. |
| 28. Acceleration | 28.1 When the Employer wants the Contractor to finish before the Intended Completion Date, the Project Manager shall obtain priced proposals for achieving the necessary acceleration from the Contractor. If the Employer accepts these proposals, the Intended Completion Date shall be adjusted accordingly and confirmed by both the Employer and the Contractor.  28.2 If the Contractor’s priced proposals for acceleration are accepted by the Employer, they are incorporated in the Contract Price and treated as a Variation. |
| 29. Delays Ordered by the Project Manager | 29.1 The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| 30. Management Meetings | 30.1 Either the Project Manager or the Contractor may require the other to attend a management meeting. (Which will be held at the place **indicated in PCC**. The periodicity to be fixed by Project Manager / Contractor jointly). The business of a management meeting shall be to review the progress of construction with reference to the construction program given in accordance with GCC 26.1, the plans for remaining work and to deal with matters raised in accordance with the early warning procedure.  30.2 The Project Manager shall record the business of management meetings and provide copies of the record to those attending the meeting and to the Employer. The responsibility of the parties for actions to be taken shall be decided by the Project Manager either at the management meeting or after the management meeting and stated in writing to all who attended the meeting. |
| 31. Early Warning | 31.1 The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price, or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible.  31.2 The Contractor shall cooperate with the Project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone involved in the work and in carrying out any resulting instruction of the Project Manager. |

C. Quality Control

|  |  |
| --- | --- |
| 32. Quality Assurance | 32.1 The Contractor shall institute Quality Assurance (QA) and Quality Control (QC) systems in accordance with Quality Assurance Plan to demonstrate compliance with the requirements of the Contract as approved by the Project Manager.  32.2 Compliance with the QA/QC systems shall not relieve the Contractor of any of his duties obligations or responsibilities under the Contract. |
| 33. Tests | 33.1 The Contractor shall provide all apparatus, assistance, documents and other information, electricity, equipment, fuel, consumables, instruments, labour, materials, and suitably qualified and experienced staff, as are necessary to carry out the specified tests efficiently.  33.2 If the Project Manager instructs the Contractor to carry out a test not specified in the Specification to check whether any work has a Defect and the test shows that it does, the Contractor shall pay for the test and any samples. If there is no Defect, the test shall be a Compensation Event. |
| 34. Identifying and Correction of Defects | 34.1. The Project Manager shall check the Contractor’s work and notify the Contractor of any defects that are found specifying a time by which it should be corrected. Such checking shall not affect the Contractor’s responsibilities. The Project Manager may instruct the Contractor to search for a Defect and to uncover and test any work that the Project Manager considers may have a Defect.  34.2 The contractor shall permit the Employer’s Technical auditor to check the contractor’s work and notify the Project Manager and Contractor of any defects that are found. Such a check shall not affect the Contractor’s or the Project Manager’s responsibility as defined in the Contract Agreement  34.3 The Project Manager shall give notice to the Contractor of any Defects [specifying a time limit by which it should be corrected] before the end of the Defects Liability Period, which begins at Completion, and is **defined in the PCC.** The Defects Liability Period shall be extended for as long as Defects remain to be corrected.  34.4 Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| 35. Uncorrected Defects | 35.1 If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager shall assess the cost of having the Defect corrected and the Contractor shall pay this amount.  ***Note: 1. Where in certain cases, the technical specifications provide for acceptance of works within specified tolerance limits at reduced rates, Project Manager will certify payments to Contractor accordingly*.**  ***2. Where the failure to correct a particular defect within the specified time is considered as a fundamental breach of contract a notice should be given to the contractor as stated in GCC 57.2(e).*** |

D. Cost Control

|  |  |
| --- | --- |
| 36. Contract Price | 36.1 The Bill of Quantities shall contain priced items for the Works to be performed by the Contractor. The Bill of Quantities is used to calculate the Contract Price. The Contractor will be paid for the quantity of the work accomplished at the rate in the Bill of Quantities for each item.  . |
| 37. Changes in the Contract Price | 37.1 If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than 25 percent, provided the change exceeds 1 percent of the Initial Contract Price, the Project Manager shall adjust the rate to allow for the change.  (a) If the quantity of work executed exceeds the quantity of the item in BOQ beyond the higher specified limit the Project Manager shall fix the rate to be applied for the additional quantity of the work executed.  (b) If the quantity of work executed less than the quantity of the item in BOQ lesser than the lower specified limit, the Project Manager shall fix the rate to be applied for whole of the quantity of the work so executed.  37.2. The Project Manager shall not adjust rates from changes in quantities if thereby the Initial Contract Price is exceeded by more than 15 percent, except with the prior approval of the Employer.  37.3 If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. |
| 38. Variations | 38.1 All Variations shall be included in updated Programs, produced by the Contractor.  38.2 The Contractor shall provide the Project Manager with a quotation (with breakdown of unit rates) for carrying out the Variation when requested to do so by the Project Manager. The Project Manager shall assess the quotation, which shall be given within seven (7) days of the request or within any longer period stated by the Project Manager and before the Variation is ordered.  38.3 If the work in the Variation corresponds to an item description in the Bill of Quantities and if, in the opinion of the Project Manager, the quantity of work above the limit stated in Sub-Clause 37.1 or the timing of its execution do not cause the cost per unit of quantity to change, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work.  38.4 If the Contractor’s quotation is unreasonable, [*or if contractor fails to provide the Project Manager with a quotation within a reasonable time specified by Project Manager in accordance with GCC38.2*] the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs  38.5 If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event.  38.6 The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |
| 39. Cash Flow Forecasts | 39.1 When the Program, is updated, the Contractor shall provide the Project Manager with an updated cash flow forecast. The cash flow forecast shall be in Indian Rupees. |
| 40. Payment Certificates | 40.1 The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed less the cumulative amount certified previously alongwith details of measurement of the quantity of works executed in a tabular form approved by the Project Manager.  40.2 The Project Manager shall check the details given in the Contractor’s monthly statement and within 14 days certify the amounts to be paid to the Contractor after taking into account any credit or debit for the month in question in respect of materials for the works in the relevant amount and under conditions set forth in GCC Sub-Clause 49.4 *[Secured Advance]*  40.3 The value of work executed shall be determined by the Project Manager after due check measurement of the quantities claimed as executed by the contractor  40.4 The value of work executed shall comprise of the value of the quantities of work in the Bill of Quantities that have been completed;  40.5 The value of work executed shall include the valuation of Variations and Compensation Events.  40.6 The Project Manager may exclude any item certified in a previous certificate or reduce the proportion of any item previously certified in any certificate in the light of later information. |
| 41. Payments | 41.1 Payments shall be adjusted for deductions for advance payments, retention, other recoveries in terms of contract & taxes to be deducted at source [TDS] as per applicable law. The Employer shall pay the Contractor the amounts certified by the Project Manager within 28 days of the date of each certificate. If the Employer makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made upto the date when the late payment is made at the rate **stated in the PCC.**  41.2 If an amount certified is increased in a later certificate or as a result of an award by the Adjudicator/DRE or an Arbitrator, the Contractor shall be paid interest upon the delayed payment as set out in this clause. Interest shall be calculated at the rate stated in GCC 41.1 above, from the date upon which the increased amount would have been certified in the absence of dispute.  41.3 Items of the Works for which no rate or price has been entered in shall not be paid for by the Employer and shall be deemed covered by other rates and prices in the Contract. |
| 42. Compensation Events | 42.1 The following shall be Compensation Events:   1. The Employer does not give access to a part of the Site by the Site Possession Date pursuant to GCC Sub-Clause 20.1. 2. The Employer modifies the Schedule of Other Contractors in a way that affects the work of the Contractor under the Contract. 3. The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. 4. The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. 5. The Project Manager unreasonably does not approve a subcontract to be let. 6. Ground conditions are substantially more adverse than could reasonably have been assumed before issuance of the Letter of Acceptance from the information issued to bidders (including the Site Investigation Reports), from information available publicly and from a visual inspection of the Site. 7. The Project Manager gives an instruction for dealing with an unforeseen condition, caused by the Employer, or additional work required for safety or other reasons. 8. Other contractors, public authorities, utilities, or the Employer does not work within the dates and other constraints stated in the Contract, and they cause delay or extra cost to the Contractor. 9. The advance payment is delayed. 10. The effects on the Contractor of any of the Employer’s Risks. 11. The Project Manager unreasonably delays issuing a Certificate of Completion.   42.2 If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Contract Price shall be increased and/or the Intended Completion Date shall be extended. The Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended.  42.3 As soon as information demonstrating the effect of each Compensation Event upon the Contractor’s forecast cost has been provided by the Contractor, it shall be assessed by the Project Manager, and the Contract Price shall be adjusted accordingly. If the Contractor’s forecast is deemed unreasonable, the Project Manager shall adjust the Contract Price based on the Project Manager’s own forecast. The Project Manager shall assume that the Contractor shall react competently and promptly to the event.  42.4 The Contractor shall not be entitled to compensation to the extent that the Employer’s interests are adversely affected by the Contractor’s not having given early warning or not having cooperated with the Project Manager. |
| 43. Tax | 43.1 The rates quoted by the Contractor shall be deemed to be inclusive of the VAT, Sales and other taxes that the Contractor will have to pay for the performance of this Contract. The Employer will perform such duties in regard to the deduction of such taxes at source [TDS] as per applicable law.  43.2 The Project Manager shall adjust the Contract Price if taxes, duties, and other levies are changed between the deadline for the submission of bids for the Contract and the date of the last Completion certificate. The adjustment shall be the change in the amount of tax payable by the Contractor, provided such changes are not already reflected in the Contract Price. |
| 44. Currencies | 44.1 All payments shall be made in Indian Rupees. |
| 45. Price Adjustment | 45.1 Contract price shall be adjusted for increase or decrease in rates and price of labour, materials, fuels and lubricants and other inputs to the works in accordance with the principles and procedures outlined below. A table of adjustment data is **included in the PCC** which indicates the coefficients of various inputs and the sources of indices for various schedules of BOQ. If the PCC does not include a table of adjustment data this sub clause shall not apply and there shall be no price adjustment.  (a) The price adjustment according to sub para (d) below, shall apply for the work done from the start date given in the PCC upto the end of the Intended Completion Date. If there is delay in completion beyond such date for reasons attributable to the contractor, the Price Adjustment for the work carried out during such period, for reasons attributable to the Contractor, shall be regulated by sub-para (g) below.  (b) The Contract Price shall be adjusted to take account of any increase or decrease in cost after the base date, which affect the Contractor in performance of obligations under the Contract.  (c) The total value (R) of the work done during the specified period [GCC 40.1] shall be as under:  R= SUM (RS1 + RS2 + RS3 + …….RSn),  Where,  ‘Rsn’ is the value of work done during the specified period to which the price adjustment shall be applied for the relevant schedule of Bill of Quantities (BOQ) specified in P.C.C during the specified period, and represented as under:  Rsn = (Vsn + Ssn) minus (amount of secured advance recovered in the same period + value of works executed under variations for which price adjustments will be worked separately based on terms mutually agreed between the Project Manager and the Contractor)  where,  Vsn is the total value of work done during the specified period for the respective schedule of BOQ, and  Ssn is the secured advance paid during the specified period for the respective schedule of BOQ,  (d) The adjustment to be applied to the amount otherwise payable to the Contractor, as valued in accordance with the appropriate schedule of BOQ and certified in Payment Certificates, shall be determined from formulae which shall be of the following general type:  Pn = a + b Ln/Lo +c En/Eo + d Mn/Mo+ ……….  where,  “Pn” is the adjustment multiplier to be applied to the value of the work done during the period “n”, this period being a month unless otherwise stated in the PCC.  “a” is a fixed coefficient, stated in the relevant table of adjustment data, representing the non-adjustable portion in contractual payments;  “b”, “c”, “d”,… are coefficients representing the estimated proportion of each cost element related to the execution of the Works, as stated in the relevant table of adjustment data; such tabulated cost elements may be indicative of resources such as labour, equipment and materials;  “Ln”[*Labour*], “En”[*Equipment*], “Mn”[*Material*], …. are the current cost indices or reference prices for period “n”, each of which is applicable to the relevant tabulated cost element [*Labour, Equipment, Steel, Cement, Fuel/Lubricants, Bitumen, others*] on the date, specified in the Table-2 of Adjustment Data, prior to the last day of the period (to which the particular Payment Certificate relates); and  “Lo”, “Eo”, “Mo”, ….are the base cost indices or reference prices, expressed in the relevant currency of payment, each of which is applicable to the relevant tabulated cost element on the Base Date.  (e) The cost indices or reference prices stated in the tables of adjustment data given in PCC shall be used. The base date shall be the deadline for the submission of bids.  (f) If the Contractor fails to complete the Works within the Intended Completion date, adjustment of prices thereafter shall be made using either:  (i) index or price applicable for each cost element tabulated in the tables of adjustment data on the specified date prior to the expiry of the Intended Completion Date, or  (ii) the current index or price applicable for the period in question whichever is more favourable to the Employer.   1. The weightings (coefficients) for each of the factors of cost stated in the table(s) of adjustment data shall only be varied by the Project Manager if they have been rendered unreasonable, unbalanced or inapplicable, as a result of Variations. 2. Unless otherwise **stated in the P.C.C.**, the Price adjustment shall be done in each monthly Interim Payment Certificate [IPC]. The coefficients and indices are given in the Tables of Adjustment Data in Contract data.   To the extent that full compensation for any rise or fall in costs to the contractor is not covered by the provisions of this or other clauses in the contract, the unit rates and prices included in the contract shall be deemed to include amounts to cover the contingency of such other rise or fall in costs |
| 46. Retention | 46.1 The Employer shall retain from each payment due to the Contractor the proportion **stated in the PCC** until Completion of the whole of the Works  46.2 Upon the issue of a Certificate of Completion of the Works by the Project Manager, in accordance with GCC 53.1, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. On completion of the whole works the Contractor may substitute the balance retention money with an “on demand” Bank guarantee. |
| 47. Liquidated Damages | 47.1 The Contractor shall pay liquidated damages to the Employer at the rate per day **stated in the PCC** for each day that the Completion Date is later than the Intended Completion Date (for the whole of the works or the milestones as stated in the PCC). The total amount of liquidated damages shall not exceed the amount **defined in the PCC.** The Employer may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities.  47.1.1 Time is the essence of the contract and payment or deduction of liquidated damages shall not relieve the contractor from his obligation to complete the work as per agreed construction program and milestones, or from any of the Contractor’s other obligations and liabilities under the contract.  47.2 If the Intended Completion Date including milestones is extended after liquidated damages have been paid, the Project Manager shall correct any overpayment of liquidated damages by the Contractor by adjusting the next payment certificate. The Contractor shall be paid interest on the overpayment, calculated from the date of payment to the date of repayment, at the rates specified in GCC Sub-Clause 41.1. |
| 48. Bonus | * 1. Not used. |
| 49. Advance Payment  Secured Advances | 49.1 The Employer shall make advance payment to the Contractor of the amounts **stated in the PCC** by the date **stated in the PCC,** against provision by the Contractor of an Unconditional Bank Guarantee in a form and by a bank acceptable to the Employer in amounts in Indian Rupees equal to the advance payment. The Guarantee shall remain effective until the advance payment has been repaid, but the amount of the Guarantee shall be progressively (*each instalment not less than Rs. 500,000*) reduced by the amounts repaid by the Contractor. Interest shall not be charged on the advance payment.  49.2 The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilization expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager.  49.3 The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, following the schedule of completed percentages of the Works on a payment basis. No account shall be taken of the advance payment or its repayment in assessing valuations of work done, Variations, price adjustments, Compensation Events, Liquidated Damages.  49.4 The Project Manager shall make advance payment in respect of materials intended for but not yet incorporated in the Works in accordance with conditions **stipulated in the PCC**. |
| 50. Securities | 50.1 The Performance Security shall be provided to the Employer no later than the date specified in the Letter of Acceptance and shall be issued in an amount **specified in the PCC,** by a Nationalized or Schedule bank in India, and denominated. The Bank Guarantee for Performance Security and additional security for unbalanced bids shall be valid until a date 28 days from the date of issue of the Certificate of Completion. |
| 51. Dayworks | 51.1 Not used. |
| 52. Cost of Repairs | 52.1 Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |

E. Finishing the Contract

|  |  |
| --- | --- |
| 53. Completion | 53.1 The Contractor shall request the Project Manager to issue a Certificate of Completion of the Works, and the Project Manager shall do so upon deciding that the whole of the Works is completed. |
| 54. Taking Over | 54.1 The Employer shall take over the Site and the Works within seven days of the Project Manager’s issuing a certificate of Completion. |
| 55. Final Account | 55.1 The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract at the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within 56 days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within 56 days a schedule that states the scope of the corrections or additions that are necessary including corrections and additions to comply with the applicable Laws/ Rules/ Regulations for protection of environment, public health and safety, and the applicable parts of the Environment Management Planof the project. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate within 56 days of receiving the contractor’s revised account. |
| 56. Operating and Maintenance Manuals | 56.1 If “as built” Drawings [including a compact disk containing digitized drawings] and/or operating and maintenance manuals are required, the Contractor shall supply them by the dates **stated in the PCC.**  56.2 If the Contractor does not supply the Drawings [including a compact disk containing digitized drawings] and/or manuals by the dates **stated in the PCC** pursuant to GCC Sub-Clause 56.1**,** or they do not receive the Project Manager’s approval, the Project Manager shall withhold the amount **stated in the PCC** from payments due to the Contractor. |
| 57. Termination | 57.1 The Employer or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract after giving fourteen (14) days written notice.  57.2 Fundamental breaches of Contract shall include, but shall not be limited to, the following:   1. the Contractor stops work for 28 days when no stoppage of work is shown on the current Program and the stoppage has not been authorized by the Project Manager; 2. the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within 28 days; 3. the Employer or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; 4. a payment certified by the Project Manager is not paid by the Employer to the Contractor within 84 days of the date of the Project Manager’s certificate; 5. the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; 6. the Contractor does not maintain a Security, which is required; 7. the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as **defined in the PCC**; or 8. if the Contractor, in the judgment of the Employer, has engaged in corrupt or fraudulent practices in competing for or in executing the Contract, pursuant to GCC Clause 25.1, then the Employer may, after giving fourteen (14) days written notice to the Contractor, terminate the Contract and expel him from the Site. 9. The contractor has contravened Clauses 7 and 9 of GCC. 10. The contractor does not adhere to the agreed construction program and agreed environmental management plan [Clause 26 of GCC] and also fails to take satisfactory remedial action as per agreements reached in the management meetings [Clause 30 of GCC] for a period of 60 days. 11. The contractor fails to carry out of the instructions of the Project Manager within a reasonable time determined by the Project Manager in accordance with GCC Clause 15.1 and 22. 12. The contractor (in case of Joint Venture) has modified the composition of the joint venture and/or the responsibility of each member of the joint venture from what is stated in joint venture agreement without the prior approval of the Employer.   57.3 When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under GCC Sub-Clause 57.2 above, the Project Manager shall decide whether the breach is fundamental or not.  57.4 Notwithstanding the above, the Employer may terminate the Contract for convenience.  57.5 If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| 58. Payment upon Termination | 58.1 If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received upto the date of the issue of the certificate less other recoveries due in terms of contract, less taxes to be deducted at source [TDS] as per applicable law, and less the percentage to apply to the value of the work not completed, as **indicated in the PCC.** Additional Liquidated Damages shall not apply. If the total amount due to the Employer exceeds any payment due to the Contractor, the difference shall be a debt payable to the Employer.  58.2 If the Contract is terminated for the Employer’s convenience or because of a fundamental breach of Contract by the Employer, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received upto the date of the certificate less other recoveries due in terms of the contract and less taxes due to be deducted at source [TDS] as per applicable law. |
| 59. Property | 59.1 All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Employer if the Contract is terminated because of the Contractor’s default. |
| 60. Release from Performance | 60.1 If the Contract is frustrated by the outbreak of war or by any other event entirely outside the control of either the Employer or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |
| 61. Suspension of Bank Loan or Credit | 61.1 In the event that the Bank suspends the Loan or Credit to the Employer, from which part of the payments to the Contractor are being made:   1. The Employer is obligated to notify the Contractor of such suspension within 7 days of having received the Bank’s suspension notice. 2. If the Contractor has not received sums due it within the 28 days for payment provided for in Sub-Clause 40.1, the Contractor may immediately issue a 14-day termination notice. |

**APPENDIX TO GENERAL CONDITIONS**

**Bank’s Policy- Corrupt and Fraudulent Practices**

***(Text in this Appendix shall not be modified)***

**Guidelines for Procurement of Goods, Works, and Non-Consulting Services under IBRD Loans and IDA Credits & Grants by World Bank Borrowers, dated January 2011:**

“**Fraud and Corruption:**

1.16 It is the Bank’s policy to require that Borrowers (including beneficiaries of Bank loans), bidders, suppliers, contractors and their agents (whether declared or not), sub-contractors, sub-consultants, service providers or suppliers, and any personnel thereof, observe the highest standard of ethics during the procurement and execution of Bank-financed contracts.[[30]](#footnote-30) In pursuance of this policy, the Bank:

(a) defines, for the purposes of this provision, the terms set forth below as follows:

(i) “corrupt practice” is the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence improperly the actions of another party;[[31]](#footnote-31);

(ii) “fraudulent practice” is any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation;[[32]](#footnote-32)

(iii) “collusive practice” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party;[[33]](#footnote-33)

(iv) “coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party;[[34]](#footnote-34)

(v) “obstructive practice” is

(aa) deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation, or

(bb) acts intended to materially impede the exercise of the Bank’s inspection and audit rights provided for under paragraph 1.16(e) below.

(b) will reject a proposal for award if it determines that the bidder recommended for award, or any of its personnel, or its agents, or its sub-consultants, sub-contractors, service providers, suppliers and/or their employees, has, directly or indirectly, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices in competing for the contract in question;

(c) will declare misprocurement and cancel the portion of the loan allocated to a contract if it determines at any time that representatives of the Borrower or of a recipient of any part of the proceeds of the loan engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices during the procurement or the implementation of the contract in question, without the Borrower having taken timely and appropriate action satisfactory to the Bank to address such practices when they occur, including by failing to inform the Bank in a timely manner at the time they knew of the practices;

(d) will sanction a firm or individual, at any time, in accordance with the prevailing Bank’s sanctions procedures,[[35]](#footnote-35) including by publicly declaring such firm or individual ineligible, either indefinitely or for a stated period of time: (i) to be awarded a Bank-financed contract; and (ii) to be a nominated[[36]](#footnote-36);

(e) will require that a clause be included in bidding documents and in contracts financed by a Bank loan, requiring bidders, suppliers and contractors, and their sub-contractors, agents, personnel, consultants, service providers, or suppliers, to permit the Bank to inspect all accounts, records, and other documents relating to the submission of bids and contract performance, and to have them audited by auditors appointed by the Bank.”

**Section IX. Particular Conditions of Contract**

*Except where otherwise indicated, all* PCC *should be filled in by the* Employer *prior to issuance of the Bidding Documents. Schedules and reports to be provided by the* Employer *should be annexed.*

|  |  |
| --- | --- |
| **A. General** | |
| **GCC 1.1 (d)** | The financing institution is: |
| **GCC 1.1 (r)** | The Employer is *[insert name, address, and name of authorized representative]*. |
| **GCC 1.1 (v)** | The Intended Completion Date for the whole of the Works shall be *[insert date]*  *[If different dates are specified for completion of the Works by section (“sectional completion” or milestones), these dates should be listed here]* |
| **GCC 1.1 (y)** | The Project Manager is *[insert name, address, and name of authorized representative]*. |
| **GCC 1.1 (aa)** | The Site is located at *[insert address of Site]* and is defined in drawings No. *[insert numbers]* |
| **GCC 1.1 (dd)** | The Start Date shall be one week after the date of issue of notice to proceed with works to the contractor. |
| **GCC 1.1 (hh)** | The Works consist of *[insert brief summary, including relationship to other contracts under the Project]*.  Identification number of Contract is……………….. |
| **GCC 2.2** | Sectional Completions are: *[insert nature and dates, if appropriate]* |
| **GCC 2.3 (i)** | The following documents also form part of the Contract: *[list documents]*   |  |  |  | | --- | --- | --- | | S. No. | Document | Description of the document | | 1. | Construction Methodology | Construction methodology given in bid amended as per comments of Employer given in letter of acceptance. | | 2. | Quality control | Quality control procedures and assurance plans given in the bid and amended as per comments of Employer given in letter of acceptance. | | 3. | Environmental, Social, Health and Safety | (i) ESHS Management Strategies and Implementation Plans; (ii) Labor Influx and Worker’s Camp Management Plan including the process for mitigating construction related impacts on local community; and (iii) Code of Conduct that will apply to its employees and subcontractors, to ensure compliance with its Environmental, Social, Health and Safety (ESHS) obligations under the contract. | |
| **GCC 3.1** | The language of the contract is *English.*  The law that applies to the Contract is the laws of Union of India. |
| **GCC 5.1** | The Project manager *[may or may not]* delegate any of his duties and responsibilities. |
| **GCC 7.1** | The ceiling for sub-contractor is 25% [*This is addition to what was stated in bid and incorporated in contract agreement.]* |
| **GCC 8.1** | Schedule of other contractors: *[insert Schedule of Other Contractors, if appropriate]* |
| **GCC 9.1** | Key Personnel and equipment:  GCC 9.1 is replaced with the following:   * 1. Key Personnel are the Contractor’s personnel named in this GCC 9.1 of the Particular Conditions of Contract. The Contractor shall employ the Key Personnel and use the equipment identified in its Bid, to carry out the Works or other personnel and equipment approved by the Project Manager. The Project Manager shall approve any proposed replacement of Key Personnel and equipment only if their relevant qualifications or characteristics are substantially equal to or better than those proposed in the Bid.   *[insert the name/s of each Key Personnel agreed by the Employer prior to Contract signature, Schedule of Key Personnel and equipment as indicated in accepted bid & construction methodology].* |
| **GCC 13.1** | The minimum insurance amounts and deductibles shall be:  *[Employers should fill these columns carefully in consultation with insurance companies. It should not be left blank]*   |  |  |  |  | | --- | --- | --- | --- | | S.No. | Description | Minimum cover for Insurance | Maximum deductible for Insurance | | (i) | Works and Plant and Materials which are incorporated in works |  |  | | (ii) | Loss or damage to Construction Equipment |  |  | | (iii) | Other Property |  |  | | (iv) | Personal injury or death insurance:  a) for other people; |  |  | |  | b) for Contractor’s Employees | In accordance with the statutory requirements applicable in India | | |
| **GCC 14.1** | Site Data are: *[list Site Data]* |
| **GCC 15.2** | *[Insert after GCC 15.2.2 the following]*  15.2.2 (b): The Contractor shall implement all mitigation measures for which responsibility is assigned to him as stipulated in the Environmental Management *[Plan/Framework (strike out whichever is not applicable)],* and the conditions stipulated in Section VII-Work Requirements of this Bidding Document, even if not explicitly covered under the ESHS-MSIP submitted by the bidder and made part of the Contract Document. |
| **GCC 20.1** | The Site Possession Date(s) shall be: *[insert location and date(s)]*  The Site Possession Dates shall be:  Section 1 \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  Section 2\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  Section 3 \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| **GCC 23.1 &**  **GCC 23.2** | Name of the agreed Adjudicator/Dispute Review Expert ………………………………………... *(insert name before signing contract)*.  Appointing Authority for the Adjudicator/Dispute Review Expert: *[insert name of Authority]*.  *[Note: if ITB 46 provides for an Adjudicator from list provided by an Institution, insert the name of the same institution as the appointing authority]* |
| **GCC 24.3** | Daily rate and types of reimbursable expenses to be paid to the Adjudicator/Dispute Review Expert: *[insert daily fees [not less than Rs. 5000 per day] and reimbursable expenses – boarding/lodging/travel etc.]*.  *[Note: if ITB 46 provides for provision of an Adjudicator from list provided by an institution, kindly state that ‘the daily fee and reimbursable expenses payable to the Adjudicator will be governed by rules of ………. (name of the Institution)].* |
| **GCC 24.4** | The procedure for adhoc arbitration will be as follows:   1. In case of Dispute or difference arising between the Employer and an Indian Contractor relating to any matter arising out of or connected with this agreement, such disputes or difference shall be settled in accordance with the Arbitration and Conciliation Act, 1996. The arbitral tribunal shall consist of 3 Arbitrators one each to be appointed by the Employer and the Contractor. The third Arbitrator shall be chosen by the two Arbitrators so appointed by the Parties and shall act as Presiding Arbitrator. In case of failure of the two Arbitrators appointed by the parties to reach upon a consensus within a period of 30 days from the appointment of the Arbitrator appointed subsequently, the Presiding Arbitrator shall be appointed by the\* Indian Council of Arbitration/ President of the Institution of Engineers (India)/The International Centre for Alternative Disputes Resolution (India). For the purposes of this Sub-Clause, the term “Indian Contractor” means a contractor who is registered in India and is a juridic person created under Indian law as well as a joint venture between such a contractor and a Foreign Contractor.   Note: *[Sub-para (b) is applicable in case of contract award to foreign contractors].*   1. In the case of dispute with a Foreign Contractor the dispute shall be settled in accordance with provisions of UNCITRAL Arbitration Rules. The Arbitral Tribunal shall consist of three Arbitrators one each to be appointed by the Employer and the Contractor. The third Arbitrator shall be chosen by the two Arbitrators so appointed by the Parties, and shall act a presiding Arbitrator. In case of failure of the two Arbitrators appointed by the parties to reach upon a consensus within a period of 30 days from the appointment of the Arbitrator appointed, the Presiding Arbitrator shall be appointed by the\* Indian Council of Arbitration/President of the Institution of Engineers (India)/The International Centre for Alternative Disputes Resolution (India). For the purposes of this Clause, the term “Foreign Contractor” means a contractor who is not registered in India and is not a juridical person created under Indian Law. 2. If one of the parties fails to appoint its Arbitrator in pursuance of sub-clause (a) and (b) above within 30 days after receipt of the notice of the appointment of its Arbitrator by the other party, then the \*Indian Council of Arbitration/President of the Institution of Engineers (India)/The International Centre for Alternative Disputes Resolution (India), both in cases of Foreign Contractor as well as Indian Contractor, shall appoint the Arbitrator. A certified copy of the order of the\* Indian Council of Arbitration/President of the Institution of Engineers (India)/The International Centre for Alternative Disputes Resolution (India), making such an appointment shall be furnished to each of the parties. 3. Arbitration may be commenced prior to or after completion of the Works, provided that the obligations of the Employer, the Project Manager, the Contractor and the Adjudicator/ Dispute Review Expert shall not be altered by reason of the arbitration being conducted during the progress of the Works. 4. Arbitration proceedings shall be held at\_\_\_\_\_\_\_\_\_\_, India, and the language of the arbitration proceedings and that of all documents and communications between the parties shall be English. 5. The decision of the majority of Arbitrators shall be final and binding upon both parties. The cost and expenses of Arbitration proceedings will be paid as determined by the arbitral tribunal. However, the expenses incurred by each party in connection with the preparation, presentation, etc. of its proceedings as also the fees and expenses paid to the Arbitrator appointed by such party or on its behalf shall be borne by each party itself. 6. Where the value of the contract is Rs.50 million and below, the disputes or differences arising shall be referred to the Sole Arbitrator. The Sole Arbitrator should be appointed by agreement between the parties; failing such agreement, by the appointing authority, namely the \* Indian Council of Arbitration/President of the Institution of Engineers (India)/The International Centre for Alternative Disputes Resolution (India). 7. The Arbitrator should give final award within……… days of starting of the proceedings [*indicate the days (Between 120-180) by which arbitrator should give award].* 8. Performance under the contract shall continue during the arbitration proceedings and payments due to the contractor by the Employer shall not be withheld, unless they are the subject matter of the arbitration proceedings.   \* Choose *one alternative. Insert Chairman of the Executive Committee of the Indian Roads Congress (for highway project) or any other appropriate institution (for other types of works).*  ***Alternatively***  ***[Note: this may be used only in cases of contract awards to Indian contractors]***  *[Apart from the adhoc arbitration services obtained through mutually agreed Arbitrator(s) as above, Institutional arbitration services are also available in India. Institutional arbitration (and mediation) dispute resolution mechanisms can be gainfully used, preferably for relatively larger contracts. Following clause may be included, if it is decided to use Institutional Services for arbitration for resolution of disputes, and in such a case other clauses related to Arbitration/ Arbitrator would be deleted. In the sample clause below, substitute the reference to ‘Rules of Domestic Commercial Arbitration of the Indian Council of Arbitration’ by the specific institution that is sought to be engaged e.g. The International Centre for Alternative Dispute Resolution (ICADR), The Indian Institute of Arbitration and Mediation (IIAM), Indian Chamber’s Council of Arbitration, Delhi International Arbitration Centre (DAC), Construction Industry Arbitration Council (CIAC), Council For National and International Commercial Arbitration, London Court of International Arbitration (India Centre) or the like.]*  "Any dispute or difference whatsoever arising between the parties out of or relating to the construction, meaning, scope, operation or effect of this contract or the validity or the breach thereof shall be settled by arbitration in accordance with the Rules of Domestic Commercial Arbitration of the Indian Council of Arbitration and the award made in pursuance thereof shall be binding on the parties.  The arbitral tribunal shall consist of 3 Arbitrators, arbitration proceedings shall be held at\_\_\_\_\_\_\_\_\_\_, India and the language of the arbitration proceedings and that of all documents and communications between the parties shall be English”. *[ICA rules provide for arbitration tribunal of 3 arbitrators if the value of claim is over Rs 1 crore unless the parties have agreed otherwise for a sole arbitrator].* |
| **B. Time Control** | |
| **GCC 26.1** | The Contractor shall submit a revised Program including Environmental Management Plan and ESHS-MSIP for the Works (in such form and detail as the Project Manager shall reasonably prescribe) within 14 days of delivery of the Letter of Acceptance.  [*This program should be in adequate detail and generally conform to the program submitted alongwith bid. Deviations if any from that should be clearly explained and should be satisfactory to the Project Manager]* |
| **GCC 26.3** | The period between Program updates is \_\_\_\_\_\_ *[insert number]* days.  The amount to be withheld for late submission of an updated Program is\_\_\_\_\_\_ *[insert amount say Rs 500,000]*. |
| **GCC 26.6** | The following is inserted as a new sub clause 26.6:  “26.6 The contractor will submit a brief Labor Influx and Worker’s Camp Management Plan including the process for mitigating construction related impacts on local community within 30 days of signing the contract. The plan shall be updated and a revised plan shall be submitted, if required.” |
| **GCC 30** | Venue of management meeting will be……………….*(State the venue)* |
| **C. Quality Control** | |
| **GCC 34.3** | The Defects Liability Period is: *[insert number]* days.  *[The Defects Liability Period is usually limited to 12 months, but could be less(not less than 6 months) in very simple cases]* |
| **D. Cost Control** | |
| **GCC 41.1** | Interest rate for Delayed payment is ….% per annum (insert the number corresponding to the State Bank of India prime lending rate). |
| **GCC 45.1** | Price Adjustment:  The contract *[insert “is” or “is not”]* subject to price adjustment in accordance with G.C.C. Clause 45 and following information regarding coefficients *[specify “does” or “does not” apply] [Price adjustment is mandatory for all contract with completion time exceeding 18 months.]*  The Price Adjustment shall be done in accordance with Tables 1&2 of Adjustment Data given in Appendix 2. The base and current price of the following items shall be based on the source indicated below:   1. Diesel: Selling price of IOC depot at ….In case the work extends over long stretches or different sections specify separate identified depot… 2. Bitumen: Selling Price of Bitumen from the IOC refinery at … *[specify]*… 3. ………   **The price Adjustment will be done monthly** *(or if it is different state here)* |
| **GCC 46.1** | The proportion of payments retained (Retention Money) shall be 6% from each bill subject to the maximum of 5% of final contract price. |
| **GCC 47.1** | The liquidated damages for the whole of the Works are *[insert percentage of the final Contract Price]* per day. The maximum amount of liquidated damages for the whole of the Works is *[insert percentage]* of the final Contract Price.  For milestone 1 Rs. \_\_\_\_\_\_\_\_\_\_\_\_per day  For milestone 2 Rs. \_\_\_\_\_\_\_\_\_\_\_\_per day  All works Rs. \_\_\_\_\_\_\_\_\_\_\_\_per day  *[Usually liquidated damages are set between 0.05 percent and 0.20 percent per day, and the total amount is not to exceed between 5 percent and 10 percent of the Contract Price.* *If Sectional Completion and Damages per Section have been agreed, the latter should be specified here]* |
| **GCC 49.1** | The amount of the advance payments are:   |  |  |  | | --- | --- | --- | | Nature of Advance | Amount (Rs.) | Conditions to be fulfilled | | 1. Mobilization | 5% of the Contract price | On submission of un-conditional Bank Guarantee. *(to be drawn before end of 20% of Contract period*) | | 2. Equipment  *(This advance is not applicable for equipment already owned or hired/leased by the contractor.)* | 90% for new and 50% of depreciated value for old equipment. Total amount will be subject to a maximum of 5%/10%/15%\* of the Contract price.  *(\*Choose one and delete others)* | After equipment is brought to site as per agreed construction program (*provided the Project Manager is satisfied that the equipment is required for performance of the contract)* and on submission of unconditional Bank Guarantee for amount of advance. | | 3. Secured advance for non-perishable materials brought to site *[Specify the item or items for which this will be given here]* | 75% of Invoice value or Market value –lower of the two. | a) The materials are in-accordance with the specification for Works;  b) Such materials have been delivered to site, and are properly stored and protected against damage or deterioration to the satisfaction of the Project Manager.  c) the Contractor’s records of the requirements, orders, receipt and use of materials are kept in a form approved by the Project Manager and such records shall be available for inspection by the Project Manager;  d) The contractor has submitted with his monthly statement the estimated value of the materials on site together with such documents as may be required by the Project Manager for the Purpose of valuation for material and providing evidence of ownership and payment thereof;  e) Ownership of such materials shall be deemed to vest in the Employer for which the Contractor has submitted an Indemnity Bond in an acceptable format; and  f) The quantity of materials are not excessive and shall be used within a reasonable time as determined by the Project Manager. | | (The advance will be paid to the Contractor no later than 15 days after fulfilment of the above conditions). | | |   Repayment of advance payment for mobilization and equipment:  The advance shall be repaid with percentage deductions from the interim payments certified by the Project Manager under the Contract. Deductions shall commence in the next Interim Payment Certificate following that in which the total of all such payments to the contractor has reached not less than 15 percent of the Contract Price or \_\_\_\_\_\_\_months from the date of payment of first instalment of advance, whichever period concludes earlier, and shall be made at the rate of \_\_\_@percent of the amounts of all Interim Payment Certificates until such time as the advance has been repaid, always provided that the advance shall be completely repaid prior to the expiry of the original time for completion.  **Repayment of secured advance**:  The advance shall be repaid from each succeeding monthly payments to the extent materials *[for which advance was previously paid pursuant to Clause 49 of GCC and 49.1(3) of PCC.]* have been incorporated into the Works.  @ *Stipulate appropriately, namely 30% for 20% advance, 25% for 15% advance, 15% for 10% advance and 7.5% for 5% advance respectively.* |
| **GCC 50.1** | “GCC 50.1 is replaced with the following  The Performance Security and an Environmental, Social, Safety and Health (ESHS) Performance Security shall be provided to the Employer no later than the date specified in the Letter of Acceptance and shall be issued in the amounts specified in the PCC (for GCC 50.1), and shall be issued by a Nationalized or Scheduled bank in India. The Performance Security and the ESHS Performance Security, shall be valid until a date 28 days from the date of issue of the Certificate of Completion.” |
| **GCC 50.1** | The Performance Security amount is ……. percent of contract price plus Rs. ….. as additional security for unbalanced bids [*in terms of ITB Clause 40*], and Environmental, Social, Safety and Health (ESHS) Performance Security amount is *…* percent of Contract Amount.  The standard form of Performance Security acceptable to the Employer shall be unconditional Bank Guarantees from a Scheduled or Nationalized banks in India of the types as presented in Section X of the Bidding Documents.  *[Notes: The* ***Bank Guarantees*** *shall be unconditional (on demand) (see Section X, Contract Forms). The ESHS Performance Security will normally be in the amount(s) of around 1% of the Accepted Contract Amount. The sum of the total “demand guarantees” (Performance Security including ESHS Performance Security) shall normally not exceed 10 % of the Accepted Contract Amount.*  *Throughout this bidding document the term ’performance security’, unless the context clearly indicates otherwise, means and includes both ‘the performance security and the ESHS performance security’ to be submitted by the successful bidder in the amounts specified above].* |
| **E. Finishing the Contract** | |
| **GCC 56.1** | \* The date by which operating and maintenance manuals are required is within 28 days of issue of certificate of completion of whole or section of work, as the case may be ………….*[insert date]*  \* The date by which “as-built” drawings (in scale…) including a compact disc containing digitized drawings in 2 sets are required is within 28 days of issue of certificate of completion of whole or section of the work, as the case may be …………..*[insert date]*. |
| **GCC 56.2** | The amount to be withheld for failing to produce “as built” drawings and/or operating and maintenance manuals \*by the date required in G.C.C. 56.1 is Rs.\_\_\_\_\_\_\_\_\_ |
| **GCC 57.2 (g)** | The maximum number of days is: *[insert number; consistent with clause 47.1 on liquidated damages].* |
| **GCC 58.1** | The percentage to apply to the value of the work not completed, representing the Employer’s additional cost for completing the Works, is 20%. |

# Appendices

Appendix 1

## Salient Features of Labour & Environment Protection Laws[[37]](#footnote-37)

SALIENT FEATURES OF SOME MAJOR LABOUR LAWS

APPLICABLE TO ESTABLISHMENTS ENGAGED IN BUILDING AND OTHER CONSTRUCTION WORK

|  |
| --- |
| 1. Employees Compensation Act 1923: The Act provides for compensation in case of injury, disease or death arising out of and during the course of employment. 2. Payment of Gratuity Act 1972: gratuity is payable to an employee under the Act on satisfaction of certain conditions on separation if an employee has completed 5 years’ service or more or on death at the rate of 15 days wages for every completed year of service. The Act is applicable to all establishments employing 10 or more employees. 3. Employees P.F. and Miscellaneous Provision Act 1952 (*since amended*): The Act provides for monthly contribution by the employer plus workers @ 10% or 8.33%. The benefits payable under the Act are:   (i) Pension or family pension on retirement or death, as the case may be.  (ii) Deposit linked insurance on the death in harness of the worker.  (iii) Payment of P.F. accumulation on retirement/death etc.   1. Maternity Benefit Act 1961: The Act provides for leave and some other benefits to women employees in case of confinement or miscarriage etc. 2. Sexual Harassment of Women at the Workplace (Prevention, Prohibition and Redressal) Act, 2013: This Act defines sexual harassment in the workplace, provides for an enquiry procedure in case of complaints and mandates the setting up of an Internal Complaints Committee or a Local Complaints Committee 3. Contract Labour (Regulation & Abolition) Act 1970: The Act provides for certain welfare measures to be provided by the Contractor to contract labour and in case the Contractor fails to provide, the same are required to be provided, by the Principal Employer by law. The Principal Employer is required to take Certificate of Registration and the Contractor is required to take license from the designated Officer. The Act is applicable to the establishments or Contractor of Principal Employer if they employ 20 or more contract labour. 4. Minimum Wages Act 1948: The Employer is supposed to pay not less than the Minimum Wages fixed by appropriate Government as per provisions of the Act if the employment is a scheduled employment. Construction of Buildings, Roads, Runways are scheduled employments. 5. Payment of Wages Act 1936: It lays down the mode, manner and by what date the wages are to be paid, what deductions can be made from the wages of the workers. 6. Equal Remuneration Act 1976: The Act provides for payment of equal wages for work of equal nature to male and female workers and for not making discrimination against Female employees in the matters of transfers, training and promotions etc. 7. Payment of Bonus Act 1965: The Act is applicable to all establishments employing 20 or more employees. Some of the State Governments have reduced this requirement from 20 to 10. The Act provides for payments of annual bonus subject to a minimum of 8.33% of the wages drawn in the relevant year. It applies to skilled or unskilled manual, supervisory, managerial, administrative, technical or clerical work for hire or reward to employees who draw a salary of Rs. 10,000/- per month or less. To be eligible for bonus, the employee should have worked in the establishment for not less than 30 working days in the relevant year. The Act does not apply to certain establishments.      1. Industrial Disputes Act 1947: the Act lays down the machinery and procedure for resolution of Industrial disputes, in what situations, a strike or lock-out becomes illegal and what are the requirements for laying off or retrenching the employees or closing down the establishment. 2. Trade Unions Act 1926: The Act lays down the procedure for registration of trade unions of workmen and employers. The Trade Unions registered under the Act have been given certain immunities from civil and criminal liabilities. 3. Child Labour (Prohibition & Regulation) Act 1986: The Act prohibits employment of children below 14 years of age in certain occupations and processes and provides for regulation of employment of children in all other occupations and processes. Employment of Child Labour is prohibited in the Building and Construction Industry. 4. Inter-State Migrant workmen’s (Regulation of Employment & Conditions of Service) Act 1979: The Act is applicable to an establishment which employs 5 or more inter-state migrant workmen through an intermediary (who has recruited workmen in one state for employment in the establishment situated in another state). The Inter-State migrant workmen, in an establishment to which this Act becomes applicable, are required to be provided certain facilities such as housing, medical aid, traveling expenses from home upto the establishment and back, etc. 5. The Building and Other Construction Workers (Regulation of Employment and Conditions of Service) Act 1996 and the Building and Other Construction Workers Welfare Cess Act, 1996 (BOCWW Cess Act): All the establishments who carry on any building or other construction work and employ 10 or more workers are covered under these Acts. All such establishments are required to pay cess at the rate not exceeding 2% of the cost of construction as may be notified by the Government. The Employer of the establishment is required to provide safety measures at the building or construction work and other welfare measures, such as Canteens, First – Aid facilities, Ambulance, Housing accommodations for workers near the work place etc. The Employer to whom the Act applies has to obtain a registration certificate from the Registering Officer appointed by the Government. 6. Factories Act 1948: the Act lays down the procedure for approval of plans before setting up a factory engaged in manufacturing processes, health and safety provisions, welfare provisions, working hours, annual earned leave and rendering information regarding accidents or dangerous occurrences to designated authorities. It is applicable to premises employing 10 persons or more with aid of power or 20 or more persons without the aid of power. 7. Weekly Holidays Act -1942 8. Bonded Labour System (Abolition) Act, 1976: The Act provides for the abolition of bonded labour system with a view to preventing the economic and physical exploitation of weaker sections of society. Bonded labour covers all forms of forced labour, including that arising out of a loan, debt or advance. 9. Employer’s Liability Act, 1938: This Act protects workmen who bring suits for damages against employers in case of injuries endured in the course of employment. Such injuries could be on account of negligence on the part of the employer or persons employed by them in maintenance of all machinery, equipment etc. in healthy and sound condition. 10. Employees State Insurance Act 1948: The Act provides for certain benefits to insured employees and their families in case of sickness, maternity and disablement arising out of an employment injury. The Act applies to all employees in factories (as defined) or establishments which may be so notified by the appropriate Government. The Act provides for the setting up of an Employees’ State Insurance Fund, which is to be administered by the Employees State Insurance Corporation. Contributions to the Fund are paid by the employer and the employee at rates as prescribed by the Central Government. The Act also provides for benefits to dependents of insured persons in case of death as a result of an employment injury. 11. The Personal Injuries (Compensation Insurance) Act, 1963: This Act provides for the employer’s liability and responsibility to pay compensation to employees where workmen sustain personal injuries in the course of employment. 12. Industrial Employment (Standing Order) Act 1946: It is applicable to all establishments employing 100 or more workmen (employment size reduced by some of the States and Central Government to 50). The Act provides for laying down rules governing the conditions of employment by the Employer on matters provided in the Act and get the same certified by the designated Authority. |

SALIENT FEATURES OF SOME OF THE MAJOR LAWS THAT ARE APPLICABLE FOR PROTECTION OF ENVIRONMENT.

|  |
| --- |
| 1. The Environment (Protection) Act, 1986 and as amended: This provides for the protection and improvement of environment and for matters connected therewith, and the prevention of hazards to human beings, other living creatures, plants and property. ‘Environment’ includes water, air and land and the inter-relationship which exists among and between water, air and land, and human beings, other living creatures, plants, micro-organism and property. 2. The Forest Conservation Act, 1980, as amended, and Forest (Conservation) Rules, 1981 as amended: These provides for protection of forests by restricting conversion of forested areas into non- forested areas and prevention of deforestation, and stipulates the procedures for cutting any trees that might be required by the applicable rules. Permissions under the Act also stipulates the norms and compliance requirements of the employer and any contractor on behalf of the employer. 3. State Tree Preservation Acts as may be in force: These provide for protection of trees of important species. Contractors will be required to obtain prior permission for full or partial cutting, uprooting, or pruning of any such trees. 4. The Wildlife (Protection) Act, 1972, and as amended: This provides for protection of wildlife through notifying National Parks and Sanctuaries and buffer areas around these zones; and to protect individuals of nationally important species listed in the Annex of the Act. 5. The Biological Diversity Act, 2002: This provides for conservation of biological diversity, sustainable use of components of biological diversity, and fair and equitable sharing of the benefits arising out of the use of biological resources, knowledge and for matters connected therewith or incidental thereto. 6. The Public Liability Insurance Act, 1991 as amended and The Public Liability Insurance Rules, 1991 as amended: These provide for public liability insurance for the purpose of providing immediate relief to the persons affected by accident occurring while handling hazardous substances and for mattes connected herewith or incidental thereto. Hazardous substance means any substance or preparation which is defined as hazardous substance under the Environment (Protection) Act 1986, and exceeding such quantity as may be specified by notification by the Central Government. 7. The Ancient Monuments and Archaeological Sites and Remains Act, 1958 and the Ancient Monuments and Archaeological Sites and Remains (Amendment and Validation) Act, 2010, the Ancient Monuments and Archaeological Sites and Remains Rules, 1959 amended 2011, the National Monuments Authority Rules, 2011 and the similar State Acts: These provide for conservation of cultural and historical remains found in India. Accordingly, area within the radii of 100m and 300m from the “protected property” are designated as “protected area” and “controlled area” respectively. No development activity (including building, mining, excavating, blasting) is permitted in the “protected area” and development activities likely to damage the protected property is not permitted in the “controlled area” without prior permission of the Archaeological Survey of India (ASI) or the State Departments of Art and Culture or Archaeology as applicable. 8. The Environmental Impact Assessment Notification, 2006 and as amended: This provides for prior environmental clearance for new, modernization and expansion projects listed in Schedule 1 of the Notification. Contractors will be required to ensure that no work starts until applicable clearances under the Notification is not available. Contractors will be responsible for implementation of any environmental management plan stipulated as per the permission under this Notification; and will be required to prepare and submit to the employer and compliance report stipulated in the permission under the Notification. 9. The Water (Prevention and Control of Pollution) Act, 1974 as amended, and the Water (Prevention and Control of Pollution) Rules, 1975 as amended: These provide for the prevention and control of water pollution and the maintaining and restoring of wholesomeness of water. ‘Pollution’ means such contamination of water or such alteration of the physical, chemical or biological properties of water or such discharge of any sewage or trade effluent or of any other liquid, gaseous or solid substance into water(whether directly or indirectly) as may, or is likely to, create a nuisance or render such water harmful or injurious to public health or safety, or to domestic, commercial, industrial, agricultural or other legitimate uses, or to the life and health of animals or plants or of aquatic organisms. Contractors will need to obtain consent for establishment and consent for operation of any item of work or installation of equipment that generates waste water, and observe the required standards of establishment and operation of these items of work or installations; as well as install and operate all required waste water treatment facilities. 10. The Water (Prevention and Control of Pollution) Cess Act, 1977 and The Water (Prevention and Control of Pollution) Cess Rules, 1978: These provide for the levy and collection of a cess on water consumed by persons carrying on certain industries and by local authorities, with a view to augment the resources of the Central Board and the State Boards for the prevention and control of water pollution under the Water (Prevention and Control of Pollution) Act, 1974. 11. The Air (Prevention and Control of Pollution) Act, 1981 as amended, and the Air (Prevention and Control of Pollution) Rules, 1982: These provides for prevention, control and abatement of air pollution. ‘Air Pollution’ means the presence in the atmosphere of any ‘air pollutant’, which means any solid, liquid or gaseous substance (including noise) present in the atmosphere in such concentration as may be or tend to be injurious to human beings or other living creatures or plants or property or environment. Contractors will need to obtain consent for establishment and consent for operation of any item of work or installation of equipment that generates air pollution such as batching plants, hot mix plants, power generators, backup power generation, material handling processes, and observe the required standards of establishment and operation of these items of work or installations. 12. Noise Pollution (Control and Regulation) Rules, 2000, and as amended: This provides for standards for noise for day and night for various land uses and specifies special standards in and around sensitive receptors of noise such as schools and hospitals. Contractors will need to ensure compliance to the applicable standards, and install and operate all required noise control devices as may be required for all plants and work processes. 13. Chemical Accidents (Emergency Planning, Preparedness and Response) Rules, 1996: This provides for Requirement of preparation of on-site and off-site Disaster Management Plans for accident-prone areas. 14. The Explosives Act 1884 and the Explosives Rules, 2008: These provide for safe manufacture, possession, sale, use, transportation and import of explosive materials such as diesel, Oil and lubricants etc.; and also for regulating the use of any explosives used in blasting and/or demolition. All applicable provisions will need compliance by the contractors. 15. The Petroleum Rules, 2002: This provides for safe use and storage of petroleum products, and will need to be complied by the contractors. 16. The Gas Cylinder Rules 2004 and amendments: This provides for regulations related to storage of gas, and possession of gas cylinder more than the exempted quantity. Contractors should comply with all the requirements of this Rule. 17. Manufacture, Storage and Import of Hazardous Chemical Rules of 1989 and as amended: These provide for use and storage of hazardous material such as highly inflammable liquids like HSD/LPG. Contractors will need to ensure compliance to the Rules; and in the event where the storage quantity exceeds the regulated threshold limit, the contractors will be responsible for regular safety audits and other reporting requirements as prescribed in the Rules. 18. Hazardous & Other Wastes (Management and Transboundary Movement) Rules, 2016: These provide for protection of general public from improper handling storage and disposal of hazardous waste. The rules prescribe the management requirement of hazardous wastes from its generation to final disposal. Contractors will need to obtain permission from the State Pollution Control Boards and other designated authorities for storage and handling of any hazardous material; and will to ensure full compliance to these rules and any conditions imposed in the permit. 19. The Bio Medical Waste Management Rules, 2016: This provides for control, storage, transportation and disposal of bio-medical wastes. As and where the contractor has any first aid facility and dispensaries, established in either temporary or permanent manner, compliance to these Rules are mandatory. 20. Construction and Demolition Waste Management Rules, 2016: This provides for management of construction and demolition waste (such as building materials possible to be reused, rubble and debris or the like); and applies to all those waste resulting from construction, re-modelling, repair or demolition of any civil structure. Contractor will need to prepare a waste disposal plan and obtain required approval from local authorities, if waste generation is more than 20 tons in any day or 300 tons in any month during the contract period; and ensure full compliance to these rules and any conditions imposed in the regulatory approval. 21. The E-Waste (Management) Rules, 2016: This provides for management of E-wastes (but not covering lead acid batteries and radio-active wastes) aiming to enable the recovery and/or reuse of useful material from e-waste, thereby reducing the hazardous wastes destined for disposal and to ensure the environmentally sound management of all types of waste of electrical and electronic equipment. This Rule applies to every manufacturer, producer, consumer, bulk consumer, collection centers, dealers, e-retailer, refurbisher, dismantler and recycler involved in manufacture, sale, transfer, purchase, collection, storage and processing of e-waste or electrical and electronic equipment listed in Schedule I, including their components, consumables, parts and spares which make the product operational. 22. Plastic waste Management Rules, 2016: This provides for control and management of the plastic waste generated from any activity. Contractors will ensure compliance to this Rule. 23. The Batteries (Management and Handling) Rules 2001: This provides for ensuring safe disposal and recycling of discarded lead acid batteries likely to be used in any equipment during construction and operation stage. Rules require proper control and record keeping on the sale or import of lead acid batteries and recollection of the used batteries by registered recyclers to ensure environmentally sound recycling of used batteries. Contractors will ensure compliance to this Rule. 24. The Ozone Depleting Substances (Regulation and Control) Rules, 2000 and as amended: This provides for regulation of production and consumption of ozone depleting substances in the country, and specifically prohibits export to or import from countries not specified in the Rules, and prohibits unless specifically permitted, any use of ozone depleting substance. 25. The Coastal Regulation Zone Notifications, 1991 and as amended: This provides for regulation of development activities within the 500m of high tide line in coastal zone and 100m of stretches of rivers and estuaries influenced by tides. Contractors will be required to ensure that no work starts until applicable clearances under the Notification is not available. Contractors will be responsible for implementation of any plan stipulated as per the permission under this Notification; and will be required to prepare and submit to the employer and compliance report stipulated in the permission under the Notification. 26. The Motor Vehicle Act 1988 as amended (and State Motor Vehicle Acts as may be in force) and the Motor Vehicle Rules, 1989, and as amended (and State Motor Vehicle Rules as may be in force): To minimize the road accidents, penalizing the guilty, provision of compensation to victim and family and check vehicular air and noise pollution. Contractors will be required to ensure full compliance to these rules. 27. Easement Act, 1882: This provides for the rights of landowners on groundwater. Contractors will need to ensure that other landowners’ rights under the Act is not affected by any groundwater abstraction by the contractors. 28. State Groundwater Acts and Rules as may be in force and the Guidelines for Groundwater Abstraction for drinking and domestic purposes in Notified Areas and Industry/Infrastructure project proposals in Non-Notified areas, 2012: These provide for regulating extraction of ground water for construction/industrial and drinking and domestic purposes. Contractors will need to obtain permission from Central/State Groundwater Boards prior to groundwater abstraction through digging any bore well or through any other means; and will to ensure full compliance to these rules and any conditions imposed in the permit. 29. The Mines Act, 1952 as amended; the Minor Mineral and concession Rules as amended; and the State Mineral (Rights and Taxation) Acts as may be in force: These provide for for safe and sound mining activity. The contractors will procure aggregates and other building materials from quarries and borrow areas approved under such Acts. In the event the contractors open any new quarry and/or borrow areas, appropriate prior permission from the State Departments of Minerals and Geology will need to be obtained. Contractors will also need to ensure full compliance to these rules and any conditions imposed in the permit. 30. The Insecticides Act, 1968 and Insecticides Rules, 1971 and as amended: These provide for regulates the manufacture, sale, transport, distribution, export, import and use of pesticides to prevent risk to human beings or animals, and for matters connected therewith. No one should import or manufacture; sell, stock or exhibit foe sale; distribute, transport, use: (i) any misbranded insecticides, (ii) any insecticide the sale, distribution or use of which is for the time being prohibited under the Act; and (iii) any insecticide except in accordance with the condition on which it was registered under the Act. 31. National Building Codes of India, 2005 and as amended: This provides guidelines for regulating the building construction activities in India. The code mainly contains administrative regulations, development control rules and general building requirements; stipulations regarding materials, structural design and construction; and building and plumbing services. Contractors will be required to comply with all Bureau of Indian Standards Codes dealing with: (i) use and disposal of asbestos containing materials in construction; (ii) paints containing lead; (iii) permanent and temporary ventilations in workplace; (iv) safety, and hygiene at the workplace; (v) prevention of fire; (vi) prevention of accidents from faulty electrical gadgets, equipment and accessories; and all other such codes incidental to the Contract. |

Appendix 2

## 

## Tables of Adjustment Data

(Cl. 45 of GCC)

**Table 1: Coefficients governing the adjustment for changes in cost.**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **S. No.** | **Coefficients Name** | **Symbol** | **Schedules (Reference Number)**  **[*Description of each schedule is given below*]** | | | | | | | | |
|  |  |  | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 |
| 1. | Fixed | a | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 |
| 2. | Labour [L] | b |  |  |  |  |  |  |  |  |  |
| 3. | Steel [S] | c |  |  |  |  |  |  |  |  |  |
| 4. | Cement [C] | d |  |  |  |  |  |  |  |  |  |
| 5. | Plant & Equipment spares [E] | e |  |  |  |  |  |  |  |  |  |
| 6. | Diesel and Petroleum products [D] | f |  |  |  |  |  |  |  |  |  |
| 7. | Bitumen [B] | g |  |  |  |  |  |  |  |  |  |
| 8. | Others[O] | 0 |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |
|  | **Total** |  | **100%** | **100%** | **100%** | **100%** | **100%** | **100%** | **100%** | **100%** | **100%** |

[*Fixed element is normally 15%*]

|  |
| --- |
| ***BOQ SCHEDULES***  *[The following Schedules are for example only. The schedules may be modified and specified as appropriate for each work*]  Schedule 1: Earth Work in Formation  Schedule 2: Civil Engineering Work (Bridge)  Schedule 3: Civil Engineering Work Building,  Schedule 4: Steel Fabrication Works  Schedule 5: Road Works –WBM  Schedule 6: Road BTM  Schedule 7: |

**Table 2:** Cost Indices and Reference Prices (applicable for specific items) for adjustment in contract prices [as per GCC 45].

WPI with base 2004-2005 = 100 on the Base Date

Base Date = Deadline for submission of bids

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| S. No. | Cost Element | Symbol | Indices or Cost on the Base Date | Index for adjustment | Sources of Index |
|
| [1] | [2] | [3] | [4] | [5] | [6] |
| 1. | Fixed | a |  |  |  |
| 2. | Labour | b | Lo- all India average Consumer Price Index (CPI) Number for Industrial Workers for ….. centre[[38]](#footnote-38) (Base 2001 = 100) on the base date. | Ln-CPI for the month for which the IPC is related | Labour Bureau, Ministry of Labour and Employment, Government of India. |
| 3. | Steel | c | So – Whole-sale Price Index (WPI) for Steel [*Steel Long]* | Sn-WPI for the month which is two months prior to the month to which IPC is related | Economic Advisor, Ministry of Commerce and Industry, Government of India. |
| 4. | Cement | d | Co-WPI for Grey Cement | Cn-WPI for the month which the cement is brought to site or one month prior to the month to which IPC is related, whichever is less | Economic Advisor, Ministry of Commerce and Industry, Government of India |
| 5. | Plant & Equipment spares | e | Eo-WPI for “Construction machinery ” | En – WPI for the month to which IPC is related | Economic Advisor, Ministry of Commerce and Industry, Government of India |
| 6. | Diesel**[[39]](#footnote-39)** | f | Do-Unit Cost from the identified depot on the base date | Dn-Unit Cost for on the first day of the month to which the IPC relates | From the ………. Depot |
| 7. | Bitumen**[[40]](#footnote-40)** | g | Bo-Unit Cost from the identified refinery on the base date | Bn- Cost per unit quantity on the first day of the month in which the material is brought to site or two months prior to the date to which IPC is related | From …. Refinery |
| 8. | Others | h | Oo- All India Wholesale Price Index(WPI) for all commodities | On- All India WPI for all commodities for the month to which IPC is related | Economic Advisor, Ministry of Commerce and Industry, Government of India |

IPC – Interim Payment Certificate

Appendix -3[[41]](#footnote-41)

Appointment of Adjudicator / Dispute Review Expert

Suggested Draft of Letter of Appointment of Adjudicators in civil works contracts

Sub:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_(Name of the Contract)

**To**

Name and address of the Adjudicator / Dispute Review Expert

We hereby confirm your appointment as Adjudicator/ Dispute Review Expert for the above contract to carry out the assignment specified in this Letter of Appointment.

For administrative purpose\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_(*name of the officer representing the Employer*) has been assigned to administer the assignment and to provide the Adjudicator / Dispute Review Expert with all relevant information needed to carry out the assignment on behalf of both the Employer and the contractor. The services will be required during the period of contract for the work of (Name of the Contract)\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_.

The Adjudicator / Dispute Review Expert shall visit the worksite once in 3 (three)months till the completion of the work indicated above or as specifically requested by Employer/ Contractor for the period upto the end of defects liability period with prior intimation to the Employer and the contractor. The duration of each visit shall ordinarily be for one day only. These durations are approximate and (*Name of the Employer and Name of the Contractor*) may find it necessary to postpone or cancel the assignment and/or shorten or extend the duration.

The appointment will become effective upon confirmation of letter by you. The appointment of Adjudicator/ Dispute Review Expert shall be liable for termination under a 30 (thirty) days written notice from the date of issue of the notice, if both Employer and the Contractor so desire. Also the appointment shall automatically stand terminated 14 days after the defect notice / correction period as stated in Clauses 23 and 24 of the Conditions of Contract is over.

The Adjudicator/ Dispute Review Expert will be paid a fee of Rs.\_\_\_\_\_\_ (Rupees \_\_\_\_\_\_\_\_\_\_\_\_only) per each day of visit at the worksite. The actual expenses for boarding and traveling in connection with the assignment will be reimbursed to the Adjudicator/ Dispute Review Expert. The Adjudicator/ Dispute Review Expert will submit a pre-receipted bill in triplicate to the Employer indicating the date of the visit, fees for the visit and a proof in support of the actual expenditure [only for items valued above Rs. 200 each] incurred by him against boarding, lodging and traveling expenses after performing the visit on each occasion. The Employer will make the admissible payment (both the Employer’s and the Contractor’s share) to the Adjudicator/ Dispute Review Expert within 30 days of the receipt of the bill. The Contractor’s share on this account (half the paid amount) will be recovered by the Employer from the Contractor’s bills against the work.

In accepting this assignment, the Adjudicator/ Dispute Review Expert should understand and agree that he is responsible for any liabilities and costs arising out of risks associated with travel to and from the place of emergency repatriation, loss or damage to personal/professional effects and property. The Adjudicator/ Dispute Review Expert is advised to effect personal insurance cover in respect of such risks if he does not already have such cover in place. In this regard, the Adjudicator/ Dispute Review Expert shall maintain appropriate medical, travel, accident and third-party liability insurance. The obligation under this paragraph will survive till termination of this appointment.

Procedures for resolution of disputes by the Adjudicator/ Dispute Review Expert is described in the contract of \_\_\_\_\_\_\_\_\_\_\_\_\_(name of the contract) between the Employer and the contractor vide clause no.24 of the General Conditions of Contract. Your recommendation should be given in the format attached, within 28 days of receipt of a notification of dispute.

The Adjudicator/ Dispute Review Expert will carry out the assignment in accordance with the highest standard of professional and ethical competence and integrity, having due regard to the nature and purpose of the assignment, and will conduct himself in a manner consistent herewith. After visiting the worksite, the Adjudicator / Dispute Review Expert will discuss the matter with the Employer and if necessary with the Contractor before arriving at any decision.

The Adjudicator/ Dispute Review Expert will agree that all knowledge and information not within the public domain, which may be acquired while carrying out this service shall be all time and for all purpose, regarded as strictly confidential and held in confidence, and shall not be directly or indirectly disclosed to any party whatsoever, except with the permission of the Employer and the contractor. The Adjudicator’s decision should be communicated in the form of a speaking order specifying the reasons.

The Adjudicator/ Dispute Review Expert will agree that any manufacturing or construction firm with which he might be associated with, will not be eligible to participate in bidding for any goods or works resulting from or associated with the project of which this consulting assignment forms a part

Read and Agreed Name of Adjudicator/ Dispute Review Expert

Signature

Place:

Date:

Name of Employer

Signature of authorized representative of Employer

Name of the Contractor

Signature of authorized representative of Contractor

Attachment: Copy of contract document between the Employer and contractor and format for recommendation.

**SUMMARY OF AJUDICATIOR’S RESPONSIBILITIES**

The Adjudicator has the following principal responsibilities:

1. Visit the site periodically.
2. Keep abreast of job activities and developments.
3. Encourage the resolution of disputes by the parties.
4. When a dispute is referred to it, conduct a hearing (no legal presentation), complete its deliberations, and prepare a recommendations in a professional and timely manner(as per sample format)

*[in this and the next form, use the term Adjudicator, or Dispute Review Expert as specified in the rest of the bidding document.]*Sample Format of Adjudicator’s Recommendation

**[Project Name]**

**Recommendation of Adjudicator**

Dispute No. XX [*NAME OF DISPUTE*]

Hearing Date: \_\_\_\_\_\_\_\_\_\_\_\_

**Dispute**

Description of dispute. A one or two sentence summation of the dispute.

**Contractor’s Position**

A short summation of the contractor’s position as understood by the Adjudicator.

**Employer’s Position**

A short summation of the Employer’s position as understood by the Adjudicator.

**Recommendation**

The Adjudicator’s specific recommendation for settlement of the dispute. (*The recommended course is consistent with the explanation*).

**Explanation**

(*This section could also be called Considerations, Rationale, Findings, Discussion, and so on.*)

The Adjudicator’s description of how each recommendation was reached.

Respectfully submitted,

Date : \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date : \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date : \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Section X - Contract Forms

This Section contains forms which, once completed, will form part of the Contract. The forms for Performance Security and Advance Payment Security, when required, shall only be completed by the successful Bidder after contract award.

Letter of Acceptance

*[letterhead paper of the Employer]*

[The Letter of Acceptance shall be the basis for formation of the Contract as described in ITB Clause 43. This Standard Form of Letter of Acceptance shall be filled in and sent to the successful Bidder only after evaluation of bids has been completed, subject to any review by the World Bank required under the Loan Agreement.]

*[insert date]*

Identification No and Title of Contract: *[insert identification number and title of the Contract]*

To: *[insert name and address of the Contractor]*

This is to notify you that your Bid dated *[insert date]* for execution of the *[insert name of the Contract and identification number, as given in the PCC]* for the Contract Price ………………. *[insert amount in numbers and words]* as corrected and modified[[42]](#footnote-42) in accordance with the Instructions to Bidders is hereby accepted by our Agency.

*[insert one of the following (a) or (b) options]*

(a) We accept that *[insert name proposed by bidder]* be appointed as the Adjudicator/Dispute Review Expert [DRE].[[43]](#footnote-43)

(b) We do not accept that *[insert name proposed by bidder]* be appointed as Adjudicator/DRE, and by sending a copy of this Letter of Acceptance to *[insert name of the Appointing Authority]*, we are hereby requesting *[insert name]*, the Appointing Authority, to appoint the Adjudicator/DRE in accordance with GCC 23.[[44]](#footnote-44)

We note that as per your bid, you do not intend to subcontract any component of work.

[OR]

We note that as per your bid, you propose to employ M/s. ………………… as sub-contractor for executing ……………………..

[*Delete whatever is inapplicable*]

You are hereby requested to furnish Performance Security, plus additional security for unbalanced bids in terms of ITB clause 40, in the form detailed in ITB Clause 45 for amounts[[45]](#footnote-45) of Rs. \_\_\_\_ and Rs \_\_\_\_\_\_ specified therein, within 21 days of the receipt of this letter of acceptance, and visit this office to sign the contract, failing which action as stated in ITB Clause 45.2 will be taken. The securities shall be valid up to 28 days from the date of completion i.e. up to …………. and shall be as per the Performance Security Form and the ESHS Performance Security Form, included in Section X - Contract Forms, of the bidding document.

We have reviewed the construction methodology submitted by you alongwith the bid in response to ITB Clause 16 and our comments are given in the attachment. You are requested to submit a revised Program including environmental management plan as per Clause 26 of General Conditions of Contract within 14 days of receipt of this letter of acceptance.

Yours faithfully,

Authorized Signature………………………..

Name and Title of Signatory…………………

Name of Agency……………………………..

Issue of Notice to proceed with the work

(letterhead of the Employer)

\_\_\_\_\_\_\_\_\_ (*date*)

To

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (*name and address of the Contractor)*

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Dear Sirs:

Pursuant to your furnishing the requisite securities as stipulated in ITB clause 45.1, insurance policy as per GCC 13, construction methodology as stated in letter of acceptance and signing of the contract agreement for the construction of\_\_\_\_\_\_\_\_\_\_\_\_\_\_@ a Bid Price of Rs.\_\_\_\_\_\_\_\_\_\_\_, you are hereby instructed to proceed with the execution of the said works in accordance with the contract documents.

Yours faithfully,

(Signature, name and title of signatory authorized to sign on behalf of Employer)

**Attachment: Contract Agreement**

Contract Agreement

THIS AGREEMENT made the . . . . . . day of . . . . . . . . . . . . . . . . ., . . . . . . ., between . . . . . ***[name of the*** Employer***]***. . . . . . . . . . (hereinafter “the Employer”), of the one part, and . . . . . ***[name of the Contractor]***. . . . .(hereinafter “the Contractor”), of the other part:

WHEREAS the Employer desires that the Works known as . . . . . ***[name of the Contract]****. . . . .*should be executed by the Contractor, and has accepted a Bid by the Contractor for the execution and completion of these Works and the remedying of any defects therein,

The Employer and the Contractor agree as follows:

1. In this Agreement words and expressions shall have the same meanings as are respectively assigned to them in the Contract documents referred to.

2. The following documents shall be deemed to form and be read and construed as part of this Agreement. This Agreement shall prevail over all other Contract documents.

* + 1. this Agreement
    2. the Letter of Acceptance
    3. the Contractor’s Bid including completed schedules and priced bill of quantities,
    4. the Addenda No’s . . . . . ***[insert addenda numbers if any]***. . . . .
    5. the Particular Conditions of contract
    6. the General Conditions of contract;
    7. the Specifications
    8. the Drawings*;* and
    9. Construction Program, Methodology, Quality Assurance Program and Environmental Management Plan
    10. Joint Venture Agreement [for JVs only]
    11. Any other document listed in PCC as forming part of the Contract

3. In consideration of the payments to be made by the Employer to the Contractor as indicated in this Agreement, the Contractor hereby covenants with the Employer to execute the Works and to remedy defects therein in conformity in all respects with the provisions of the Contract.

4. The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein, the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties hereto have caused this Agreement to be executed in accordance with the laws of . . . . . [name of the borrowing country]. . . . .on the day, month and year indicated above.

|  |  |  |  |
| --- | --- | --- | --- |
| Signed by: |  | Signed by: |  |
| for and on behalf of the Employer | | for and on behalf the Contractor | |
| in the presence of: |  | in the presence of: |  |
| Witness, Name, Signature, Address, Date | | Witness, Name, Signature, Address, Date | |

**Performance Security - Bank Guarantee**

**[including Additional Performance Security for unbalanced bids]**

*[Guarantor letterhead or SWIFT identifier code]*

Performance Guarantee No…………………….*[insert guarantee reference number]*

Date………………………….*[insert date of issue of the guarantee]*

To: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[name of Employer]*

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[address of Employer]*

WHEREAS \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[name and address of Contractor[[46]](#footnote-46)]* (hereinafter called "the Contractor") has undertaken, in pursuance of Contract No. \_\_\_\_\_ dated \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ to execute \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[name of Contract and brief description of Works]* (hereinafter called "the Contract");

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognized bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE we hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[amount of guarantee[[47]](#footnote-47)]* \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[in words]*, such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[amount of guarantee]* as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition or modification.

This guarantee shall be valid until ……… (i.e.) 28 days from the date of expiry of the Defects Liability Period, and any demand for payment under it must be received by us at this office on or before that date.

Signature and seal of the guarantor \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Name of Bank \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Address \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

***Note: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.***

**Environmental, Social, Health and Safety (ESHS)**

**Performance Security - Bank Guarantee**

*[Guarantor letterhead or SWIFT identifier code]*

ESHS Performance Guarantee No…………………….*[insert guarantee reference number]*

Date………………………….*[insert date of issue of the guarantee]*

To: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[name of Employer]*

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[address of Employer]*

WHEREAS \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[name and address of Contractor[[48]](#footnote-48)]* (hereinafter called "the Contractor") has undertaken, in pursuance of Contract No. \_\_\_\_\_ dated \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ to execute \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[name of Contract and brief description of Works]* (hereinafter called "the Contract");

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognized bank for the sum specified therein as security for compliance with Environmental, Social, Health and/or Safety (ESHS) obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE we hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[amount of guarantee[[49]](#footnote-49)]* \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[in words]*, such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[amount of guarantee]* as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition or modification.

This guarantee shall be valid until ……… (i.e.) 28 days from the date of expiry of the Defects Liability Period, and any demand for payment under it must be received by us at this office on or before that date.

Signature and seal of the guarantor \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Name of Bank \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Address \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

***Note: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.***

**Advance Payment Security**

**Demand Guarantee**

*[Guarantor letterhead or SWIFT identifier code]*

Advance Payment Guarantee No…………………….*[insert guarantee reference number]*

Date………………………….*[insert date of issue of the guarantee]*

To: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[name of Employer]*

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[address of Employer]*

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*[name of Contract]*

Gentlemen:

In accordance with the provisions of the Conditions of Contract, Sub-clause 49.1 ("Advance Payment") of the above-mentioned Contract, \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[name and address of Contractor[[50]](#footnote-50)]* (hereinafter called "the Contractor") shall deposit with \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_­\_\_\_\_\_\_ *[name of Employer]* a bank guarantee to guarantee his proper and faithful performance under the said Clause of the Contract in an amount of \_\_\_\_\_\_\_\_\_\_\_\_\_ *[amount of guarantee**[[51]](#footnote-51)]* \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[in words]*.

We, the \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[bank or financial institution]*, as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligator and not as Surety merely, the payment to \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[name of Employer]* on his first demand without whatsoever right of objection on our part and without his first claim to the Contractor, in the amount not exceeding \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ [amount of guarantee] \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[in words]*.

We further agree that no change or addition to or other modification of the terms of the Contract or of Works to be performed thereunder or of any of the Contract documents which may be made between \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[name of Employer]* and the Contractor, shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition or modification.

This guarantee shall remain valid and in full effect from the date of the advance payment under the Contract until \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[name of Employer]* receives full repayment of the same amount from the Contractor. Consequently any demand for payment under this guarantee must be received by us at this office on or before that date.

Yours truly,

Signature and seal: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Name of Bank: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Address: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

***Note: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.***

**Retention Money Security**

**Demand Guarantee**

*[Guarantor letterhead or SWIFT identifier code]*

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[Bank’s name and address of issuing branch or office]*

**Beneficiary: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_** *[Name and Address of Employer]*

***Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_***

**RETENTION MONEY GUARANTEE NO.: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

We have been informed that \_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[name of contractor[[52]](#footnote-52)]* (hereinafter called “the Contractor”) has entered into Contract No. \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[reference number of the contract]* dated \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ with you, for the execution of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[name of contract and brief description of Works]* (hereinafter called “the Contract”).

Furthermore, we understand that, according to the conditions of the Contract, when the Taking-Over Certificate has been issued for the Works and the first half of the Retention Money has been certified for payment, payment of \_\_\_\_\_\_\_\_\_\_\_ *[insert* the second half of the Retention Money*]* is to be made against a Retention Money guarantee.

At the request of the contractor, we \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*[name of Bank]* hereby irrevocably undertake to pay you the sum or sums not exceeding in total an amount of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[amount in Rupees]* (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_) *[amount in words[[53]](#footnote-53)]* upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation under the Contract without cavil or argument.

It is a condition for any claim and payment under this guarantee to be made that the payment of the second half of the Retention Money referred to above must have been received by the Contractor on its account number \_\_\_\_\_\_\_\_\_ at \_\_\_\_\_\_\_\_\_\_\_ *[name and address of Bank].*

This guarantee shall expire, at the latest, 21 days after the date when the Employer has received a copy of the Defects Liability Certificate issued by the Project Manager. Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

*\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

*[Signature(s) and seal of the guarantor]*

*Note: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.*

1. The firms that qualify technically shall be notified subsequently for opening of the financial part of their bids. [↑](#footnote-ref-1)
2. W*here Bids are invited concurrently for multiple contracts, add a new para. 5 as follows: “Bidders may bid for one or several contracts, as further defined in the bidding document. Bidders wishing to offer discounts in case they are awarded more than one contract will be allowed to do so, provided those discounts are included in the Letter of Bid.” and renumber paras 5 – 11.* [↑](#footnote-ref-2)
3. If needed, Employer may attach minimum requirements for ESHS Management Strategies and Implementation Plans and ESHS Code of Conduct. [↑](#footnote-ref-3)
4. Non-performance, as decided by the Employer, shall include all contracts where (a) nonperformance was not challenged by the contractor, including through referral to the dispute resolution mechanism under the respective contract, and (b) contracts that were so challenged but fully settled against the contractor. Non-performance shall not include contracts where Employers decision was overruled by the dispute resolution mechanism. Non-performance must be based on all information on fully settled disputes or litigation, i.e. dispute or litigation that has been resolved in accordance with the dispute resolution mechanism under the respective contract and where all appeal instances available to the Bidder have been exhausted. [↑](#footnote-ref-4)
5. The Bidder shall provide accurate information on the letter of Bid about any litigation or arbitration resulting from contracts completed or ongoing under its execution over the last five years. A consistent history of court/arbitral awards against the Bidder or any member of a joint venture may result in disqualifying the Bidder. [↑](#footnote-ref-5)
6. The Employer may use this information to seek further information or clarifications in carrying out its due diligence. [↑](#footnote-ref-6)
7. At………………………..price level. Financial turnover of previous years shall be given weightage @5% per year based on rupees value to bring them to the price level of the financial year in which bids are received. [↑](#footnote-ref-7)
8. For contracts under which the Bidder participated as a joint venture member or sub-contractor, only the Bidder’s share, by value, shall be considered to meet this requirement. [↑](#footnote-ref-8)
9. At …………………...price level. Cost of completed works of previous years shall be given weightage @5% per year based on rupees value to bring them to the price level of the financial year in which bids are received. [↑](#footnote-ref-9)
10. In case appointment of Adjudicator was proposed from the list provided by an Institution in ITB 46, the replacement should also be proposed from the list of same institution. [↑](#footnote-ref-10)
11. Use one of the two options as appropriate***.*** [↑](#footnote-ref-11)
12. Immediately preceding the financial year in which bids are received. [↑](#footnote-ref-12)
13. If applicable [↑](#footnote-ref-13)
14. Immediately preceding the financial year in which bids are received. [↑](#footnote-ref-14)
15. *In the case of a JV, the bidder should be stated as “a Joint Venture consisting of ………., and …….”.* [↑](#footnote-ref-15)
16. *The Bidder should insert the amount of the guarantee in words and figures denominated in Indian Rupees. This figure should be the same as shown in Clause 19.1 of the Instructions to Bidders.* [↑](#footnote-ref-16)
17. *45 days after the end of the validity period of the Bid.* [↑](#footnote-ref-17)
18. ***If none has been paid or is to be paid, indicate “none”.*** [↑](#footnote-ref-18)
19. The total amount is automatically calculated by the e-procurement system, from unit rates and quantities, where the e-procurement system supports such functionality [↑](#footnote-ref-19)
20. The amount in words is automatically populated by the e-procurement system, where the e-procurement system supports such functionality [↑](#footnote-ref-20)
21. In this context, any action to influence the procurement process or contract execution for undue advantage is improper. [↑](#footnote-ref-21)
22. For the purpose of this sub-paragraph, “*another party*” refers to a public official acting in relation to the procurement process or contract execution. In this context, “*public official*” includes World Bank staff and employees of other organizations taking or reviewing procurement decisions. [↑](#footnote-ref-22)
23. For the purpose of this sub-paragraph, “party” refers to a public official; the terms “benefit” and “obligation” relate to the procurement process or contract execution; and the “act or omission” is intended to influence the procurement process or contract execution. [↑](#footnote-ref-23)
24. For the purpose of this sub-paragraph, “parties” refers to participants in the procurement process (including public officials) attempting either themselves, or through another person or entity not participating in the procurement or selection process, to simulate competition or to establish bid prices at artificial, non-competitive levels, or are privy to each other’s bid prices or other conditions. [↑](#footnote-ref-24)
25. For the purpose of this sub-paragraph, “party” refers to a participant in the procurement process or contract execution. [↑](#footnote-ref-25)
26. A firm or individual may be declared ineligible to be awarded a Bank financed contract upon: (i) completion of the Bank’s sanctions proceedings as per its sanctions procedures, including, inter alia, cross-debarment as agreed with other International Financial Institutions, including Multilateral Development Banks, and through the application the World Bank Group corporate administrative procurement sanctions procedures for fraud and corruption; and (ii) as a result of temporary suspension or early temporary suspension in connection with an ongoing sanctions proceeding. See footnote 14 and paragraph 8 of Appendix 1 of these Guidelines. [↑](#footnote-ref-26)
27. A nominated sub-contractor, consultant, manufacturer or supplier, or service provider (different names are used depending on the particular bidding document) is one which has either been: (i) included by the bidder in its pre-qualification application or bid because it brings specific and critical experience and know-how that allow the bidder to meet the qualification requirements for the particular bid; or (ii) appointed by the Borrower. [↑](#footnote-ref-27)
28. The method of measurement should be spelled out precisely in the Preamble to the Bill of Quantities, describing for example the allowances (if any) for timbering in excavation, etc. Many national standard reference guides have been prepared on the subject, and one such guide is the *Standard Method of Measurement* of the U.K. Institution of Civil Engineers. [↑](#footnote-ref-28)
29. Based on Government Directives. [↑](#footnote-ref-29)
30. In this context, any action to influence the procurement process or contract execution for undue advantage is improper. [↑](#footnote-ref-30)
31. For the purpose of this sub-paragraph, “*another party*” refers to a public official acting in relation to the procurement process or contract execution. In this context, “*public official*” includes World Bank staff and employees of other organizations taking or reviewing procurement decisions. [↑](#footnote-ref-31)
32. For the purpose of this sub-paragraph, “party” refers to a public official; the terms “benefit” and “obligation” relate to the procurement process or contract execution; and the “act or omission” is intended to influence the procurement process or contract execution. [↑](#footnote-ref-32)
33. For the purpose of this sub-paragraph, “parties” refers to participants in the procurement process (including public officials) attempting either themselves, or through another person or entity not participating in the procurement or selection process, to simulate competition or to establish bid prices at artificial, non-competitive levels, or are privy to each other’s bid prices or other conditions. [↑](#footnote-ref-33)
34. For the purpose of this sub-paragraph, “party” refers to a participant in the procurement process or contract execution. [↑](#footnote-ref-34)
35. A firm or individual may be declared ineligible to be awarded a Bank financed contract upon: (i) completion of the Bank’s sanctions proceedings as per its sanctions procedures, including, inter alia, cross-debarment as agreed with other International Financial Institutions, including Multilateral Development Banks, and through the application the World Bank Group corporate administrative procurement sanctions procedures for fraud and corruption; and (ii) as a result of temporary suspension or early temporary suspension in connection with an ongoing sanctions proceeding. See footnote 14 and paragraph 8 of Appendix 1 of these Guidelines. [↑](#footnote-ref-35)
36. A nominated sub-contractor, consultant, manufacturer or supplier, or service provider (different names are used depending on the particular bidding document) is one which has either been: (i) included by the bidder in its pre-qualification application or bid because it brings specific and critical experience and know-how that allow the bidder to meet the qualification requirements for the particular bid; or (ii) appointed by the Borrower. [↑](#footnote-ref-36)
37. This list is only illustrative and not exhaustive. Bidders and Contractors are responsible for checking the correctness and completeness of the list. The law as current on the date of bid opening will apply. [↑](#footnote-ref-37)
38. The Centre to be specified should be the relevant one for which CPI is published by the Labour Bureau. [↑](#footnote-ref-38)
39. The PCC specifies the identified depot for the rate of diesel for the base date and the applicable date for price adjustment. [↑](#footnote-ref-39)
40. The PCC specifies the identified refinery for the rate of Bitumen for the base date and the applicable date price adjustment. [↑](#footnote-ref-40)
41. If ITB 43 makes provision of an Adjudicator from list provided by an institution, kindly modify Appendix 3 to state that the fee and reimbursable payable to the adjudicator shall be as per the rules of the Institution. [↑](#footnote-ref-41)
42. *Delete “corrected and” or “and modified” if not applicable. See Notes on Standard Form of Agreement, next page.* [↑](#footnote-ref-42)
43. *To be used only if the Contractor disagrees in the Bid with the Adjudicator proposed by the Employer in the Instructions to Bidders, and has accordingly offered another candidate.*  [↑](#footnote-ref-43)
44. *To be used only if the Contractor disagrees in the Bid with the Adjudicator proposed by the Employer in the ITB, has accordingly offered another candidate, and the Employer does not accept the counterproposal.* [↑](#footnote-ref-44)
45. *Insert amounts for (i) Performance Security, plus additional security for unbalanced bids; and (ii) ESHS Performance Security respectively.* [↑](#footnote-ref-45)
46. *In the case of a JV, insert the name of the Joint Venture* [↑](#footnote-ref-46)
47. *An amount shall be inserted by the Guarantor, representing the percentage of the Contract Price specified in the Contract less provisional sum if any, plus additional performance security for unbalanced bids if any, and denominated in Indian Rupees.* [↑](#footnote-ref-47)
48. *In the case of a JV, insert the name of the Joint Venture* [↑](#footnote-ref-48)
49. *An amount shall be inserted by the Guarantor, representing the percentage of the Contract Price specified in the Contract less provisional sum if any, and denominated in Indian Rupees.* [↑](#footnote-ref-49)
50. In the case of a JV, insert the name of the Joint Venture [↑](#footnote-ref-50)
51. An amount shall be inserted by the bank representing the amount of the Advance Payment, and denominated in Indian Rupees. [↑](#footnote-ref-51)
52. *In the case of a JV, insert the name of the Joint Venture* [↑](#footnote-ref-52)
53. *The Guarantor shall insert an amount representing the amount of the second half of the Retention Money.* [↑](#footnote-ref-53)